NCCR: 1st Progress Report - Cover Sheet

| Title of the NCCR | Origin, Evolution and Characterisation of Planets |
| --- | --- |
| NCCR Director Name, first name Institution | Prof. Dr. Willy Benz University of Bern |
| Date of submission |  |

NCCR PlanetS Office, Physikalisches Institut, Universität Bern, Sidlerstr. 5, CH-3012 Bern

Table of Content

1.	Executive Summary	4

2.	Research	8

2.1 Scientific development of the NCCR and status of integration	9

2.1.1 Implemented structure and integration status of the NCCR	9

2.1.2 Scientific development of the NCCR	14

2.1.3 Development of the coordinating role of the NCCR	16

2.2 Objectives of the research units, first achievements	17

2.2.1 Research projects	17

Project 1:  Circumstellar discs and planetary systems	18

Project 2:  Origin and Evolution of Volatiles in Planets	23

Project 3:  Atmospheres of exoplanets	27

Project 4:  Solar system remote sensing	35

Project 5:  Planet Formation and Evolution	41

Project 6:  Numerical Laboratory for Planet Formation	50

Project 7:  Multi-faceted determination of planet properties and system architecture	56

2.2.2 Research platforms	67

Platform DACE:  Data and Analysis Center for Exoplanets	68

Platform CHEOPS	72

3.	Knowledge and Technology Transfer	74

4.	Education and training	76

5.	Equal opportunities	78

6.	Communication	80

7.	Structural aspects	83

8.	Management	88

8.1 Overall PlanetS management	88

8.2 Geneva Management Office	90

9.	Lists	92

9.1 Overview of personnel and functions	92

9.2 Education and training	92

9.3 Publications	92

9.4 Lectures at congresses etc.	92

9.5 Services, patents, licences, start-up companies etc.	92

9.6 Cooperation with third parties	92

10.	Statistical output data	92

11.	Finance	92

11.1 Finance NCCR Overview	92

11.2 Funding sources	92

11.3 Allocation to projects	93

11.4 Expenditures	93

11.5 Comments on finances	93

12.	Annexe 1: Strategy for Knowledge and Technology Transfer (KTT)	95

12.1 Scope of the document	95

12.2 Current State and Aimed Goals	95

12.2.1 Assessment of the current state and general goals of the Technology Platform	95

12.2.2 Areas of intervention	96

12.3 Organisation and Resources Allocation within the Platform	97

12.3.1 Organisation	97

12.3.2 Use of funding	97

12.3.3 Seed funding for R&D projects	98

12.4 Action Plan	99

12.5 Examples for the Technology Platform activities	99

12.5.1 External mandate	99

12.5.2 CTI project	100

12.5.3 R&D project	100

13.	Annexe 2: Strategy for Education and Training	101

13.1 Assessment of the current state	101

13.2 Areas of intervention	101

13.2.1 Target Groups and Goals:	101

13.2.2 Measures for Intervention:	102

13.2.3 Tools	103

13.2.4 Metrics for Success	103

13.3 Resource allocation and organisation	103

13.4 Action Plan	104

14.	Annexe 3: Strategy for Equal Opportunities	107

14.1 Assessment of the current state	107

14.1.1 Gender diversity situation in Switzerland and Europe	107

14.1.2 Current state of gender diversity in the NCCR PlanetS	107

14.1.3 General Assembly, Anzère, Switzerland, January 2015	108

14.2 Areas of intervention	108

14.3 Resource allocation and organisation	109

14.4 Action plan	109

15.	Annexe 4: Communication Strategy	115

15.1 Starting point and analysis	115

15.1.1 The NCCR PlanetS	115

15.1.2 Vision	115

15.1.3 Mission	115

15.2 Communication	115

15.3 Communication objectives	116

15.4 Communication Strategy 2014 – 2018	118

15.5 Target groups & Messages	118

15.6 Communication style	120

15.7 Marketing Activities	120

15.8 Budget	123

15.9 Organisation	123

15.10 Evaluation	123

15.11 Communication channels	124

# Executive Summary

The search for planetary systems orbiting other stars has demonstrated that planets are extremely common objects. While the quest to find bodies similar to the Earth is still ongoing, the first spectra of exoplanets have been taken, signalling the shift from an era of discovery to one of physical and chemical characterisation. The National Centre for Competence in Research (NCCR) PlanetS has been designed to respond to this shift by providing an interdisciplinary national research programme dedicated to the study of the origin and evolution of planets and their characterisation.

The Swiss National Science Foundation established the NCCR PlanetS in June 2014. It brings together researchers from the Universities of Berne (UBE, Leading House), Geneva (UGE, co-Leading House), and Zürich (UZH) as well as of the ETHs Zürich (ETHZ) and Lausanne (EPFL).

By establishing a unified research framework, PlanetS provides the opportunity to tackle the increasingly multi-disciplinary challenges associated with our rapidly expanding field of research. Building upon a very solid and broad base of existing research in planetary sciences in Switzerland, PlanetS is structured around seven research projects and five platforms, ensuring a leading scientific expertise within a framework fostering collaborations and synergy.

The research within PlanetS follows two tracks concurrently. On one hand, it capitalises on past investments by exploiting data acquired by space missions, ground-based instrumentation, theoretical models and laboratory infrastructures. On the other hand, PlanetS invests in new area and prepares for the future by developing new joint competences in research.

Eight months after its official start, the structures of PlanetS have been set-up, the new collaborators have been hired, the teams have been organised, the routines have been established and the research has started.

The following highlights in research activities can already be mentioned:

- Project 1: Circumstellar discs and planetary systems: The discovery of two new young planet candidates through high-contrast imaging and advances in the commissioning of the SPHERE instrument on the VLT.

- Project 2: Origin and evolution of volatiles in planets: The definition of new analytical methods for high-precision elemental and isotopic studies together with the analysis of the first samples.

- Project 3: Atmospheres of exoplanets: The extension of the capabilities of present instrumentation (e.g. HARPS) and software for the observation of exoplanetary atmospheres.

- Project 4: Solar system remote sensing: The new optical coherence tomography experiment has been set-up and is running. The evolution of samples is followed in a thermal vacuum chamber. First application to the nucleus of comet 67P/Churyumov-Gerasimenko is ongoing.

- Project 5: Planet Formation and evolution: The viscous diffusion of the gas in the protoplanetary disc sets the C/O dispersion in giant planet envelopes. A diagnostic tool to interpret sodium line measurements in atmospheres has been developed.

- Project 6: Numerical Laboratory for planet formation: 3D self-gravitating disc simulations have been started. The new GENGA N-body code has entered production phase and is now routinely used across several projects.

- Project 7: Multi-faceted determination of planet properties and system architecture: The analytical framework developed to study the long-term evolution of planetary systems including dissipative effects is being applied to study TTVs in the Kepler data, and the commissioning of the SPHERE instrument and of the Next Generation Transit Search facility in Paranal.

Concurrently to the research projects, PlanetS is developing five platforms with the aim to foster collaboration and synergy. Two of them also have clear scientific goals (DACE and CHEOPS) while the other three are more organisational in nature (Communication and Outreach, Technology, Academic Coordination). All five platforms are now operational.

The following highlights in the platform activities can be mentioned:

- DACE: The formal kick-off of the platform took place on January 16th 2015 and the technical development is ongoing. Visualisation and data exchange tools are being developed within the platform to facilitate the comparison of theoretical and observational data. Sophisticated data analysis tools developed by the various projects are being incorporated into DACE (http://dace.unige.ch).

- CHEOPS: The first two CHEOPS PhD student projects have been selected with work to begin June 1st 2015. Hiring of the candidates is on going.

- Technology transfer: A meeting with external experts to define the technology transfer strategy was held and contacts with the NCCR MUST are ongoing. An external expert with a large experience in industry has the mandate of ensuring a good match between the planned activities and the needs by the private sector. A paper describing the transfer strategy of PlanetS was written.

- Academic Coordination: The collaborators of the platform have been hired, and the structure of the platform has been set up. On the Education and Training side, a survey of the needs of NCCR members has been performed and is presently being analysed. On the Equal Opportunity side, the first actions on gender equality have been undertaken during the first General Assembly in Anzère. Two papers have been written describing the strategy of the platform as well as our strategy in the specific domain of Equal Opportunity.

- Communication and Outreach: The first Newsletter was issued and a second one is imminent. The official website was launched. A plaque with engraved children drawings destined to fly on the CHEOPS satellite is in preparation. A major project related to the exhibit in the Muséum d’histoire naturelle in Geneva marking the 20th anniversary of the discovery of 51 Peg b has been started with an inauguration planed for March 2015 (http://www.ville-ge.ch/mhng/expo_2015_exoplanetes.php). A paper describing the communication and outreach strategy of PlanetS was written.

In addition an administrative structure and team has been put into place and is functioning. Points of contact within this structure at each project/platform location ensure a smooth global working of operations.

The Executive Board is meeting regularly (at least once every 3 months) to discuss and decide on the main priorities within PlanetS activities. It also took on the task to define a national roadmap for ground-based instrumentation related to exoplanet detection and characterisation for the E-ELT and more generally for all ESO facilities.

The PlanetS Advisory Board has been created and so far two distinguished scientists have been appointed to this Board. The first one is Prof. Michel Mayor, discoverer of the first exoplanet. He brings deep insights in the field of exoplanets and has a wealth of knowledge on the Swiss astronomical research landscape. The second is Prof. Brian Schmidt, Nobel Prize winner in Physics 2011. As one of the top executives in the Arc Centre of Excellence CAASTRO in Australia, he brings a broad knowledge of and experience in the organisation of large multi-disciplinary research programs. In addition, as the chair of the gender action committee in CAASTRO, he advises us also on our actions in this area. We plan in the coming month to recruit 2-3 additional Board members specialised in solar system science and technology transfer.

The first PlanetS General Assembly (GA) was held on January 28th-30th 2015 in Anzère, Valais. Nearly 100 participants attended this GA during which the entire NCCR was presented. Ample time for discussions allowed seeding a number of future joint actions. Both members of the Advisory Board attended the meeting and provided feedback in an open session at the end of the GA.

The structural measures planed at local level are being implemented as foreseen (see Sect. 7).

# Research

The discovery in 1995 of the first giant planet outside our solar system by the Swiss astronomers Prof. Michel Mayor and Prof. Didier Queloz spawned a unique revolution in modern astronomy. Since then, the progress has been such that the field is now shifting from an era of discovery to one of physical and chemical characterisation. The National Centre for Competence in Research (NCCR) PlanetS is been designed to respond to this shift by providing an interdisciplinary research programme dedicated to the study of the origin and the evolution of planets as well as their characterisation.

The NCCR PlanetS was selected by the State Secretariat for Education, Research, and Innovation (SERI) in December 2013 and established by the Swiss National Science Foundation in June 2014. This Centre brings together researchers from the Universities of Berne (UBE, Leading House), Geneva (UGE, co-Leading House), and Zürich (UZH) as well as of the ETHs Zürich (ETHZ) and Lausanne (EPFL).

The goal of PlanetS is to set up a truly multi-disciplinary national centre of competence for the search, characterisation and study of planetary systems and their suitability to harbour life. Pulling together the existing know-how in all aspects of astrophysics, space exploration, planetary sciences, geosciences, cosmochemistry and high-tech optical and mechanical systems will achieve this. PlanetS is serving as a national focal point for organising instrumental developments, carrying out laboratory analyses, fostering new theoretical developments, coordinating education of doctoral students and outreach activities. Our long-term vision is to use the NCCR to setup a permanent Swiss Institute for Planetary Sciences (SIPS).

While PlanetS builds upon a very solid base of existing research in planetary sciences in Switzerland, it allows for important new developments. These are needed if Switzerland is to continue to play a leadership role internationally in this very competitive field of astronomy. Fig. 2.1 illustrates the overall concept of our NCCR. The new activities (research projects and platforms) within PlanetS complement each other and together with the existing activities reveal the broader picture and allow for new insights.

Fig. 2.1: The NCCR activities complement each other and those already carried out in Switzerland (lighter colours). Together they constitute a comprehensive effort. The platforms provide the essential structuring and enabling elements of the NCCR.

By establishing a unified framework, PlanetS provides the opportunity to answer the increasingly multi-disciplinary challenges associated with our rapidly expanding field of research. Building upon a very solid and broad base of existing research in planetary sciences in Switzerland, PlanetS is structured around seven research projects and five platforms, ensuring a leading scientific expertise within a framework fostering collaborations and synergy.

The research within PlanetS follows two tracks concurrently. On one hand, it capitalises on past investments by exploiting data delivered by various space missions, ground-based instrumentation, theoretical models, or laboratory infrastructure. On the other hand, PlanetS invests in new area and prepares for the future by developing new competences in research.

## 2.1 Scientific development of the NCCR and status of integration

Eight months after its official start, the structures of PlanetS have been set-up, the new collaborators have been hired, the teams have been organised, the routines have been established and the research has started. In the following, we detail the different steps undertaken in research as well as in all other domains of action.

### 2.1.1 Implemented structure and integration status of the NCCR

To achieve the goals of PlanetS, we have structured our NCCR into two distinct basic units: research projects and platforms. Research projects are units defined with a clear scientific goal and grouping together researchers from different institutions. Platforms are units defined with the clear task to serve all research projects, providing structure, promoting exchanges and building synergies. An overview of the resulting NCCR structure is given in Fig. 2.2.

Fig. 2.2: Organisation of the NCCR. The direction of the NCCR is under the responsibility of the Director and Co-Director, assisted by the Executive Board, and advised by the Advisory Board. The Management of the NCCR comprises the Scientific Coordination, the Administration, the ‘Communication and Outreach’, ‘Academic Coordination’ and the ‘Technology’ platforms, each of them being led by a member of the Executive Board. The Director and the Co-Director lead two scientific platforms (CHEOPS and DACE), and a member of the Executive Board leads each of the seven research projects. Each project is sub-divided into a number of sub-projects addressing different aspects and being led by sub-project leaders.

The seven research projects have been defined to address the main research goals of PlanetS while taking into account the existing expertise in the different institutes across Switzerland. We have pooled geographically dispersed scientific resources into a set of coherent research projects with the goal of improving efficiency and building synergies. As a result, a number of research projects are carried out at more than one institution. This is, in particular, the case for Projects 2, 4 and 5. In addition, some research projects have hired joint PhD students leading to even stronger connections. The organisation of the seven research projects and their sub-projects in terms of collaboration between institutions is illustrated in Fig. 2.3. In this figure, the various institutions are colour-coded in order to highlight their contribution to single research projects.

Fig. 2.3: Overview of the seven research projects and their different sub-projects in terms of institutional distribution (the institution’s colour code is indicated on the right). Three projects are actually distributed on two sites (large bi-colour arrows on the left), some are carried out in collaboration with teams from other institutions (small arrows on the right). The small lines on the right connecting institutions indicate shared PhD students.

The members of a research project are scientists either specifically hired by PlanetS or belonging to already existing research teams, possibly located at different institutions. By assembling individual research groups into larger research projects we create new entities that are tailored to the scientific goals of PlanetS. This enables interactions between otherwise disseminated groups very early in the process of scientific investigation. We believe that such early involvement is essential for all parties in order to build a sense of ownership of the research project, which is an essential step for successful teamwork.

We caution here that in a metric in which collaboration within an NCCR is judged from the number of joint publications between research groups, having larger research groups is a clear drawback. Such bibliometric measurements will not capture the fact that individual research groups are already of a collaborative nature.

To provide structure and to allow building synergy, our NCCR PlanetS has five platforms. Each platform has a coordinator and, for some of them, a co-coordinator.

| Platform | Coordinator | Co-Coordinator |
| --- | --- | --- |
| Technology transfer | Prof. F. Pepe (UGE) | Prof. N. Thomas (UBE) |
| Academic Coordination | Prof. M. Meyer (ETHZ) | Prof. M. Schönbächler (ETHZ) |
| Communication and Outreach | Prof. W. Benz (UBE) | Prof. B. Moore (UZH) |
| CHEOPS | Prof. W. Benz (UBE) |  |
| DACE | Prof. S. Udry (UGE) |  |

These coordinators are also members of the Executive Board. Three platforms are associated to the management of the NCCR: Technology Transfer (TT), Academic Coordination, and Communication and Outreach. The other two platforms have of a more scientific nature and will be presented further below.

We note that our platforms are not a one-to-one match to the action domains as foreseen by SNF. Fig. 2.4 provides the mapping between the SNF defined domains of action and the PlanetS platforms.

Fig. 2.4: Mapping of the SNF defined domains of actions on the NCCR PlanetS platforms.

This re-definition of the domains of actions has been motivated by the fact that we believe that the methodology, as well as the content of the message to be delivered must be tailored to the target audience. Schools and the general public have very different needs/expectations than young scientists working in academia or private industry. We have therefore designed the three platforms with the target population in mind rather than focusing on the general tasks to be accomplished. In this way, each platform can be specialised to address a relatively homogeneous audience and corresponding specialists have been hired (or will be soon) to carry out the work professionally. Dealing both with internal and external communication, the Communication and Outreach Platform is possibly the least homogeneous of the platforms, but adequate staffing mitigates this. At the request of the SNF, we deliver are a separate paper on equal opportunity. More details on the actions and strategies defined for these platforms can be found elsewhere in this report (Sect. 3 to 6 and Annexes 1 to 4).

Technology Platform

Advances in the study of planets rely on new observations and new measurements, which themselves are enabled by the development of new technologies. As such, astronomy and space sciences have a role of technology driver. In the framework of PlanetS we aim at developing a strategy on a Swiss scale, involving in a symmetric way partners from Universities, Technical Universities, Industry and other institutions related to astronomy. The goal is to bring these partners together, promote exchange of information and knowledge, develop and exploit synergies, and promote and coordinate R&D activities. The capability of relying on proven and innovative technology is very important if Switzerland is to keep an important role in the development of future ESO or ESA missions. The actions already taken in the framework of the Technology Platform, as well as the strategy for the future, are presented respectively in Sect. 3 and Annexe 1 of this report.

Academic Coordination Platform

This platform regroups all the actions related to the interactions between the NCCR and the academic world. This includes the development of a doctoral network, the mobility and career advancement of young scientists, distinguished visitor programme, etc. This platform also has gender equality as one of its main responsibility as some of the actions that can be taken to eliminate women specific barriers concern the academic environment. However, we note that completely eliminating these barriers will not lead to parity among permanent faculty members in our field as long as the number of female students in the hard-core natural sciences (e.g. physics) remains so low. Hence, it is of paramount importance to attract the younger girls (high- and middle-school level) to natural sciences. Our outreach programme will aim at this goal.

Communication and Outreach Platform

This platform is in charge of all aspects of communication and of outreach activities. Communication includes internal communication (flow of information within the NCCR, team building, etc.) and external communication (scientific community, media, general public, etc.). Outreach activities are connected to exhibitions in museums, special activities in schools, etc.). In many instances (general public, schools, etc.) communication and outreach activities are aimed at the same target groups and require similar approaches. This is why we have moved all activities related to the public at large (young or not) into this platform while knowledge transfer within academia is in the academic platform.

In addition to these general-purpose platforms, PlanetS is also building two distinctly different platforms: CHEOPS and DACE. These two platforms are of a scientific nature but are meant to serve all research projects.

CHEOPS Platform

Its role is to provide the organisation and the funding for high-visibility science exploitation of the CHEOPS mission. While the funding for the Swiss contribution to CHEOPS (prime-ship of payload development and ground segment) is organised through the Swiss State Secretariat for Education, Research and Innovation (SERI), the funding for the science exploitation of the mission has to come through individual research grants. Hence, the NCCR provides a unique opportunity to ensure a substantial and coordinated funding of the science exploitation of the mission. The CHEOPS platform will provide this coordination, and will guarantee a unique visibility of the mission, at the same time ensuring the availability of the broadest possible expertise. For this, a series of competitively attributed CHEOPS PhDs and CHEOPS Fellows will be supported by the NCCR during its existence. During the first months of the NCCR, we began advertising and have selected the first two CHEOPS PhDs, for an expected start in summer 2015. Details on these two projects are presented elsewhere in this report (Sect. 2.2.2). A call for CHEOPS Fellows will be organised in the fall of 2015 to start in 2016.

DACE Platform

This platform is an answer to the dramatic increase in the quantity and diversity of data generated by planetary research, both from the ground and from space. The huge wealth of data makes it very difficult to locate the relevant information and, for example, it is difficult to cross-correlate it with other information in order to understand trends.  Following some earlier initiatives (e.g. the Extrasolar Planets Encyclopaedia or more recently the NASA Exoplanet Archive), the Geneva node has started developing a Data & Analysis Center for Exoplanets. The role of the DACE Platform in the NCCR is to transform the Data & Analysis Center for Exoplanets into a national facility for planetary research. As a NCCR platform, DACE will act as a federating tool for all research projects ranging from observations to simulations. As a result, the DACE Platform will help Swiss astronomers to make the best use of their knowledge, through a platform where data will be stored, shared, compared, analysed, and exchanged. The first steps in the development of the DACE tool are presented elsewhere in this report (Sect. 2.2.2).

Integration indicators

One of the most serious challenge facing PlanetS is to get all the members to function as a team while conserving their local identity. This challenge ultimately stems from the nature of the Swiss political system in which Universities are cantonal entities and ETHs are federal entities. Each team has to conserve its local support and identity while at the same time sharing know-how and expertise with the entire NCCR. This is not easy to achieve. However, we believe that the structures put into place and a good communication will allow us to be successful. Early signs that we are on a good track can be mentioned:

- The Executive board meets on a regular basis (at least every 3 months). All projects leaders report on the progress of their respective projects. The Board then looks for synergies and discusses the initiation of new actions. These discussions are very constructive, as decisions have always been taken in consensus.

- The hiring process of new collaborators (mainly PhD students and postdocs) was centralised and single ads for several positions were issued. This has procured the NCCR with a very large visibility in the community. In addition, the majority of the different applications have been reviewed simultaneously between the different projects, leading to a better overview and ultimately to a better match between projects and applicants.

- A programme of shared PhD students between projects has been initiated. In practice, these students spend the bulk of their time during the first two years with one project learning the skills needed for the second project. After two years, the students move to the second project ready to apply the skills learned. By exchanging young scientists between projects, we expose them to a broader area of science while creating synergy within PlanetS. This approach has also some practical benefits: 1) it minimises travel and 2) it mitigates current complex PhD regulations differences between universities.

- The overall structure of the NCCR was presented and discussed at the first General Assembly of PlanetS held January 28th-30th 2015. Nearly 100 attendees (PlanetS members and associate scientists) participated in the meeting. The NCCR Advisory Board also attended the presentations and provided feedback during an open discussion session.

### 2.1.2 Scientific development of the NCCR

The main focus of these first months of our NCCR was set on building the coherent and integrated structure of PlanetS. This meant for each project and platform to recruit the missing team members and to initiate the new projects. This phase took some time, as finding the appropriate collaborators was not always so easy. As a consequence, for most projects and platforms the actual start of scientific work occurred only a few months ago. Hence, we can only report on a small number of new scientific achievements at this point in time. Highlights are given below, more details can be found in the individual projects and platform reports (Sect. 2.2). This summary is focussed on the contribution of each project towards the overall goals of PlanetS organised around the three themes: Origin, Evolution and Characterisation of planetary systems.

Origin of planetary systems

Projects (1, 2, 5, 6 and 7) contribute to this first theme using very different approaches (observations, laboratory, theory):

- Observations of planets in formation in the HD100546 system, as well as of the associated disc morphology, provide constraints on the timing of giant planet formation, as well as on some key processes (e.g. gap formation) at work during their formation. Such observations are presented in the report of Project 1.

- The chronology of the formation of the solar system can be constrained to a precision that will never be achievable for extra-solar planetary systems. As presented in the report of Project 2, an improved chronology of the timing of volatile delivery to terrestrial planets can be obtained by means of high precision measurement of different chronometers (e.g. the Rb-Sr system) using modern technics (e.g. Thermal Ionisation Mass Spectrometry), or recent facilities (e.g. SwissSims at the university of Lausanne).

- The next generation of planet formation models started in Project 5 include a better treatment of the dynamics of the gas (in multi-dimensions) and planetesimals embedded in the disc as well as the gravitational interactions between massive bodies (during formation and late-time evolution). For these aspects, the use of the new GENGA code (see report of Project 6) will result in a dramatic improvement of the numerical efficiency of planet formation models.

- New very high resolution numerical models have been developed in Project 6, targeting the initial stage or protoplanetary disc  and the formation of planetesimals.

- Finally, on the theoretical front, members of Project 7 have started working on the effect of dissipation in protoplanetary discs and the consequences on the final architecture of planetary systems.

Evolution of planetary systems

The evolution of planetary systems is addressed by considering both solar system bodies and exoplanets.

- The early history of Mars is potentially crucial to the understanding of the evolution of low mass planets, in particular in relation with their habitability. In order to constrain the past water activity and the diversity of climatic conditions during the early history of Mars, members of Project 4 have started the geological characterisation of Light-Toned Layered Deposits (LLD). Apart from their own scientific interest, these studies are used to prepare the target list of the CaSSIS instrument.

- The GPU based GENGA integrator is now being used by members of Projects 5 and 6 to compute systematically the long-term evolution of synthetic planetary systems. It has been implemented in the DACE Platform as well for a real-time 3D visualization of planetary system evolution.

- Members of Project 7 have started the development of semi-analytical methods for celestial dynamics computations. This approach is potentially much faster than direct numerical integration. Once validated, it will be used for two main purposes. Firstly, the classification of planetary systems into stable or unstable systems. Secondly, the determination of possible configurations that can be subsequently refined by algorithms aiming at determining the actual architecture of a system from observational data.

Characterisation of planetary systems

The third theme of PlanetS is the characterisation of planetary systems. Different projects have contributed to this, from the instrumental, to observational and theoretical point of views.

- Using new high contrast imaging algorithms for the search of gas giant planets, members of Project 1 have initiated a search for exoplanets, using direct imaging archival data. This has resulted in the detection of a ~10 Jupiter mass planet, using VLT/NACO data.

- The characterisation of exoplanets using high-resolution spectroscopy is one of the core goals of Project 3. Members of this project have detected sodium in the hot Jupiter HD189733b and have performed an analysis of the upper atmosphere of the hot Neptune GJ436b from HST data. Finally, new observations of water vapour signatures using the same technique have been recently obtained. In parallel to this observational work, members of Project 3 have conducted an upgrade of the CORALIE and HARPS spectrographs.

- In 2014, the first data received from the arrival of the Rosetta spacecraft at its target comet have been one focus of solar system research. Members of Project 4 are actively participating to the characterisation of the 67P/CG comet, in particular by constructing a 3D shape model based on the images taken by the OSIRIS camera on-board Rosetta. These data will be used to shed light on the evolution of cometary bodies, whose structure is believed to be close to the one of planetary building blocks.

- Members of Projects 3 and 5 have started a program to develop an atmospheric retrieval tool in order to interpret future observations. They have also developed a new theoretical model in order to put constraints on the thermodynamical structure of a planetary atmosphere using observations of Alkali metals (e.g. Na).

- Members of Projects 5 and 7 have started working on refining the determination of the exoplanet yield of PLATO, combining real stellar catalogues, realistic transit survey capabilities, and state of the art simulations of radial velocity follow-up performances.

- Collaboration between members of Project 7 and of the DACE Platform has been started, in order to determine Keplerian fits to radial velocity observations. This tool is used in the DACE database for online orbit fitting, and will be extended in the next period to astrometric data as well as to multi-planetary systems. In addition, a Bayesian tool is being developed, as part of Project 7 and of the DACE Platform, to assess the validity of different fits.

- Finally, members of Project 7 are taking an active part in the installation and commissioning of NGTS, the Next Generation Transit Search.

As of February 1st 2015 Dr. Christoph Mordasini joined UBE on a 5-year Starting Grant from SNF. His project entitled “Planets in time” complements the “Origin” and “Evolution” aspects of our NCCR described above. Together with his team (one PhD student and one postdoc) Dr. Mordasini will be associated with the NCCR and in particular with Project 5.

### 2.1.3 Development of the coordinating role of the NCCR

The scientific coordination of the NCCR is under the responsibility of the Director, Co-Director and members of the Executive Board. The Scientific Officer, with the help of the NCCR Programme Office, ensures the implementation and the monitoring of this coordination.

With the development of large ground- and space-based infrastructures priorities have to be assigned for Swiss participation in these projects. In 2007, the Swiss astronomy professors issued a Roadmap for Astronomy in Switzerland 2007-2016. This Roadmap has just been updated to take into account the latest developments. Two members of PlanetS participated actively in the committee assigned to the writing of this update (Prof. Willy Benz, chair of the committee and Prof. Michael Meyer).

This update defined a national strategy over all fields of astronomy (including from space) in Switzerland and issued a set of recommendations. The role of PlanetS is to coordinate at a national level the research in planetary sciences. This includes in particular the definition of the priorities among the various large research infrastructures (ground- or space-based) dedicated to our field of science.

A first exercise in strategic planning has begun and is helping defining the future astronomical instrumentation of the E-ELT in particular and of ESO facilities in general. The Executive Board has appointed a dedicated Working Group (WG) involving all interested parties to discuss these issues. The WG terms of reference include the development of a coherent exoplanet instrument roadmap for the E-ELT and other ESO facilities taking into account the entire future landscape (including space missions). While the process is still ongoing, a first meeting has already allowed identifying a common position. This position was already presented at the ‘ESO in the 2020s’ conference (Prof. Yann Alibert, Munich, January 2015) and a position paper drafted jointly by two sub-project leaders (Dr. Sascha Quanz and Dr. Christophe Lovis) working respectively in Project 1 and 3. This white paper, once approved by the Board, will be distributed to the appropriate decision makers.

## 2.2 Objectives of the research units, first achievements

### 2.2.1 Research projects

PlanetS has seven research projects spreading over the three main scientific themes of the NCCR: Origin, Evolution and Characterisation. Each research project is itself divided into a number of sub-projects. Fig. 2.5 presents this research organisation.

Fig. 2.5: Research project organisation. Each of the seven main projects is divided into a number of sub-projects addressing specific aspects of the research.  This leads to a total of 20 research sub-projects. Most of them are under the responsibilities of a younger scientist.

In this section, we present each of the research projects and its sub-projects separately. We report on their activities and accomplishments during the time since the establishment of PlanetS.

### Project 1:  Circumstellar discs and planetary systems

## Project leader:  Michael R. Meyer – ETH Zurich

### 1. Abstract

Project 1 aims at a) high-spatial resolution observations of protoplanetary discs in order to constrain the initial conditions of planet formation and b) the direct detection and characterisation of exoplanets at large orbital radii. With regard to protoplanetary discs we focussed on the commissioning of the SPHERE instrument and preparation and execution of science verification and early guaranteed time observations. Data for several high-profile targets will be collected in the coming weeks. In the exoplanet detection programme, a key result was the discovery of two new young planet candidates; one embedded in the protoplanetary disc of the Herbig Ae/Be star HD169142, and the other one in the HD61005 debris disc system. In addition, the protoplanet candidate orbiting the Herbig Ae/Be star HD100546 was confirmed with multi-wavelength data. Significant progress has also been made in implementing a spectral retrieval code to determine the atmospheric properties of directly imaged gas giant planets; a first paper is in preparation. Finally, we achieved “first light” in our Laboratory for Astronomical Instrumentation and our involvement in the ERIS project is ongoing. The instrument underwent some significant design simplification to keep it on track for first light at the VLT in 2019.

### 2. Results and achievements since the last report

Protoplanetary discs

A prerequisite for future scientific achievements was the successful commissioning of the SPHERE instrument at the VLT. We are playing a special role on the disc imaging team and utilisation of the ZIMPOL component of SPHERE under the leadership of Prof. Hans Martin Schmid. A series of Science Verification Time (SVT) proposals with ETH participation were carried out successfully in December 2014 and early Guaranteed Time Observations (GTO) have been planned (first observations took place in the first week of February 2015). Several disc imaging papers based on SVT data (e.g., for AU Mic and HD142527) with contributions from ETH are expected to be finalised in the coming weeks. In addition, we are in charge of coordinating the early GTO observations of HD100546 (target coordinator: Quanz) and support those of HD61005 and TW Hya as well as other observations with ZIMPOL. Finally, we were – and still are – involved in a number of observational (visible, NIR, and mm), and theoretical studies concerning the morphology in discs due to the presence of planets including the formation of gaps and other asymmetric structures (see publication list).

Exoplanet Imaging

We have continued work on high contrast imaging algorithm development to search for gas giant planets at thermal infrared wavelengths with NACO on the VLT. A paper presenting the “PynPoint” data analysis package has been accepted for publication in Astronomy & Computing (Amara, Quanz & Akeret 2015). NCCR PhD student Conor Francois continues to analyse archival data from ESO and previously unpublished proprietary data from VLT/NACO. The key result is the direct detection of a gas giant planet candidate (see Fig. 1) orbiting around the nearby, young solar-type star HD61005. This candidate was missed in previous work and its discovery was possible using advanced principal component based data analysis algorithms. High-priority, follow-up observations with VLT/SPHERE were carried out in the context of the GTO programme in early February 2015 (target coordinator: Francois). The goal is to confirm the detection and characterise the spectral energy distribution of the object in the near infrared. In addition to leading this high-profile follow-up programme, we are involved in the interpretation of SPHERE SVT data of some known exoplanets (e.g., in a characterisation study of the HR 8799 planets) and are participating in planning the exploitation of the main 200 nights NIRSUR exoplanet survey of the SPHERE consortium.

A paper confirming the detection and characterising the protoplanet that is still embedded in the disc around the young star HD100546 is under review at the Astrophysical Journal (Fig. 2; Quanz et al., 2015). It is the first time that the effective temperature and luminosity of a forming gas giant planet could be empirically constrained. Also, the data suggest the existence of a circumplanetary disc surrounding the central protoplanet. Follow-up observations from SPHERE have been collected in early February 2015 including the search for accretion signatures of the forming planet.

| Fig. 1: A newly discovered planet candidate (yellow arrow) orbiting the nearby, Sun-like star HD61005. The star itself is located in the image centre and was subtracted during the data analysis process. Based on the estimated age of the star (~40 Myr) and the measured flux of the planet, models predict a mass of ~10 Jupiter masses for this object. The data were taken with VLT/NACO at 3.8 μm (L’ filter) using the Apodising Phase Plate coronagraph to supress the stellar diffraction pattern. |  |
| --- | --- |

Fig. 2: Confirmation of the protoplanet candidate HD100546 b in the L’ and M’ band (Quanz et al. submitted). The object has been shown to be co-moving with the central star and may enable empirical studies of the formation process of gas giant planets at large orbital radii.

Furthermore, the NCCR Post-Doc Dr. Maddalena Reggiani led a study of another protoplanet candidate embedded in the disc surrounding the young intermediate mass star HD 169142. The discovery paper appeared in ApJL in 2014. She is also leading a paper on the statistical analysis from the SPHERE pre-survey “NACO Large Programme” that will be submitted to A&A in February 2015. A final draft has been circulated to the core team.

On a side note it should be mentioned that a new open time proposal to search for additional young planets embedded in circumstellar discs has been accepted at the VLT and the observations will be carried out with NACO at the VLT in early May 2015.

In collaboration with Prof. Jonathan Fortney and Dr. Michael Line, the NCCR Postdoc Dr. Kamen Todorov is developing a spectral retrieval code for directly imaged gas giant exoplanets with the goal of determining the fundamental physical properties and the main chemical components of the planets’ atmospheres. A simple description for a haze layer has been added to the code and first tests with actual data from the “super-Jupiter” kappa Andromeda b look very promising. We obtained VLT/SINFONI near infrared spectra of HD106906 b – a very long period gas giant planet – in January / February 2015 to carry out the first retrieval based characterisation of this object. Todorov also published a paper in Nature on the spectrum of the transiting exoplanet HAT-P11b with Dr. Drake Deeming and colleagues.

We are part of an international team that will attempt to image planetary companions to HL Tau with the LBTI in Arizona in complement to ALMA. The ALMA image, taken to test the longest baseline currently available, revealed a number of concentric rings inside a bright circumstellar disc possibly created via planet-disc interactions. First datasets were obtained in December 2014, but an additional observing time of 3 hours was granted to an MPIA-led proposal with ETH participation.

Adrian Glauser continued to lead our role in the ERIS project in collaboration with Arcetri Observatory and MPE. In collaboration with ESO and other partners we investigated a significant simplification of the design to keep the instrument on track for first light in 2019. We will play a major role in procuring the detector and plan to support ESO in detector testing. Our main optical work involves the pupil wheel, filter wheel, and field stop optics for the instrument. In this context it is important to mention that the IR lab at ETH achieved “first light” in summer 2014 demonstrating diffraction limited imaging at 3 μm with a beam appropriate or testing VLT optics. This work is in preparation for using our IR test bench for the ERIS and METIS projects. Glauser is also the Project 1 contact for the NCCR Technology Platform and he participated in the first meeting in Bern.

Finally, in February 2015 Ambizione Fellow Dr. Jonas Kuhn joins our research group. Kuhn is going to work on diffraction suppression techniques (hard- and software) for high-contrast imaging applications at the interface of coronagraphy and interferometry.

### 3. Contribution to the overall goals of the NCCR

Main contributions of Project 1 in the past months include the direct detection and/or characterisation of 3 (proto-)planet candidates. Two of these objects are still embedded in the gas-rich disc they formed from, while the third one – if confirmed – is orbiting a star with a spatially resolved debris disc. Having images and flux measurements of young planets and of the circumstellar discs they are embedded in will help us to constrain the immediate formation process of gas giant planets on wide orbits and to study the interaction of planets and discs at early ages.

### 4. Scientific collaboration within PlanetS

M. Meyer participated with NCCR colleagues F. Pepe and D. Ehrenreich in publishing a review on exoplanet instrumentation for Nature, which appeared in September 2014. In addition we hosted Amaury Thiabaud (PhD student, Project 5) to discuss possible joint planet formation projects.

### 5. Next steps

As described above, a major focus will be the first run of SPHERE GTO observations early in 2015. This will result in new datasets for both subprojects, i.e., protoplanetary discs and exoplanet imaging. In addition, we are planning to submit a DDT proposal for ALMA as well as an additional Cycle 3 open time ALMA proposal in spring 2015 to complement our NACO and SPHERE observations of young, embedded planets.

Concerning algorithm development for high-contrast imaging data, a new method to model and subtract thermal background emission between 3 and 5 μm was applied in the confirmation paper of the protoplanet HD100546 b. The accompanying paper is still in preparation with the goal of having a first draft in the coming months.

On the exoplanet characterisation side, we expect the paper discussing the properties of the HR8799 planetary system based on SPHERE SVT data to be submitted soon. We will contribute to the interpretation of the datasets. In addition, we plan to compose a first draft of a paper describing the functionality and performance of our atmospheric retrieval code. Then the code will be used to analyse our new VLT/SINFONI data of HD106906 b and we will discuss which additional objects we will study in the coming months in greater detail.

We anticipate significant work for ERIS in 2015 including use of our cold optical bench for testing apodising phase plates as a coronographic option. Finally, Ambizione Fellow Jonas Kuhn (JPL) who arrives in February will take up his laboratory work and synergies and links to different NCCR projects will be discussed.

In terms of scientific collaboration within the NCCR we will carry out at least two one-day mini-workshops (one with Project 5 and one with Project 7) to discuss where and how we can collaborate most efficiently in the areas of exoplanet imaging and atmospheric retrieval (see above). We are also planning a visit to the laboratory of Project 4 to discuss how results from the LOSSy programme might be used to interpret the results from scattered / polarised light observations of circumstellar discs. Finally, C. Lovis (Project 3) and S. Quanz (Project 1) will draft a white paper discussing the long-term instrumentation strategy for exoplanet research in Switzerland (see Sect. 2.1.3 of the report).

### 6. List of publications resulting directly from PlanetS

Pepe, Ehrenreich & Meyer, “Instrumentation for the detection and characterisation of exoplanets”, Nature, Volume 513, Issue 7518, pp. 358-366 (2014)

Amara, Quanz & Akaret, “PynPoint Code for Exoplanet Imaging”, accepted for publication in Astronomy & Computing (arXiv:1405.3284)

Meru et al.,”Long-lasting dust rings in gas-rich discs: sculpting by single and multiple planets”, submitted to ApJ (arXiv:1411.5366)

Quanz et al., “Confirmation and characterisation of the protoplanet HD100546 b - Direct evidence for gas giant planet formation at 50 au”, submitted to ApJ (arXiv:1412.5173)

### 7. List of publications with minor contributions from PlanetS

Brittain et al., ”NIR Spectroscopy of the HAeBe Star HD 100546. III. Further Evidence of an Orbiting Companion?”, ApJ, Volume 791, Issue 2, article id. 136, 7 pp. (2014)

Chauvin et al., “The VLT/NaCo large program to probe the occurrence of exoplanets and brown dwarfs at wide orbits. II. Survey description, results, and performances”, A&A, Volume 573, id.A127, 19 pp. (2015)

Desidera et al., “The VLT/NaCo large program to probe the occurrence of exoplanets and brown dwarfs in wide orbits. I. Sample definition and characterisation”, A&A, Volume 573, id.A126, 45 pp. (2015)

Fraine at al., “Water vapour absorption in the clear atmosphere of a Neptune-sized exoplanet”, Nature, Volume 513, Issue 7519, pp. 526-529 (2014)

Garufi et al., “Shadows and cavities in protoplanetary discs: HD163296, HD141569A, and HD150193A in polarized light”, A&A, Volume 568, id.A40, 10 pp. (2014)

Janson et al., “High-contrast Imaging with Spitzer: Deep Observations of Vega, Fomalhaut, and epsilon Eridani”, accepted for publication in A&A (arXiv:1412.4816)

Osorio et al., “Imaging the Inner and Outer Gaps of the Pre-transitional Disc of HD 169142 at 7 mm”, ApJL, Volume 791, Issue 2, article id. L36, 7 pp. (2014)

Reggiani et al., “Discovery of a Companion Candidate in the HD 169142 Transition Disc and the

Possibility of Multiple Planet Formation”, ApJL, Volume 792, Issue 1, article id. L23, 5 pp. (2014)

Thalman et al., “SPOTS: The Search for Planets Orbiting Two Stars. I. Survey description and first observations”, A&A, Volume 572, id.A91, 12 pp. (2014)

Todorov et al., “Updated Spitzer Emission Spetroscopy of Bright Transiting Hot Jupiter HD 189733b”, ApJ, Volume 796, Issue 2, article id. 100, 15 pp. (2014)

### Project 2:  Origin and Evolution of Volatiles in Planets

## Project leader:  Maria Schönbächler – ETHZ

### 1. Abstract

Project 2 addresses central questions regarding the origin and evolution of volatiles in planets. The overarching theme is to determine the origin and evolution of volatiles at the different stages of terrestrial planet formation. The focus is on timescales and processes. Understanding the presence or absence of volatiles at the different stages of planet formation is important because the volatiles significantly influence the predominant physical and chemical processes (e.g., mantle dynamics, magmatism, oxidation state, core formation) and thus shape the final state of a planet, including its atmosphere and habitability.

This project applies sophisticated analytical techniques to extra-terrestrial samples (meteorites, interplanetary dust particles (IDP) and returned samples from the stardust mission) in the laboratory to tackle these questions. The project is subdivided into four work packages, two of which have been started.

The first six months of the project were used to initiate the developments that are necessary for the analytical studies of chondrites and include design of chemical standards, sample preparation and development of analytical protocols for elemental and isotopic analyses. One focus is the chronology of CAIs using the Rb-Sr chronometer. The goal is to quantify the effect of nucleosynthetic anomalies on Rb-Sr ages for volatile element loss from planetesimals and planets. To this end, an analytical method for high precision Sr isotope analyses has been set up. The accuracy and reproducibility of the method was tested by repeated analyses of a suite of terrestrial samples. Terrestrial barite sample were also analysed and will serve a proxy for terrestrial volatile depletion.

### 2. Results and achievements since the last report

The project is divided into four work packages (WP) that are described in more detail in the following.

WP1: Formation of volatile-depleted material in the solar nebula (Lead – Prof. Klaus Mezger)

PhD student Jonas Pape was hired and started in July 2014 to work on this WP.

One goal of this WP is to obtain high precision ages for some of the oldest and most primitive materials of the solar system to understand their genesis and chemical evolution as a function of time in an evolving solar nebula. The essential tool for this study is the secondary ion mass spectrometer located at the University of Lausanne (SwissSims). This instrument has not been used for analyses similar to those we plan to perform and thus extensive methods development is needed before the actual measurements are possible.

In a first round of tests, we have evaluated the suitability of different analytical protocols. These first tests also showed that it is necessary to place sample and standard together in the same mount in order to maintain uniform conditions that permit us to obtain reproducible data. In parallel the standards that are needed to calibrate the instrument and to correct for chemical and isotopic fractionation effects during the analyses have been designed. These standards will be in the form of glasses of different compositions and will be produced together with Prof. Peter Ulmer from ETHZ, who has extensive experience with the production of chemically homogenous glass standards.  The first meteorite samples of low metamorphic grade have been selected and are ready to be prepared for analysis.

WP2: Planetesimals: timing of hydration and volatile enrichment in the inner solar system (Lead – Prof. Klaus Mezger)

This WP has not started yet (planned for year 2 of the NCCR).

It aims to determine the timing of aqueous alteration that affected the parent bodies of carbonaceous chondrites in order to establish whether aqueous alteration was a single or re-occurring event. The WP also aims to characterise specific isotopic signature of these parent bodies (e.g. D/H). The outcome will be very important to verify planet formation models.

WP3: Accretion of terrestrial planets: timing and origin of the volatile components. (Lead – Prof. Maria Schönbächler)

PhD student Tom Henshall was hired and started in June 2014 on this WP.

A goal of this WP is to reassess the timing of volatile element depletion in terrestrial planets. The Rb-Sr chronometer is an ideal tool to determine these timescales and has been used for decades. However, the results have been clouded by the fact that the estimates of the baseline for dating (the initial Sr isotope composition of our solar system) is affected by nucleosynthetic anomalies. This in turn results in incorrect ages for volatile depletion of planetary bodies. The goal of this WP is to obtain high precision Sr isotope data on the oldest material of our solar system (CAIs: Calcium-Aluminium-rich inclusion found in primitive meteorites) to reassess the initial Sr isotope composition of our solar system.

Fig. 1: The Sr isotope composition for various terrestrial samples. The ε84Sr value is defined as the deviation of the 84Sr/86Sr ratio of the sample form the SRM-987 Sr standard expressed in parts per 104. BCR-2 and BHVO-2 are basalts, AN-G is an anorthite. Literature data are from Hans et al. 2013, Earth Planet. Sci. Lett. 374 204–214; Paton et al. 2013, ApJL, 763, L40; Brennecka et al. 2013, PNAS, 43, 17241–17246.

To this end, we have successfully set up and tested high precision Sr isotope analyses using TIMS (Thermal Ionisation Mass Spectrometry). This method requires the chemical extraction of Sr from the sample matrix using ion exchange chemistry before analysis on TIMS. The analytical procedure was tested with terrestrial rocks (mainly basalts; Fig. 1). Our results show a good overlap with published literature data. This demonstrates the accuracy and precision of our data. The exception is the anorthite sample (Fig. 1), which consistently yields slightly lower ε84Sr values and we are currently preforming tests to elucidate, whether this is an analytical artifact or an inherent feature of this particular sample.

In addition to the method development, we produced scanning electron microscopy (SEM) maps of primitive meteorites. The goal is to identify and classify suitable CAI samples for Sr isotope analyses. This part of the WP is work in progress, but we have already identified the first suitable candidates.

We also plan to refine the initial Sr isotope composition of the Earth. This value - when compared to the solar system baseline and integrated in planet formation models – yields important information about the timing of moderately volatile element loss from the Earth. To this end, we have analysed Archean barite, which can be used to assess the initial Sr isotope composition of the Earth’s mantle due to its extremely low Rb/Sr ratio. First results of barites from the Barberton Greenstone Belt (BGB) indicate a similar initial Sr isotope composition as proposed in a previous study (McCulloch, Primitive 87Sr/86Sr from an Archean barite and conjecture on the Earth's age and origin, Earth Planet. Sci. Lett. (1994) 126, 1-13).

WP4: Volatiles in planetary interiors and comets and their possible influence on atmospheres (Lead – Dr. Henner Busemann)

This WP as not started yet. Dr. Maïa Kuga was hired for a postdoc position and will start on 1 April.

This subproject addresses the questions:  How did the volatiles in the interior of terrestrial planets and their atmospheres evolve and to what extent were primary volatiles from the original building blocks involved, or delivered later e.g., via comets and/or asteroids? To answer these questions, we will measure the abundances and isotope ratios of noble gases in meteorites, interplanetary and cometary dust.

### 3. Contribution to the overall goals of the NCCR

A key goal of the project will be to establish the processes and timing of volatile addition to the inner rocky planets of a solar system through the direct study of material from our solar system, which serves as a model for other solar systems with planets.

### 4. Scientific collaboration within PlanetS

Project 2 itself is based on the collaboration between the University of Bern and ETH Zürich.

We also started a collaboration with Project 5 (Amaury Thiabaud). This collaboration aims at the combination of planet formation models and geochemical constraints.

The first stage of Project 2 mainly involves method development and thus we collaborate mostly with partners outside PlanetS (e.g. SwissSims team Lausanne, Prof. Peter Ulmer, ETHZ, Smithsonian Institution, Washington DC (USA) (E. Bullock, sample characterisation of CAIs)). Once data are available closer collaboration with scientists modelling (Project 5, 6), and observing the evolution of dust discs is anticipated (Project 1).

### 5. Next steps

Most of the time and efforts this year will be spent on the development of analytical methods to obtain high precision and high resolution elemental and isotopic data from meteorites in order to establish the timeline of their formation and subsequent alteration. Moreover, WP 4 will commence and will focus on noble gas analyses.

This will contribute towards our 4-year goals, which are defined as following:

- To use short-lived isotopes to constrain the time and duration of chondrule formation and the addition of volatile components to early formed planetesimals.

- To determine high precision isotope compositions of refractory inclusions (CAIs) hosted in primitive meteorites to (i) identify potential collateral nucleosynthetic anomalies and (ii) reassess the timing of volatile delivery to planetesimals and planets.

- To determine the trapped noble gases in metal-rich mineral separates and inclusions from meteorites that experienced various degrees of metal-silicate differentiation, in order to assess the behaviour of the volatiles during differentiation.

### 6. List of publications resulting directly from PlanetS

None.

### 7. List of publications with minor contributions from PlanetS

None.

### Project 3:  Atmospheres of exoplanets

## Project leader:  Francesco Pepe – University of Geneva

1. Abstract

The aim of Project 3 is to study planet atmospheres by setting up a long-term research programme based on a comprehensive ground and space-based observational approach. Observing transiting planets orbiting bright stars will allow us to measure precisely both their physical characteristics and their atmospheric structures and compositions. The main emphasis of this programme will be the characterisation of the atmospheres of planets smaller than Jupiter. This includes potential "ocean planets” of Neptune-mass, and possibly rocky super-Earths orbiting low mass stars.

The first nine months of Project 3 have been mainly devoted to setting up the project, hiring the personnel and starting the various collaborations within and outside the NCCR. Nevertheless, major achievements can be reported, as for example the publication of two review papers in Nature, the first about instrumentation for the detection and characterisation of extra-solar planets, the second about the successes and the perspectives of Doppler velocimetry. Furthermore we have acted successfully in the three areas defined by the sub-projects: 1)- We have been using and extending the capabilities of present instrumentation and software for the observation of exoplanetary atmospheres. It is worth mentioning, for instance, the clear detection of atmospheric sodium in the hot Jupiter HD189733b with HARPS, which opens new perspectives for the use of 4-m class telescopes, as well as the detection of atmospheric evaporation for a Neptune-mass planet with the Hubble Space Telescope, which is a promising advance towards the characterisation of low-mass, warm exoplanets. 2)- The collaboration with Project 5 is leading to the better understanding of planetary atmospheres. In particular, we are going to use new models developed under Project 5 to interpret observations, such as the one on HD189733, and to derive not only the existence of elements and molecules but also their abundance and possibly their distribution and the physical conditions in the atmosphere (temperature-pressure, winds, etc.). 3)- We have started working on adaptive optics models that optimise the injection efficiency of the light into the fibre-fed spectrograph. Our view, not to aim for diffracted-limited performances but, instead, ‘just’ for a reduction of image size, opens new perspectives for medium to large-size telescopes, in particular in terms of instrument and detector size, complexity and costs.

2. Results and achievements since the last report

2014 will be probably remembered as the year in which the exoplanet community realised that research is moving from an era of discoveries and detection, by means of radial velocities first and transit searches later, to a new era of extra-solar planet characterisation. Our group is acting on both sides of this transition. On the one side, and through on-going projects and SNF grants, we aim at better understanding existing high-fidelity spectrographs and optimising their use to go beyond present performance limitations. On the other side, with sub-project 3.1, we apply this knowledge and experience to the observation of signatures of extra-solar planets. In this context a first paper on the detection of sodium in the atmosphere of the exoplanet HD189733 b has been submitted to A&A in January 2015. The data had been originally gathered with HARPS for the measurement of the Rossiter-McLaughlin effect. A new and precise data-analysis technique, developed by Aurelien Wyttenbach within Prof. Francesco Pepe’s SNF grant, was applied to the same data under the guidance of Dr. Christophe Lovis and Dr. David Ehrenreich with the goal to detect the tiny additional absorption caused by the sodium in the atmosphere of the planet during its transit. A plot of the absorption spectrum is shown in Fig. 1. The detection is statistically very significant and better than any other results achieved with ground-based instrumentation.

These results also motivated a new and intense collaboration with Project 5. In fact, the high-resolution high-fidelity spectra provided by HARPS not only reveal the presence of sodium, but also carry important information about the physics and dynamics of the atmosphere. The position of the lines, for instance, can reveal the presences of strong winds. “Reconnaissance” modelling of these data in the frame of sub-project 3.2 led to 1) establish the presence of a stratosphere, where temperature increases with altitude, on HD 189733b and 2) foster enhanced discussions between Project 3 and theorists from Project 5, where detailed theoretical interpretation of these results can take place. This resulted in the submission of a joint theoretical paper on the HD 189733b sodium signature.

Fig. 1: Absorption spectrum of the NaI lines in the atmosphere of HD189733 b. The additional absorption is represented by the ratio of the planet diameter at a given wavelength to its average radius measured by broadband photometry.

This sodium detection and the new analysis techniques led Dr. Christophe Lovis to investigate also other molecular species. The current state of the analysis indicates the possible presence of water vapour in some hot Jupiters. Its detection is particularly difficult because of the superposition of telluric water-vapour signatures in the spectra, but the techniques developed are able to remove telluric features to a level never reached before. If confirmed, it would be the first time that water vapour signatures are detected on exoplanets in the visible wavelength range from the ground. Moreover, the advances made in the precise correction of telluric contamination are fundamental to high-fidelity spectroscopy in general and will have important implications for many other activities carried out in Project 3 and beyond. We plan to publish these results during the last quarter of the first PlanetS year.

It is important to note that the optimum use of high-end spectrographs led us to the development of specialised software algorithms. These algorithms are employed in dedicated data pipelines of the mentioned spectrographs. In collaboration with the DACE Platform, under the responsibility of Dr. Danuta Sosnowska and the guidance of Dr. Christophs Lovis, we are responsible for the transfer and integration of these algorithms into DACE. In particular we are extending DACE with functionalities for the re-reduction and analysis of spectra, in particular with emphasis on planetary atmospheres.

We have been able to show that the detection limits achievable with HARPS are actually comparable to those achievable with the Hubble Space Telescope (see Fig. 2). This ascertainment led to the submission of an ESO Large Programme observing proposal called “Hot Exoplanet Atmospheres Resolved with Transit Spectroscopy” — HEARTS (D. Ehrenreich, September 2014), involving researchers and PhD students of Project 3 and Project 5. The goal is the systematic observation of atmospheric signatures of planets around bright stars with HARPS. ESO’s Observing-Programme Committee (OPC), although assigning high scientific value to the proposal, rejected the programme highlighting the lack of published papers on the subject. However, the mentioned article on HD189733b’s sodium will greatly support the goals of the HEARTS proposal, which shall be resubmitted by the next period (April 1st 2015).

The high spectral resolution of HARPS gives access to the physical, chemical, and dynamical properties of the upper atmosphere of a hot Jupiter, providing a promising link with observations of atmospheric escape higher in the planetary exospheres. These observations can be done in the UV with the Hubble Space Telescope (HST) and, since atmospheric escape represents mass loss, they are important for understanding the evolution of exoplanets. New HST data that have been obtained by Dr. David Ehrenreich and analysed during the 2nd and 3rd quarter of PlanetS by Dr. Vincent Bourrier, will bring us one step further in our quest for atmospheric properties of low-mass planets. These observations show that in the UV, the Neptune-mass exoplanet GJ 436b has transits eclipsing over half (56.3±3.5%) of the stellar surface, far beyond the 0.69% occultation caused by the optical transits. The ultraviolet transits start ~2 hrs. before, and end >3 hrs. after the optical transits, which last for ~1 hr. We infer from this that the planet is surrounded and trailed, like a comet, by a large exospheric cloud composed mainly of hydrogen atoms, and represented in Fig. 3. These observations imply that large atmospheric signals could be retrieved in the UV for a whole population of moderately irradiated, low-mass exoplanets. We have submitted an observationally oriented paper to Nature mid-February 2015. A theoretical paper is in preparation. Furthermore, to better visualise and understand the three-dimensional structure of the exospheric cloud surrounding GJ 436b, we have started a discussion with Project 4 (N. Thomas) about a possible application of the visualisation tools they are using to study the 3D structure of comets.

Fig. 2: Expected absorption signal for known transiting exoplanets assuming one atmospheric scale height. The detection limits for HARPS and the HST are compared.

Our team is progressing with various instrumental projects (funded by other channels) for the future benefit of Project 3. In particular we should mention the November 2014 upgrade of the Coralie spectrograph and the planned upgrade of HARPS in May 2015. Both instruments are being upgraded with octagonal optical fibres that will improve the spectroscopic ‘fidelity’. Furthermore, the ESPRESSO project is entering its MAIV phase. In parallel, we are developing new Fabry-Pérot systems for Coralie, ESPRESSO and SPIRou.

Along the same line, and specifically within sub-project 3.3, we have contributed to the creation of a consortium to answer ESO’s call for proposal for the construction and operation of an instrument for the New-Technology Telescope (NTT). The proposal foresees the construction of a high-precision NIR spectrograph, NIRPS, which is essentially based on the same concepts as HARPS but in the infrared spectral domain. The scientific objective of this instrument is two-fold: 1) conduct a search for low-mass planets around M-dwarfs in the southern hemisphere, 2) follow-up candidates provided by the transit searches with NGTS and Cheops, and 3) detect molecular species in the atmosphere of exoplanets. It is this second aspect in particular that calls for the interest of Project 3 and in which we will be able to deploy some technological aspects we are currently developing. Under the guidance of F. Wildi, U. Conod (PhD sub-project 3.3) is investigating the optimisation of an AO system for a fibre feed. After two months first interesting results start to appear, in particular with respect to an optimum density of actuators for the deformable mirror. Due to problems in hiring a specialised engineer, we have sub-contracted a study for the definition of a ‘shoe-box’ adaptive optics system for NIRPS. The study has been integrated in the proposal submitted to ESO. The proposed adaptive-optics solution will allow us to build an extremely compact instrument and to include an integral-field unit (IFU). The combination of this IFU with high-precision, high spatial and high spectral resolution are key for the detection of atmospheric signatures because together, they allow us to increase the contrast of the planetary signal with respect to the host star. The NIRPS effort is carried out in collaboration with Projects 1, 5 and 7. If our proposal is selected, PlanetS (UGE, UBE and ETHZ, and respective projects) will be partner in the consortium and have a leading role.

Fig. 3: The left panel shows the UV transit light curve of the Neptune-mass exoplanet GJ 436b, showing an absorption depth of over 50%, which is deeper than any transit signal ever detected for an exoplanet or its atmosphere. The curves represent different models; the teal curve stands for the transit of a comet-like exospheric cloud escaping from the planet, pictured in the right panel and color-coded according to its column density.

Finally, we also report our active participation to the European-Extremely Large Telescope project and its instruments. A ‘white paper’ in support of the PLATO satellite and the HiReS@E-ELT instrument (a high-resolution spectrograph in the line of HARPS, NIRPS and ESPRESSO) has been prepared by Dr. Christophe Lovis and Prof. Stephane Udry and published on astro-ph. Therein it has been shown how important HiReS will be for the characterisation of extra-solar planets and how critical is the complementarity of space- and ground-based efforts. On the technical side Dr. François Wildi, Dr. Bruno Chazelas and Prof. Francesco Pepe are investigating the development of key technologies, such as laser-frequency combs, dispersive optics, fibre optics, adaptive optics etc. that will become essential when designing a high-resolution spectrograph for very large telescopes. A special effort has and will be conducted within sub-project 3.3 and in collaboration with the Technology Platform.

International Collaborations:

- Cambridge UK, start of ‘THE@INT’ project. Submission of a proposal to ING for the construction of a copy of HARPS for the INT at La Palma, Spain.

- NIRPS@NTT. International collaboration to propose to ESO the construction of an IR high-precision spectrograph for the NTT.

- Collaboration within a large consortium started for the preparation of the HiReS@E-ELT 'blue book'.

- A discussion with Prof. Tobias Kippenberg (EPFL) and S. Lecomte/T. Herr (CSEM) is starting to set up a Synergia among the three institutes and supported by PlanetS. The concept is to develop a key-turn IR laser-frequency comb for the spectrograph calibration based on micro resonators. Collaboration with the Technology Platform is aimed as well.

- Institut d’Astrophysique de Paris, France. Collaboration with Dr. Alain Lecavelier des Etangs on the study of atmospheric evaporation with HST data and modelling.

- University of Warwick, UK. Collaboration with P. Wheatley on the acquisition and analysis of X-ray data to understand the heating processes at the origin of atmospheric evaporation.

Hired personnel:

- Sub-project 3.1

  - June 1st 2014, start of Danuta Sosnowska, computer scientist (50%, SNF-PlanetS)

- Sub-project 3.2

  - July 1st 2014, start of David Ehrenreich, adjoint scientifique (20%, SNF-PlanetS)

  - September 15th 2014, start of Baptiste Lavie, PhD student in ‘Atmospheres modelling’ (100%, SNF-PlanetS). B. Lavie starts in Bern (with Project 5) and will come to Geneva after two years.

  - October 15th 2014, start of Vincent Bourrier, postdoc (100%, SNF-PlanetS)

- Sub-project 3.3

  - September 1st 2014, start of Uriel Conod, PhD student in ‘AO’ (100%, SNF-PlanetS)

One position still open in sub-project 3.3: 100% 'Adaptive Optics Specialist' - Two candidates have been short-listed, but declined the position. It will be necessary to re-open the position, since no adequate candidate is available at present.

3. Contribution to the overall goals of the NCCR

Despite the fact that Project 3 is addressing relatively new aspects, it has already obtained important results in characterising extra-solar planets. In particular, it contributes to the understanding of planetary atmospheres by observation and by linking these observations with models. These activities have spurred underestimated or unexpected synergies within various PlanetS projects. They also help PlanetS members to broaden the field of competences beyond already-existing excellence.

4. Scientific collaboration within PlanetS

An intensive collaboration between Projects 3 and 5 has been started. A meeting was organised in Geneva on November 19th 2014 between members of Project 3 (Dr David Ehrenreich, Dr. Christophe Lovis, Dr. Vincent Bourrier) and Project 5 (Prof. Kevin Heng, Baptiste Lavie). The goals of the meeting were:

- To inform Project 5 of the observational results being obtained within Project 3 and discuss about possible theoretical orientations.

- To follow-up on the start of Baptiste Lavie’s thesis, co-advised between both projects.

Regular (monthly to bi-monthly) meetings are foreseen, they will be alternatively held in Geneva and Bern.

Projects 3 (Prof. Francesco Pepe and Dr. David Ehrenreich) and 1 (Prof. Michael Meyer) collaborated in the preparation of a Nature review paper (Nature 513, 358-366, 2014) on 'Instrumentation for the detection and characterisation of exoplanets'. This collaboration is being extended to the NIRPS project.

Projects 3, 1, 5 and 7 collaborate in the NIRPS@NTT and the HiReS@E-ELT projects.

Projects 3 and 4 started a discussion aimed at adapting 3D visualisation tools used for comets to extended exoplanetary atmospheres.

5. Next steps

### In the following we give a few short-term objectives for Project 3:

- Several publications on ‘atmospheric characterisation’ will be submitted in the next months.

- We will re-submit the Hearts proposal to ESO.

- We will submit several observing proposals for HST time.

- The NIRPS@NTT proposal has been submitted to ESO. After the hopefully positive selection, we will start with the detailed definition of the project.

- As PlanetS we will contribute to the answer to ESO’s Request for Information for the HiReS@E-ELT instrument.

- We shall start or consolidate various R&D activities in view of the future project for high-resolution spectrographs.

6. List of publications resulting directly from PlanetS

Refereed publications

- Pepe, F., Ehrenreich, D., & Meyer, M. R., Instrumentation for the detection and characterisation of exoplanets, Nature 513, 358, 2014

Submitted publications

- Ehrenreich, D., Bourrier, V., Wheatley, P. J., Lecavelier des Etangs, A., Hébrard, G., et al., A giant comet-like cloud of hydrogen escaping the warm Neptune-mass planet GJ 436b, submitted to Nature.

- Wyttenbach, A., Ehrenreich, D., Lovis, C., Udry, S., Pepe, F., High spectral resolution detection of sodium in the atmosphere of HD189733b with the HARPS spectrograph, submitted to A&A.

7. List of publications with minor contributions from PlanetS

Refereed publications

- Ehrenreich, D., Bonfils, X., Lovis, C., Delfosse, X., Forveille, T., et al., Near-infrared transmission spectrum of the warm-Uranus GJ 3470b with the Wide Field Camera-3 on the Hubble Space Telescope, A&A 570, AA89, 2014

- Oshagh, M., Santos, N. C., Ehrenreich, D., Haghighipour, N., Figueira, P., et al., Impact of occultations of stellar active regions on transmission spectra. Can occultation of a plage mimic the signature of a blue sky?, A&A 568, AA99, 2014

- Bourrier, V., Lecavelier des Etangs, A., & Vidal-Madjar, A., The Mg i line: a new probe of the atmospheres of evaporating exoplanets, A&A 573, AA11, 2015

- Puig, L. et al., The phase 0/A study of the ESA M3 mission candidate EChO, ExA 42, 2014

- Mayor, M., Lovis, C., & Santos, N. C., Doppler spectroscopy as a path to the detection of Earth-like planets, Nature 513, 328, 2014

- Haywood, R. D., Collier Cameron, A., Queloz, D., Barros, S. C. C., Deleuil, M., et al., Planets and stellar activity: hide and seek in the CoRoT-7 system, MNRAS 443, 2517, 2014

Non-refereed publications

- Udry, S., Lovis, C., Bouchy, F., Collier Cameron, A., Henning, T., et al., Exoplanet Science with the European Extremely Large Telescope. The Case for Visible and Near-IR Spectroscopy at High Resolution, arXiv:1412.1048, 2014

- Beichman, C., et al., Observations of Transiting Exoplanets with the James Webb Space Telescope (JWST), PASP 126, 1134, 2014

- Ehrenreich, D., Search for an evaporating ocean on the super-Earth HD 97658b, hst..prop 13820, 2014

- Zerbi, F. M., Bouchy, F., Fynbo, J., Maiolino, R., Piskunov, N., et al., HIRES: the high resolution spectrograph for the E-ELT, SPIE 9147, 914723, 2014

- Swinyard, B. et al., Design and performance of the Exo-planet Characterisation Observatory (EChO) integrated payload, SPIE 9143, 91432E, 2014

- Mégevand, D. et al., ESPRESSO: the radial velocity machine for the VLT, SPIE 9147, 91471H, 2014

- Artigau, E., Astudillo-Defru, N., Delfosse, X., Bouchy, F., Bonfils, X., et al., Telluric-line subtraction in high-accuracy velocimetry: a PCA-based approach, SPIE 9149, 914905, 2014

- Artigau, E. et al., SPIRou: the near-infrared spectropolarimeter/high-precision velocimeter for the Canada-France-Hawaii telescope, SPIE 9147, 914715, 2014

- Fortier, A., Beck, T., Benz, W., Broeg, C., Cessa, V., et al., CHEOPS: a space telescope for ultra-high precision photometry of exoplanet transits, SPIE 9143, 91432J, 2014

Submitted publications

- Martins, J.H.C., et al., Spectroscopic direct detection of reflected light from 51 Peg b, submitted to A&A.

- Kennedy, G.M., Matrà, L., Marmier, M., Greaves, J.S., Wyatt, M., et al., Kuiper belt structure around nearby super-Earth host stars, submitted to MNRAS.

Conferences:

- CHEOPS science meeting, Venice (Italy), 03.06.2014 – 04.06.2014 (Ch. Lovis, speaker)

- “Fibres in astronomy”, Cambridge (MA, USA), 19.08.2014 – 24.08.2014 (F. Pepe, speaker)

- “Towards other Earths”, Porto (Portugal), 15.09.2014 – 19.09.2014 (F. Pepe and D. Ehrenreich, speakers; Ch. Lovis, part of the SOC)

- “PLATO science conference”, Taormina (Italy), 03.12.2014 – 05.12.2014 (D. Ehrenreich, speaker)

- “ESO in the 2020s”, Garching (Germany), 19.01.2015 – 22.01.2015 (several participants of sub-project 3.3)

### Project 4:  Solar system remote sensing

## Project leader:  Nicolas Thomas – University of Berne

### 1. Abstract

The goal of Project 4 is to study the surfaces of planets and smaller bodies in our Solar System and use this knowledge to support modelling of planetary formation, individual exoplanets, and proto-planetary discs by other members of the NCCR. The activities of Project 4 are developed along two programmes: LOSSy (Laboratory for Outflow Studies of Subliming Materials) and LAPIS (Laboratory for Analysis of Planetary and Interplanetary Data Sets). Specifically, (1) we will characterise surface generated by condensation and sublimation processes, (2) link laboratory measurement to remote-sensing observations, (3) analyse the Rosetta/OSIRIS imaging data, with a special focus on surface inhomogeneity, and their implications for the formation of the solar system, (4) develop a system for the storage and calibration of OSIRIS, CaSSIS and BELA experiments, and (5) develop advanced tools fort he visualisation of diverse data sets.

We have managed to initialise most aspects of the first phase of Project 4. We have procured, tested and run our new Optical Coherence Tomography experiment for measuring the surface roughness of samples. We have also demonstrated that the OCT can be used to monitor sample evolution in a thermal vacuum chamber providing us with a powerful way to characterise the evolution of volatile surfaces. We conducted  experiments that will lead to a potentially important paper questioning the use of linear mixing models to determine ice content in dirty-ice mixtures. We have also begun investigating whether we can extrapolate photometric measurements of smooth surfaces in the laboratory to rough surfaces on planets by using fractal type representations. This work is a sub-element of the visualisation activities that we are pursuing. Here we use ray-tracing algorithms to model and display parameters associated with the nucleus of comet 67P/Churyumov-Gerasimenko. Finally, our work in preparation for the CaSSIS experiment for the ExoMars Trace Gas Orbiter is progressing with the development of the scientific calibration facility now approaching completion.

### 2. Results and achievements since the last report

LOSSy

The LOSSy programme aims at

- Charaterising of surfaces generated by condensation and sublimation processes.

- Linking the laboratory observations to remote-sensing observations made by inter-planetary spacecraft.

- Establishing links to other groups interested in exoplanets to initiate laboratory studies of icy (and possibly hot) surfaces around other stars (including spectroscopy) as a new area of research.

Ice on terrestrial planets is often mixed within the soil and so it is difficult -sometimes even impossible- to detect only with imaging systems. This is the case for the Moon and Mercury, where the presence of ice in some shadowed craters has been hypothesised. Laser altimetry is a technique used to measure the topography of planetary surfaces as well as its reflectance. Since we know that the presence of ice alters the reflectance of the soil, we can use this method to try to detect the icy mixtures. Laser altimeters are already in the orbit around some of these bodies (MOLA for the Moon) or planned to be launched shortly (i.e., BELA for Mercury), but experience in interpreting their data is limited. In order to improve that, we need to perform laboratory measurements.

Fig. 1: The reflectance of an ice-dust mixture (ice made from our SPIPA facility and a JSC simulant). The dots show the prediction from linear mixing. The triangles show the observations.

Based on the literature, we have chosen some materials that are thought to be found on Mercury (e.g. basalts, magnetite) and have recreated the expected albedo of its surface. This “Mercury analogue” was then mixed with ice of two different grain sizes, and the reflectance measured as a function of the geometry of the light source (a laser) and the detector. The same procedure was used with a Moon analogue that NASA provided (JSC-1), and in both cases it was observed that samples with a certain weight percentage of ice (even 50wt% in some cases) appear darker at the laser wavelength than dry samples. Hapke’s photometric model has been used to fit the data. This model has many advantages (although there are also numerous deficiencies that must be appreciated). The obtained laboratory data have allowed us to test several hypotheses that are being currently used to estimate the amount of ice present in some lunar craters. We find that the use of these hypotheses in the case of icy mixtures is not correct. Fig. 1 shows how the model (a linear mixing model) predicts a linear change in albedo as the amount of ice increases. However, this is not observed (triangles in Fig. 1). Hence, the current estimates of ice content in lunar polar craters are the result of an over-simplified interpretation. The results of this study are currently being written up in a paper that should be submitted in the coming weeks.

Fig. 2: The newly procured OCT instrument (left) and an example of a surface roughness map produced with this equipment (right).

The LOSSy team has also been working with the newly procured Optical Coherence Tomography (OCT) experiment (Fig. 2). The device is designed to determine the surface roughness in a non-destructive approach at the 6 micron level. An example of the output from the device as acquired in our laboratory is also shown in Fig. 2. The device is now being used to characterise icy and dirty surfaces. Tests have successfully shown that the device can operate through a suprasil window into a vacuum chamber allowing us to measure surfaces evolving in vacuo. This will be of great interest to cometary surface simulations, for comparison with Rosetta results.

LAPIS

The LAPIS programme aims at the

- Analysis of the Rosetta/OSIRIS imaging data with emphasis on surface inhomogeneity/structure, including implications for Solar System formation. (Gas dynamics is mostly contained within our rolling SNF grant).

- Development of a system for storage and calibration of data acquired by OSIRIS, the CaSSIS experiment on the ExoMars Trace Gas Orbiter, and by the BELA experiment on-board the BepiColombo Mercury Planetary Orbiter.

- Preparations for the reduction and analysis of CaSSIS data including stereo reconstruction (the data analysis will be part of the second phase).

- Development of advanced tools for the visualisation of numerous/diverse data sets.

- Participation in upcoming missions to targets of interest in planetary evolution studies.

LAPIS Solar System Evolution

Fig. 3:  Evidence of sub-surface fluidisation on comet 67P. (Thomas et al., Science, in press).

Our short-term efforts are focussed on studies of cometary nuclei (through the ROSETTA mission) and Mars through the CaSSIS experiment on the ExoMars Trace Gas Orbiter. All ROSETTA/OSIRIS observations are currently being placed in a temporary database. We are using these observations to investigate the surface properties of the cometary nucleus and in particular to establish the presence of surface ices and their relationship to emitted non-volatile material. Our work is revealing that the nucleus may be physically inhomogeneous which would place constraints on the formation mechanism (Thomas et al., 2015). Comets are widely thought to be relics of Solar System formation. As possible planetesimals, the fact that 4 km sized objects may be inhomogeneous at kilometre scales has implications for the mixing in the outer part of the proto-planetary disc.

We have also initiated more detailed studies of the influence of water on the surface of Mars. Work has been focused on geological characterisation of Light-Toned Layered Deposits (LLD), which may provide new evidence of a past water activity, related to diverse climatic conditions during Hesperian and Amazonian periods on Mars. We currently study Iani Chaos, a disrupted zone located in a region of rich past geological activity (the highlands surrounding Chryse Planitia) and linked to Ares Vallis, one of the best examples of an extra-terrestrial outflow channel system. This work is leading to the development of target lists for the CaSSIS instrument.

LAPIS Calibration Activities

Almost all hardware needed for calibration of the CaSSIS instrument for the ExoMars Trace Gas Orbiter has been installed in the 103 laboratory, with a few items yet to be delivered to the Institute. We are awaiting orders of small items such as safety glasses and laboratory stools. The radiometric power supply, halogen lamp, light intensity controller and its silicon detector, the monochromatic, and the integrating sphere, have all been successfully mounted and connected to power. The calibration system is close to being ready for use.

LAPIS Visualisation Activities

We have so far focussed on 3D ray-tracing with two main applications. The first application is also related to the LOSSy sub-project. We are using computer image simulation techniques to investigate the influence of the textural parameters of a surface on its photometry. This is a crucial step to relate the experimental work conducted in the laboratory (LOSSy) to the surface photometry of planetary surfaces observed by current and future missions (LAPIS).

Fig. 4: Laboratory 103 clean room with a view of the vacuum chamber, integrating sphere, and laptop.

Surface roughness within the resolution element of inter-planetary imaging instruments cannot be easily simulated in the laboratory. We use flat surfaces in the laboratory to produce photometric functions and then use fractal surfaces in the computer combined with the measured photometric functions to simulate real planetary reflectances. This work shows real promise and is being applied to Rosetta observations of the asteroid 21 Lutetia.

Fig. 5: Example of a fractal surface (left) and the resulting prediction of the reflectance factor (right).

The second application uses ray-tracing to produce simulations of Rosetta/OSIRIS images based on shape models provided by our colleagues in the OSIRIS team. The ray tracing algorithms then allow us to determine the self-shadowing of the nucleus, which plays a significant role in modifying the local heat budget which in turn controls the outgassing. This forms a link to our normal SNF grant, which supports gas dynamics calculations.

Fig. 6: Different views of the nucleus indicating a mesh and the surface temperature distribution computed using a ray-tracing algorithm combined with a simple thermal heat balance calculation.

LAPIS: Future missions

As part of our NCCR work, we have also participated in the development of a proposal for NASA’s Europa Clipper mission. Our LOSSy facility is of direct importance to the Europa Imaging System (EIS) in providing the reflectance properties of dirty, possibly organic-rich, water-ice mixtures. We have been invited to participate scientifically in the EIS co-investigator team. We are also participating in a Discovery proposal (the Io Volcano Observer) for submission to NASA in February 2015.

### 3. Contribution to the overall goals of the NCCR

The LOSSy facility is being used to study the photometric effects of increasing amounts of ice in an ice-dust mixture. This has importance for any moon, planet, and/or exoplanet with an ice-dominated surface. Within the facility, these samples can now be evolved to produce sublimation lags. As part of the Centre for Space and Habitability (CSH) programme at UBE, we have been mixing complex abiotic molecules (tholins) with water ice and evolving this mixture in vacuo using a solar-like light source. These experiments contribute directly to the NCCR by allowing characterisation of the ice content of dirty surfaces and establishing how the surfaces can evolve.

### 4. Scientific collaboration within PlanetS

We are collaborating with EPFL within Project 4 through a PhD project, part of the LAPIS programme. Indeed, in the framework of this programme, we will set-up two facilities in parallel (at UBE and at the Space Center EPFL). The UBE facility will be the primary storage in Switzerland for OSIRIS, BELA, and CaSSIS data products as well as future missions to the Jupiter system (JUICE and IVO). It will provide calibration and archiving support. The Space Centre facility will have similar capabilities but will be targeted towards general planetary image processing (including Earth and radar data) and added value products (such as mosaics, maps, digital elevation models). A PhD student will be hired for this task. We are presently in the process of hiring this student; some promising candidates have been pre-selected.

In addition, we have identified some other collaboration with other projects of the NCCR during the last General Assembly (see Sect. 5).

### 5. Next steps

A major goal in the coming months is to establish connections with the planetary science community in Switzerland and identify potential experiments, which would have a bearing on observations of exoplanetary systems and their pre-cursors. We have used the first PlanetS general assembly to initiate interactions on the following subjects:

- Properties of ice/dust condensates in protoplanetary discs (Project 1)

- Organic aerosol properties and implications for exoplanets (Project 7)

- Mineralogy and reflectance properties of meteorites (Project 2)

We also aim to complete three publications in the coming weeks. These will be:

- Yoldi et al. on the failure of linear mixing reflectance theory for ice-dust mixtures,

- Pommerol et al. on the fitting of the angular dependence of measured reflectances using combined laboratory data and fractal-based surface roughnesses,

- Marschall et al. on the relationship of the dust distribution around comet 67P to the surface gas production rate.

Minor contributions to other papers connected to Rosetta/OSIRIS are expected in the short-term, notably

- Thomas et al., Transport of dust and ice particles across the nucleus of 67P.

In the mid-term, we expect to

- Write and publish a paper about CaSSIS in a special issue of Planetary and Space Science,

- Acquire and publish calibration data for the CaSSIS instrument,

- Complete and publish our study of light-toned deposits in Iani Chaos,

- Initialise the development of databases for the CaSSIS, BELA and OSIRIS data to provide ease of access,

- Initialise stereo reconstruction development work for use with the CaSSIS data.

### 6. List of publications resulting directly from PlanetS

None. The first paper will be by Zorine Yoldi et al. and is planned for a February 2015 submission.

### 7. List of publications with minor contributions from PlanetS

Thomas, N. et al., (2015a) The morphological diversity of Comet 67P/Churyumov-Gerasimenko, Science, in press.  (The visualisation tools have been used in a small way to support completion of this paper.)

### Project 5:  Planet Formation and Evolution

## Project leader:  Willy Benz – University of Berne

### 1. Abstract

### The goal Project 5 and its companion (Project 6), is to build upon current Swiss expertise in planet formation theory, atmospheric physics, geophysics, and climate study, in order to provide not only the theoretical framework needed for the interpretation of the present day and future observations but also to provide guidance in the development of future observational facilities. The activities of Project 5 are split in two sub-projects. In sub-project 1, we consider planetary systems as a whole, and aim at predicting/understanding mean or bulk properties such as masses, orbital parameters, mean density (or total radius), mean composition (not considering the possible partitioning of elements between atmosphere and core), luminosity, etc. In sub-project 2, we consider in more detail the internal and atmospheric structure of planets, whose global properties are computed as a result of sub-project 1.

During this first funding period, the focus of the activities in Project 5 has been the start of new activities, the hiring of new collaborators, and the setting-up of the framework for interactions with the other research projects. We have hired four new PhD students and two new postdocs. All of them started between September 2014 and March 2015. Three of these new PhD students are being shared with two other projects, which ensures close interactions on a working level.

Some aspects of the project have already led to publications while some others have produced preliminary results. Among them, one can cite the following:

- The viscous diffusion of gas inside a proto-planetary disc has been demonstrated to increase the dispersion in the C/O ratio to be expected in the envelope of giant planets.

- New theoretical estimations of the eccentricity and inclination damping timescales of forming planets result in a significantly larger number of planets ejected at distances between 20-100 AU of their star. Near-future direct imaging projects (e.g. SPHERE) will be capable of detecting this predicted population, providing a test of these models.

- We have set up a generic chemical reaction network that will be used to study both thermochemistry (equilibrium and disequilibrium) and photochemistry. This network is versatile enough to be applied to a wide range of planetary and exoplanetary atmospheres.

- We are developing an atmospheric retrieval model using modern inversion techniques, which will allow us to decipher the chemical composition and thermal structure of an exoplanetary atmosphere from an analysis of its spectrum.

- In collaboration with Project 3, we have developed a set of diagnostic tools to interpret the measurement of sodium lines using the HARPS spectrograph (Geneva Observatory), which allows us to directly infer the temperatures and densities of the atmosphere being sensed.

### 2. Results and achievements since the last report

Since the beginning of the NCCR, the activities in Project 5 have been organised along three lines:

- The hiring of new collaborators

- The setting up of new research sub-projects

- The organisation of the collaboration with other projects of the NCCR

Fig. 1: Organisation of Project 5. The names in red researchers actively participating in the project (supported by PlanetS or by other sources). The white boxes represent new research domains entirely supported by PlanetS, the light grey boxes represent research domains supported both by PlanetS and by other sources, and the dark grey box represent an already existing research domain supported by the CSH.

2.1 Hiring of new collaborators

During the first few months of Project 5, we searched for collaborators with the specific skills needed to carry out the tasks assigned to the project including those carried out in collaboration with other projects. This search resulted in the hiring of four PhDs and two postdocs:

- Sub-project 5.1

  - September 1st 2014: start of Luc Senecal (PhD student, 100% SNF-PlanetS) in collaboration with Project 6.

  - December 1st 2014: start of Dr. Sareh Ataiee, postdoc (100% SNF-PlanetS).

  - January 1st 2015: start of Thibault Roger (PhD student, 100% SNF-PlanetS) in collaboration with Project 7.

  - March 1st 2015: start of Dr. Franck Wagner, postdoc (100% SNF-PlanetS). 
Dr. Franck Wagner works at ETHZ in the group of Prof. Paul Tackley.

- Sub-project 5.2

  - September 1st 2014: start of Baptiste Lavie (PhD student, 100% SNF-PlanetS) in collaboration with Project 3.

  - September 1st 2014: start of Shang-Min Tsai, PhD student.

In addition, two PhD students, Amaury Thiabaud (funded by CSH at UBE) and David Swoboda (funded by the ERC starting grant of Prof. Yann Alibert), have been integrated into the project and will be shifted to SNF-PlanetS funding later in 2015.

Finally, Prof. Christoph Mordasini has received a 5-year Starting Grant from SNF for his project entitled “Planets in time” which brings complementary expertise in the overall area of planet evolution, and will have very close links with Project 5. He started work at UBE on February 1st 2015.

With the arrival of Dr. Franck Wagner on March 1st 2015, the Project 5 team will be complete.

2.2 Implementation of new research projects

During this reporting period, five entirely new research projects have been started:

- The planet formation models developed during the last decade (see Alibert et al. 2005, Mordasini et al. 2009, Fortier et al. 2013, Alibert et al. 2013) are based on 1+1D proto-planetary disc models. While this allows for a fast computation of the evolution of the discs, this approach has clear limitations as far as the computation of the torques leading to embryo/planet migration is concerned. To circumvent these difficulties, Dr. Sareh Ataiee has begun the implementation in the planet formation models of a full, multi-dimensional, hydrodynamic description of the discs based on the openly available GPU version of the FARGO code. We will host Dr. Clement Baruteau in March 2015 in order to implement practically the connection between the two codes.

- A dynamical model of the formation and evolution of planetary systems must include the gravitational interactions, initially, between the growing objects, and later, between mature planets. Currently, we compute the effect of these interactions using an N-body approach based on a Burlish-Stoer algorithm which is extremely time consuming and therefore very limiting. To allow for a large sample of systems to be evolved over several hundreds of millions of years, Luc Senecal is starting to implement the highly optimised GPU GENGA code developed at UZH in the planet formation and evolution models. Practically, for the first two years, his work time is split 80% in Project 6 (UZH) and 20% in Project 5 (UBE) and will reverse during the second two-year period. As a first step in Project 5, he has started computing the long-term evolution of large samples of synthetic systems.

- The assessment of theoretical models rests on comparison with observations. As the number of measurable characteristics increases, statistical comparisons become more complex. As a consequence, a good grasp of both observational biases and errors, coupled with the understanding of the model assumptions and limitations as well as advanced statistical methods, becomes essential. The expertise present in Projects 7 and 5 provides the required framework in which Thibault Roger will work towards his PhD. He has started in Project 7 (UGE) by computing the expected yield of the PLATO missions (see Rauer et al. 2014) thereby learning about observational systematics associated with transit and radial velocity detection methods. The second part of his PhD will be carried out in Project 5 (UBE) and consist of a statistical comparison between results of planet formation models and real observations.

- An atmospheric retrieval model using modern inversion techniques (e.g. Markov Chain Monte Carlo) will be an essential tool for deciphering the chemical composition and thermal structure of an exoplanetary atmosphere from the analysis of its spectrum. Working with Dr. Caroline Dorn (UBE) and Dr. Amir Khan (ETHZ) who are experts in inversion techniques, Baptiste Lavie has started to develop such a tool within Project 5 (UBE) as part of his PhD work. It is expected that after two years Baptiste Lavie will transfer to Project 3 (UGE) where he will be able to use his model to retrieve real atmospheres from actually observed spectra.

- The ability to compute the out-of-equilibrium composition of planetary atmospheres is an essential element in the toolbox necessary to retrieve atmospheric characteristics from observed spectra. Shang-Min Tsai has started the development of such a chemical reaction network as part of his PhD work in Project 5 (UBE). For this, he is collaborating with Prof. James Lyons (Arizona State University), an atmospheric chemist who is providing the chemical kinetics rates and also advising us on the construction of a chemical kinetics network.

- An atmosphere cannot be considered in isolation - exchanges between the interior and the atmosphere can take place thereby modifying over time the characteristics of the atmosphere. The computation of these exchanges is the subject of the work by Dr. Franck Wagner who will start his work in March 2015. While part of Project 5 at UBE, Dr. Franck Wagner will work at ETHZ in the group of Prof. Paul Tackley.

To enable the work of Dr. Sareh Ataiee and Luc Senecal, we have bought a new GPU-based node for our cluster. The node is presently equipped with a single K20 GPU card for testing. If tests are successful, we plan to extend our computing capability by buying seven additional GPU K20 cards.

2.3 Early results

The research topics mentioned above are new research avenues that have begun just a few months ago at best. Hence, results are still scarce and preliminary. Other topics within Project 5 represent a broadening of previous activities carried on by researchers already at UBE (Amaury Thiabaud, David Swoboda) and are therefore more mature. One has already led to an accepted publication (Thiabaud et al., in press, see http://arxiv.org/abs/1412.5784), and the second one will lead to a publication in the coming year (Swoboda et al., in prep).

Amaury Thiabaud is working on the computation of the chemical composition of planets, coupling planet formation models with computations of planetesimal and gas composition. His second paper has been accepted recently and will be published in 2015. One of the key results in this paper is that the composition of giant planet gaseous envelopes depends on the structure and evolution of the proto-planetary disc. More precisely, it was shown that the diffusion of matter in the proto-planetary disc induces a large dispersion of the C/O ratio in the envelopes of giant planets. This is particularly important, as it is often assumed in the literature that the C/O ratio in proto-planetary discs does not evolve with time.

Fig. 2: C/O ratio in the gas envelope of planets formed around a star with solar composition. In the upper panel, the composition of the gas in the proto-planetary disc evolves as a result of viscous diffusion. In the lower panel, the composition does not evolve with time. As can be seen, the variability in the resulting C/O ratio in the envelope of giant planets is higher in the former case. Adapted from Thiabaud et al. (in press).

David Swoboda is working on the computation of population synthesis models. He has conducted an extensive survey of the sensitivity of the characteristics of a synthetic planet population to the assumptions made in the modelling of the proto-planetary disc (viscosity, irradiation, dead zone, planet-gas interaction…). The amount of data to analyse is very large and thus requires more time. As an example of one of the results obtained by David Swoboda, we present in Fig. 3 two planet populations that differ only by the amount of eccentricity and inclination damping assumed for forming planets. For the first population, the eccentricity and inclination damping timescale is set to be 10 times the migration timescale, whereas for the second population, a more recent damping timescale taken from the simulations of Cresswell and Nelson (2008) has been used. As can be seen from the figure, the number of planets at large distances (a few tens of AU) increases significantly assuming the more recent damping timescales. The statistics of directly imaged planets by instruments such as SPHERE will provide a concrete test of these models.

Fig. 3: Population of planets computed for two eccentricity and inclination damping laws. On the left panel, the damping rates are taken from Cresswell and Nelson (2008), whereas on the right panel, the eccentricity and inclination damping timescales are equal to 10 times the migration timescale.

Fig. 4: Relative abundances of various atoms and molecules as computed using a custom-built chemical reaction network that solves for chemical equilibrium using a time-dependent method (rather than a relaxation/Newtonian method). The abundances are normalised relative to atomic hydrogen. At the temperatures considered, hydrogen exists predominantly in its molecular form. We consider a system only with hydrogen and oxygen. At the high temperatures considered, atomic oxygen, water and the hydroxyl radical are the important species that emerge; molecular oxygen and ozone have negligible abundances at these temperatures.

Shang-Min Tsai has reached the point where he is able to compute high-temperature chemical kinetics involving hydrogen (H) and oxygen (O). He can now address the following question: given the abundances of atoms (e.g., H and O) at a stated temperature and pressure, what are the relative abundances of molecules (e.g., water, OH)?  He is presently investigating the robustness of the answer to various numerical choices, such as the temporal and spatial order of the solution scheme.  An example of first results obtained with his new code is presented in Fig. 4.

### 3. Contribution to the overall goals of the NCCR

The overall goals of the NCCR are encapsulated by three keywords: Origin, Evolution and Characterisation of planetary systems. The different aspects of Project 5 contribute to these three overall goals of the NCCR in the following manner.

Origin: The computation of planet formation models, and in particular the work of David Swoboda and Dr. Sareh Ataiee, are clearly linked to the study of the origin of planetary systems. In addition, in the future, the work of Shang-Min Tsai will be used to take into account non-equilibrium chemical processes during planet formation. We have recently showed that the chemical reactions and condensation of species have an impact on the formation of planets (see Venturini et al. 2015, in press). However, these calculations are based on equilibrium chemistry and the chemical reaction network developed by Shang-Min will significantly improve on this.

Evolution: During the last funding period, we have computed the evolution of planets of different composition. Using these models, we have demonstrated that the observation of a large enough number of planets of different age in the 10-15 Earth masses range, can be used to constrain the water fraction in these planets (see Alibert, submitted). In addition, the work developed with Luc Senecal together with Project 6 will provide us with a tool to compute in a very efficient way the gravitational evolution of planetary systems, thus filling the gigantic time gap between the end of formation (10 Myr) and the epoch when planets are observed (a few Gyr).

Characterisation: A complete understanding of planetary spectra requires studying the atmospheric chemistry, radiation and dynamics. Atmospheric retrieval is one of the technique that can be used to obtain physical information from the measured spectrum of an exoplanet. The work of Baptiste Lavie is to develop such a retrieval code, that will later on be used to interpret heterogeneous data sets with varying resolutions, as for example the ones that will be gathered in Project 3. In addition, a proper application of atmospheric retrieval involves understanding whether an atmosphere is in chemical equilibrium; and if not, quantifying how far it is away from chemical equilibrium. The chemical reaction networks constructed by Shang-Min Tsai will allow us to quantify these effects. They will be used in particular to predict the relative abundances of molecules in chemical equilibrium, given the stated elemental abundances (e.g., abundances of carbon monoxide and water given stated abundances of carbon, hydrogen and oxygen). Our treatment also allows us to consider disequilibrium chemistry due to the motion of the atmosphere (i.e., atmospheric dynamics), an aspect that is believed to be relevant for many of the exoplanetary atmospheres we can sense with current technology.

### 4. Scientific collaboration within PlanetS

Project 5 is linked to many other projects in the NCCR. These interactions are being triggered by scientific or technical (software related) questions and by the necessity to confront theory with observation.

The approaches used for interactions between Project 5 and the other projects are essentially of three types:

- Joint collaborators (PhD students and postdocs) that actually work concurrently in two (or more) projects

- “Standard” scientific collaborations using all available modern means of communication (face-to-face, video link, email, etc.)

- Exchange of information and data analysis through theDACE Platform

We summarise below the collaborations started by Project 5 during this first reporting period. We structure the summary along the two first approaches mentioned above. The interaction with theDACE Platform has just started in January 2015.

- Type 1

  - Luc Senecal is working within Projects 5 and 6. His first two years will be at UZH (Project 6) and the last two at UBE (Project 5). As the travel time between UZH and UBE is relatively short, Luc Senecal is currently working four days per week at UZH and one day a week at UBE. This allows him to familiarise himself with Project 5 and participate in weekly group meetings.

  - Thibault Roger is working within projects 5 and 7. His first two years will be at UGE (Project 7) and his last two years at UBE (Project 5). Because of the longer travel time between the two institutions, it is not convenient to organise weekly visits to Bern. Therefore we use videoconferencing techniques to ensure frequent contacts.

  - Baptiste Lavie is working within Projects 5 and 3. His first two years will be at UBE (Project 5) and his last two years at UGE (Project 7). Again, due to distance, viodeoconferencing is being used to keep in frequent contact.

- Type 2

  - Projects 3 and 5 have developed together a set of novel diagnostics to interpret the sodium lines observed in the atmospheres of hot Jupiters, as measured by Geneva researchers using the HARPS spectrograph. These newly discovered diagnostics allow us to infer the temperatures of atmospheres, as well as the densities of the sodium atom, using simple-to-use algebraic formulae. A paper describing this technique has already been submitted to The Astrophysical Journal Letters.

  - Projects 1, 2 and 5 have begun work on the chemical composition of proto-planetary discs. For this, Amaury Thiabaud (Project 5) will develop a time-dependent model of chemical condensation based on astrochemical reaction rates with the help of Project 2, and for some aspects, collaborate with Shang-Min Tsai. Using this model, the chemical composition of the gas in proto-planetary discs will be computed. Diagnostic tools and comparisons with observations are being planed with Project 1.

  - Members of Projects 1, 3, 5, and 7 are participating in the building of a coherent Swiss position regarding the future ground-based instrumentation at ESO (see section 2.1.3 of the report).

### 5. Next steps

For the next funding period, the scientific goals of Project 5 are the following:

- Complete the survey of the effect of proto-planetary disc properties on the characteristics of the planet population at the end of the formation phase and after long-term evolution. Long-term evolution will be computed routinely using the GENGA code, in collaboration with Project 6.

- The next generation of planet formation coding, involving FARGO for the computation of the gas disc evolution, and a planetesimal mass function, will produce its first results.

- Extend the computation of planetary bulk composition of planets forming around stars of different types and composition looking for correlations between planet and stellar composition, in collaboration with Projects 1 and 2.

- Extend the chemical network to involve C-, H-, and O-bearing molecules. These calculations will contribute to the atmospheric retrieval models developed with Project 3.

- Refine the estimation of the PLATO yield, which will be computed in collaboration with Project 7.

- Start the computation of the dynamics of planetary interiors for different kinds of planets predicted by planet formation models. Start the computation of the dynamics of planetary interior for different kind of planets predicted by planet formation models.

By the end of the first period, we will have developed the next generation of integrated planet formation models, taking into account the dynamics of gas and planetesimals. In addition, we will use in these models the GPU based N-body integrator GENGA in order to increase the computation speed. Taking into account the dynamics of planetesimals will also allow us to compute in a better way the composition of planets as predicted by our models. The computation of the planetary bulk composition will serve as the initial condition for the determination of the planetary interior, as well as the computation of the planetary atmospheric dynamics and evolution. In addition, such computations will represent one of the bases for the interpretation of future CHEOPS observations.

In parallel to these theoretical efforts, our retrieval code will have been developed and tested and will be ready to interpret future observations of atmospheric composition using, e.g., high-resolution transit spectroscopy. This part of our project, which relies on a strong interaction with Project 3, will be used, in the long term, to compare results of formation and evolution models with observed characteristics of exoplanets.

### 6. List of publications resulting directly from PlanetS

Heng, K., Wyttenbach, A., Lavie, B., Sing, D., Ehrenreich, D., et al. 2015, ApJ Letters, submitted in January 2015

### 7. List of publications with minor contributions from PlanetS

Dorn, C., Khan, A., Heng, K., Alibert, Y., Benz, W. et al. 2014, Can we constrain interior structure of rocky exoplanets from mass and radius measurements?, A&A, in press, astroph/1502.03605

Venturini, J., Alibert, Y., Benz, W. & Ikoma, M. 2014, Critical core mass for enriched envelopes: the role of H2O condensation, A&A, in press, astroph/1502.01160

Pfyffer, S., Alibert, Y., Benz, W. & Swoboda, D. 2014, Theoretical models of planetary system formation. II. Post-formation evolution, A&A, in press, astroph/1502.04260

Thiabaud, A., Marboeuf, U., Alibert, Y., Leya, I., & Mezger, K., Gas composition of the main volatile elements in protoplanetary discs and its implication for planet formation, A&A 574,  AA138,  2015

Leone, G. Tackley, P., Gerya, T., May, D., & Zhu, G., Three dimensional simulations of the southern polar giant impact hypothesis for the origin of the Martian dichotomy, GeoRL 41,  8736,  2014

Li, Y., Deschamps, F., & Tackley, P., The stability and structure of primordial reservoirs in the lower mantle: insights from models of thermochemical convection in three-dimensional spherical geometry, GeoJI 199,  914,  2014

Kempton, E., Perna, R., & Heng, K.,  High Resolution Transmission Spectroscopy as a Diagnostic for Jovian Exoplanet Atmospheres: Constraints from Theoretical Models,  ApJ 795,  24,  2014

Li, Y., Deschamps, F. & Tackley, P., Effects of low-viscosity post-perovskite on the stability and structure of primordial reservoirs in the lower mantle, GeoRL 41,  7089,  2014

Yao, C., Deschamps, F., Lowman, J. , Sanchez-Valle, C., & Tackley, P. ,  Stagnant lid convection in bottom-heated thin 3-D spherical shells: Influence of curvature and implications for dwarf planets and icy moons,  JGRE 119,  1895,  2014

Fortier, A., Beck, T., Benz, W., Broeg, C., Cessa, V., et al., CHEOPS: a space telescope for ultra-high precision photometry of exoplanet transits, SPIE 9143, 91432J, 2014

Conferences:

- Alibert ISSI Team on planet formation (statistical constraints from observations, dynamics of planetary systems), Bern, 06/14, Yann Alibert, organisation

- EWASS 2014 07/14, Willy Benz, invited plenary talk

- “Explosions I have known”, Stirling Colgate’s Legacy in Science Symposium, 08/14, Willy Benz, invited talk

- ISSI-Beijing forum on “Micro-second astrometry forum”, Beijing (China) 08/14, Willy Benz, invited talk

- ISSI/ISSI-BJ workshop on "The disk and the relation to the formation of planets and their protoatmospheres", Beijing (China), 08/14, Willy Benz, convener

- Chinese Swiss Space Science Workshop, Lenk, 09/14, Willy Benz,  oral presentation

- Plato Theory Meeting, London 09/14, Yann Alibert, oral presentation

- Stockholm Cheops Science Team Meeting, 09/14, Yann Alibert, Kevin Heng, Willy Benz, oral presentations

- Planet Formation and Evolution 2014, Kiel 09/14, Yann Alibert, Julia Venturini, Kevin Heng, oral presentations (one invited) and poster presentation

- Space Matinée, Technisches Museum, Vienna (Austria), 09/14, Willy Benz invited by the Swiss Embassy in Vienna

- SPIRou Workshop, Paris 09/14, Yann Alibert, invited oral presentation

- HP4 meeting, Rostock 09/14, Caroline Dorn, invited oral presentation

- PLATO workshop 10/14, Yann Alibert, invited oral presentation

- Collegium Helveticum, Zürich, 10/14, W. Benz, invited keynote talk

- Geneva Kick-Off meeting, Geneva 10/14, Yann Alibert, Willy Benz, oral presentations

- Collegium Generale, University of Bern, 10/14

- ‘Getting ready for planetology beyond the solar system’, Ringberg 11/14, Yann Alibert, Willy Benz, Julia Venturini, oral presentations (one invited review)

- ‘Structure and dynamics of Earth-like planets’, Paris 11/14, Caroline Dorn, invited oral presentation

- PLATO meeting, Taormina 12/14, Yann Alibert, invited review

- CHEOPS Science Team meeting, Catania 12/14, Yann Alibert, Willy Benz, oral presentations

- ‘ESO in the 2020s’, Garching (Germany), 01/15, Yann Alibert, invited review

- “What is life” Conference, University of Bern, 01/15, Willy Benz, invited keynote presentation

### Project 6:  Numerical Laboratory for Planet Formation

## Project leader:  Ben Moore – University of Zürich

### 1. Abstract

### The aim of Project 6 is to study in detail some of the key processes involved during the formation and evolution of planetary systems, from the collapse of the proto-stellar cloud through to the formation of rocky Earth-like planets. Insights into the various phases of this complex evolution can be obtained through supercomputer calculations using several state-of-the-art numerical codes developed in Zurich that follow the hydro-dynamical and collisional processes that drive planet formation. Amongst the key goals of Project 6 are: to determine the initial conditions of planet formation, to test and compare models of planet formation with observational data, to make predictions for the statistical properties of planet populations, to explore the long term evolution and stability of planetary systems, to study the accretion history of terrestrial planets and the radial elemental abundances, and to explore the frequency of habitable planetary systems in different environments of our Galaxy.

In this first phase of the project we began hiring students and postdocs for our two sub-projects (WP1 and WP2). As of January 2015 three positions have been started or about to start (2 postdocs and 1 PhD student shared with Project 5) while two more PhD students have just accepted to start in Fall 2015. We have initiated the testing of a new generation of 3D self-gravitating disc simulations with enough resolution to follow the collapse of individual protoplanets. We have begun the analysis of the vorticity properties of discs undergoing vastly different phenomena, such as gravitational instability and Rossby wave instability, in order to understand which conditions are conducive to the formation of long-lived vortices that may efficiently accumulate dust particles, perhaps leading to planetesimal formation. For WP2, whose goal is to study the late stages of planet formation, in particular the formation of terrestrial planets, we have performed the initial set of simulations conceived for the PhD thesis in collaboration with Project 5. We have used the new GPU-based GENGA code, which runs 30 times faster than the popular Mercury code while retaining comparable accuracy. A paper describing GENGA has been published. Tests for the release of GENGA2, an even faster version of the same N-Body code, have been successfully initiated.

The long-term plan is to exploit such codes in order to construct an unprecedented large library of dynamical simulations of exoplanetary systems to be implemented in DACE, in collaboration with theDACE Platform.

### 2. Results and achievements since the last report

2.1 Sub-project WP1

This sub-project builds on the continued efforts of Prof. Lucio Mayer's group at UNIZH to simulate the formation and evolution of protoplanetary discs with 3D, multi-physics models. Dr. Clement Surville, the NCCR postdoc hired in support of this task, arrived at UNIZH at the end of October. Dr. Clement Surville, is an expert in grid-based hydro codes tailored to accurate modelling of the gas flow in protoplanetary discs, and wrote a 2D finite-volume cylindrical grid code with the so called "well-balanced scheme" for his PhD work in Marseille (completed end of 2013).

Work has begun in two directions. First, Dr. Clement Surville is learning how to use and modify the 3D AMD code RAMSES in collaboration with Prof. Romain Teyssier at UNIZH in order to include his well-balanced scheme into Ramses. Ideally, the scheme should be ideally utilised in combination with radiative transfer solvers in order to capture, for example, the transition between the optically thick midplane and the optically-thin radiative surface of the disc. Capturing transition zones such as this is important since we already know that the outcome of disc instabilities, such as gravitational instability or MRI, is sensitive to the rate of energy loss via radiation.

Second, Dr. Clement Surville is beginning to extend his work on planetesimal formation in self-gravitating vortices (Surville et al. 2014, submitted) triggered by Rossby waves, by considering the case of self-gravitating discs. The key background question to address is how to accumulate enough dust to grow planetesimals large enough for gravity to take over and lead to the collapse of the dust layer. A related question is whether the gravoturbulent flow in gravitationally unstable discs generates vortices. To this aim, he is beginning to analyse the gas flow in existing 3D SPH simulations (based on the Gasoline code) of self-gravitating massive protoplanetary discs available from Prof. Lucio Mayer's group at UNIZH. He will compare the vorticity structure with the one developing in non self-gravitating discs that undergo the Rossby wave instability. He will also compare with other mechanisms to accumulate solids, which rely on pressure gradients and gas drag along spiral arms. Vorticity structure is indeed important for the eventual long-term survival of vortices in the disc. The expectation is that the much stronger density fluctuations induced by the spiral pattern in self-gravitating discs may have an impact on the properties of the flow relevant for vortex formation. Preliminary results also show that vorticity structure is quite different in the gravitationally unstable discs relative to the light discs undergoing the Rossby wave instabilities; while the latter supports anticyclonic vortices, in the former the flow is cyclonic in the regions that may be conducive to dust accumulation, such as along the spiral arms.

Fig. 1: Comparison of density and vorticity properties in the flow perturbed by Rossby waves generated by a gap-opening planet (left) and in a self-gravitating disc such as that of Fig. 2 (right). The density (with background gas subtracted) and the Rossby number (with background gas subtracted) are shown as a function of radius and azimuth. On the left, the high-density regions in the outer part of the gap are anticyclonic (negative Rossby number), while in the self-gravitating disc (right), the high density structures are cylconic, with a positive Rossby number.

In Fig. 1 we can see an example of the wave-like structure in a self-gravitating disc (computed with GASOLINE) and in a non-self gravitating disc subject to the Rossby wave instability (computed with the cylindrical grid code of Dr. Clement Surville).

In parallel, Prof. Lucio Mayer, aided by Valentina Tamburello (PhD student supported through another grant), is continuing to study gravitational instability and fragmentation of protoplanetary discs using increasingly more sophisticated numerical simulations with an updated radiative transfer scheme that allows local opacity reduction effects such as those due to grain sedimentation (see Fig. 2).

He is also studying the capability for running much higher resolution simulations using a new SPH code, ChaNGa, which improves substantially on GASOLINE in terms of scalability on large parallel supercomputers owing to the CHARM++ interface that performs dynamic load balancing. This way Prof. Lucio Mayer has recently been able to test-run the first 50 million particles disc simulations at the Swiss National Supercomputing Centre.

Fig. 2: A fragmenting 3D massive protoplanetary disc computed with the new radiative transfer scheme described in Rogers & Wadsley (2011).

2.2 Sub-project WP2

We have completed an open source GPU implementation of a hybrid symplectic N-body integrator, GENGA (Gravitational ENcounters with Gpu Acceleration), designed to integrate planet and planetesimal dynamics in the late stage of planet formation and stability analyses of planetary systems. GENGA handles close encounters with very good energy conservation, which is essential in long-term planetary system integration. The GENGA code supports three simulation modes: Integration of up to 2048 massive bodies, integration with up to a million test particles, or parallel integration of a large number of individual planetary systems. In a paper accepted for publication in ApJ (see http://arxiv.org/abs/1404.2324v2) we compare the results of GENGA to Mercury and pkdgrav2 in respect to energy conservation and performance, and find that the energy conservation of GENGA is comparable to Mercury and around two orders of magnitude better than pkdgrav2 (see Fig. 3). GENGA runs up to 30 times faster than Mercury and up to eight times faster than pkdgrav2.

Dr. Joachim Stadel and Simon Grimm are also about to release the GENGA2 code and a paper is in preparation. This second version of the code uses a new integration technique, which gives order of magnitude better long-term energy conservation than GENGA. This method also removes the velocity dependence of the close encounter region around bodies so that it is now simply related to the Hill radius. This is very important for running with a larger number of bodies so that the percentage of bodies in close encounter at any time is independent of N. In this code we therefore also improve the computation for large N, in particular using more than one GPU device for the same calculation (with roughly 10 GPU devices GENGA2 will be able to integrate around 1 million planetesimals for 100 million years)

Fig. 3: Comparison of GENGA with the CPU based treecode Pkdgrav2 and the conventional serial code Mercury. Conservation of energy is comparable or better than Mercury but the code runs 30 times faster (left). A comparison of the results of a simulation of planetesimal collisions run with identical initial conditions but with different code is shown on the right.

Finally, the PhD student Luc Senecal, who holds a joint position with Bern as of September 2014, has learned how to use the planet-formation codes developed in Bern and Zurich (GENGA). The aim is to combine the two codes. Luc Senecal has written a conversion code to take output data from the planet formation model developed in Project 5, to give input data for GENGA in order to make a fast link between the two codes. He is now using GENGA to compute the long term gravitational evolution of planetary systems predicted by the planet formation models of Project 5.

- Contribution to the overall goals of the NCCR

The initial steps carried out so far in both WP1 and WP2 are essential to better understand the key physical processes that govern the formation and evolution of planets, in particular gas giants for WP1 and rocky planets or cores of gas giants for WP2. Hence these can be regarded as essential foundations of the theory efforts of the NCCR. The findings of Project 6 will immediately feed advances in population synthesis models, a focus of Project 5. In addition the investigation of processes relevant for disc evolution has connections with all aspects of the NCCR since discs are the birthplace of planets and as such will also be studied in some of the observational component of the NCCR (Projects 1 & 2).

### 4. Scientific collaboration within PlanetS

There is at this stage a shared PhD position (Luc Senecal) with Project 5, whose task is to interface the semi-analytical planet evolution models of Project 5 with the N-Body simulations of interacting planetary embryos carried out with GENGA and GENGA2. Data produced with GENGA simulations at UNIZH will be imported soon into an early version of theDACE Platform and will be used to model the most interesting exoplanet systems, thereby strengthening the collaboration with groups at the University of Geneva (DACE platform and Project 7). Prof. Lucio Mayer and his group are collaborating actively with the group of Prof. Michael Meyer (Project 1) at ETHZ, in particular on planet migration, in a study carried out with former ETHZ postdoc Dr. Farzana Meru. The first results have been reported in a paper close to acceptance which revisits the standard gap opening theory showing that gaps open only when planets do not migrate too fast across the region of the disc that satisfies the gap opening conditions.

### 5. Next steps

For WP1 in the next 6 to 9 months, we will perform the first global simulations of disc instability with enough resolution to follow the collapse of the clumps down to the dissociation stage, namely without having to separately run a collapse simulation for the clump only, as done so far due to computational bottlenecks (Galvagni et al. 2012). We will repeat the initial stage of these simulations, up to the fragmentation stage, using the RAMSES code with the M1 approximation for radiative transfer, in order to explore how the different radiative transfer schemes affect disc instability. We will also perform the first tests of the well-balanced scheme inside RAMSES on a year timescale. Finally, we will write a paper on vorticity evolution in gravitationally unstable discs and its implications for the accumulation of solids, comparing with the outcome in the case of non self-gravitating discs undergoing the Rossby wave instability.

### 6. List of publications resulting directly from PlanetS

The first paper on WP1, with PlanetS postdoc Dr. Clement Surville, will appear in the next 9 months.

### 7. List of publications with minor contributions from PlanetS

Clement Surville and Pierre Barge, "Quasi-steady vortices in protoplanetary discs: I - From dwarfs to giants", Submitted to Astronomy and Astrophysics

Matej Malik, Farzana Meru, Lucio Mayer and Michael Meyer, "On the gap-opening criterion of migrating planets in protoplanetary discs", submitted to ApJ

Simon G. Grimm and Joachim Stadel, "The GENGA Code: Gravitational Encounters in N-body Simulations with GPU Acceleration", Astrophysical Journal, 796, 23

### Project 7:  Multi-faceted determination of planet properties and system architecture

## Project leader:  Stéphane Udry – University of Geneva

### 1. Abstract

### The main interests in the exoplanet field, at the heart of the PlanetS initiative, undoubtedly reside for the next decade or two in the detection and characterisation of solid planets, to constrain the physical and atmospheric conditions at the planet surface, and to search for possible tracers of life in their atmospheres. Project 7 aims at consolidating and improving the first part of this enthusiastic endeavour, i.e. detection and fundamental characterisation, with a special emphasis on small-mass planets. This can only be achieved in an integrated view of the systems, including as well more massive planets in the outer regions and their effect on the dynamical evolution of the system. For this, the project is organised along several main lines, to: 1) Optimally determine planetary physical and orbital parameters through robust statistical treatments of all available information, possibly of different natures, taking full advantage of theDACE Platform. 2) Understand planetary system architecture (formation, evolution, and stability) and possibly planet physical properties from the semi-analytical dynamical modelling of planetary systems, including those hosting circumbinary planets. 3) Help constrain the internal structure of small-mass planets, down to super-Earths (and Earths), through the determination of the basic physical parameters (mass and radius) of planets transiting bright stars. 4) Probe the outer regions of planetary systems, fundamental for the systems’ dynamical evolution, through astrometric and direct imaging observations.

This report covers the first 9 months of the project, presenting the configuration of the team set-up, on-going work, and first scientific results.

Fig.1: Examples of exoplanet systems to characterize: Left. Artistic view of the system of 3 Neptunes around HD69830. Right. Mass-period distribution of the known exoplanets, with a colour-coded indication of the technique used for the detection.

### 2. Results and achievements since the last report

New aspects with regard to the PlanetS proposal:

A major change in the landscape of detection and basic characterisation of exoplanets took place in the period between the NCCR proposal and the actual beginning of the project with the selection by the European Space Agency of PLATO as its M3 mission, to be launched in 2024. The goal of PLATO is the detection and fundamental characterisation (mass, radius, mean density) of terrestrial planets around bright stars, out to the habitable zone of the system. It thus fits perfectly in the framework of PlanetS in general, and more particularly in the activities of our sub-project 7.3 focusing on the precise estimate of the radii of small-mass planets. Switzerland is strongly involved in PLATO with payload parts under the responsibility of UBE (Prof. Willy Benz) and the responsibility of the organisation of the ground-based follow-up in Geneva (Prof. Stéphane Udry), a key aspect for the scientific return of PLATO. As for CHEOPS, PlanetS is developing the complete framework for Switzerland to play a major role in the scientific exploitation of the PLATO data. Sub-project 7.3 now involves NGTS (Next Generation Transit Survey), CHEOPS and PLATO. The new organisation chart is provided in Fig.2.

Fig.2: Updated organisation chart of the organisation of Project 7.

Hired personnel: (see further down for a description of the sub-projects)

Part of the hard work at the beginning of a NCCR is to set-up efficient teams by hiring the best people available on the market for the needs of the various projects. Here is the situation of the hiring in Project 7:

- Sub-project 7.1

  - June 1st 2014, start date of Dr. Danuta Sosnowska, computer scientist (50%, SNF-PlanetS)

  - January 1st 2015, start date of Thibault Roger, PhD (100%, shared with Project 5, SNF-PlanetS)

  - April 1st 2015, expected start date of Dr. Rodrigo Diaz, postdoc (100%, Cash UGE).

- Sub-project 7.2

  - October 1st 2014, start date of Dr. Jean-Baptiste Delisle, postdoc (100%, In-kind UGE)

- Sub-project 7.3

  - January 1st 2014, start date of Dr. François Wildi, senior engineer (50%, In-kind UGE, CHEOPS) in advance of NCCR start

  - Apr 1st 2015, start date of Adrien Deline, PhD (100%, Cash-UGE, CHEOPS)

  - September 1st 2014, start date of Dr. Sophie Saesen, senior researcher (30%, Cash UGE, PLATO)

  - November 1st 2014, start date of Dr. Daniel Bayliss, postdoc (100%, SNF-PlanetS, NGTS)

- Sub-project 7.4

  - October 1st 2014, start date of Manuela Raimbault, PhD (100%, SNF-PlanetS)

  - April 15th 2015, expected start date of Dr. Anthony Cheetham, postdoc (100%, In-kind UGE)

To these positions financed through the NCCR, we have to add the “self-group” contributions to the project:

- Sub-project 7.1

  - Dr. Damien Ségransan, senior researcher (20%), sub-project leader

  - Dr. Rodrigo Diaz, postdoc (100%), till April 1st 2015

  - Dr. Maxime Marmier, Adjoint scientifique (60% from July 1st 2014 to March 31st 2015, and 10% from April 1st 2015 to May 31st 2015)

- Sub-project 7.2

  - Prof. Stéphane Udry, professor (10%), sub-project leader

- Sub-project 7.3

  - Prof. Stéphane Udry, professor (10%), sub-project leader

  - Dr. François Bouchy, senior researcher (20%, NGTS)

  - Prof. Didier Queloz, professor (10%, CHEOPS)

  - Dr. Bruno Chazelas, specialised physicist (50%, NGTS)

  - Dr. François Wildi, senior engineer (30%, CHEOPS)

  - Adrien Deline, PhD  (100%, CHEOPS), till March 31st 2015

- Sub-project 7.4

  - Dr. Damien Ségransan, senior researcher (20%), sub-project leader

Remarks:

- In our original planning, 2-yr postdoc slots were foreseen for various sub-projects. We quickly realised, however, that 3-yr positions were more suitable for attracting the best candidates. We reorganised our priorities and available budget accordingly, including the UGE local support. Some of the postdocs are then first financed by the in-kind contribution of UGE (Delisle, Cheetham) before switching to SNF-PlanetS funding.

- Dr. Danuta Sosnowska actually moved temporarily to the DACE Platform on November 1st 2014 (likely until October 2015), to cope with the difficulty of finding a programmer for the platform and to work on the implementation of the GENGA code (Project 6) into DACE, an activity in line with her expertise.

- Adrien Deline will start in April 2015 as a PhD student working on the CHEOPS calibration and early science under the supervision of Prof. Didier Queloz (Coordinator of the Geneva activities for CHEOPS) and Dr. David Ehrenreich (CHEOPS mission scientist). The start is earlier than foreseen previously (beginning of the 2nd year) due to the advancement of the CHEOPS project. The first four months, before the PlanetS financing (Cash UGE), will be insured locally by the Department of Astronomy of UGE (Self-group).

Two important positions are still to be filled: the leaders/co-leaders of sub-projects 7.2 and 7.3. Both positions will be financed on Self-group and In-kind UGE money.

- Discussions are progressing well with Dr. Rosemary Mardling from Monash University (Melbourne), a world specialist in the analytical modelling of the dynamical evolution of planetary systems. We already have a close collaboration on the topics of sub-project 7.2 with Dr. Rosemary Mardling. We are now in the process of setting-up a shared 50%-50% position between the universities of Monash and Geneva, to have her work for PlanetS in Geneva half of each year. Difficulties have been encountered with the local state administration with respect to getting a 50% time work, due to restrictions after the vote on immigration in Switzerland in February 2014. Some fine-tuning is also necessary on the Australian side.

- The second person to still hire is the successor of Prof. Didier Queloz who moved 75% of his activities to Cambridge. The new professor will work in the field of exoplanets (as foreseen in our organisation, leading sub-project 7.3). The hiring process will start soon, going through the academic procedures of the University of Geneva.

Results & Achievements:

Since the detection of the first planet orbiting a solar-type star other than our Sun, our knowledge about exoplanets has dramatically increased, thanks to the systematic monitoring of large samples of stars by various detection techniques (radial velocities, photometry, micro-lensing, and recently, direct imaging). The results bring valuable constraints to planet formation theories, models of planet interior structures, and atmosphere physics. Basic planetary parameter measurements are the primary vehicles for understanding the interaction between the inner structure and the atmosphere of a planet, a key element for a complete picture of its ecological system. The strongest constraints are achieved when different kinds of observations, providing complementary information, are combined together and confronted with theoretical predictions. In this project, an ambitious long-term research plan based on comprehensive ground and space-based high-quality observations is envisioned. This includes the development of (new) constraints from theoretical modelling of the systems, and the development of high-level tools to optimally combine the variety of available information, of potentially different intrinsic nature (observational, theoretical, numerical), all necessary for solving the challenges of detecting the smaller signal amplitudes associated with smaller-mass planets. The goal is to provide the optimal basic information to advance our understanding of the formation, structure, and eventually the habitability, of planetary systems.

With this goal in mind, the project is organised along four main lines (sub-projects).

2.1 Optimal determination of planetary physical and orbital parameters

The determination of planetary physical properties from combined data obtained from various sources (different instruments, techniques, or nature) represents an important improvement over parameters obtained from individual approaches. We focus in this sub-project first on the tools for an optimum determination of basic physical parameters and system architectures, with a longer-term goal of studying well-defined, unbiased, statistical distributions of these parameters. Statistical properties of planet sub-populations (different planet and host star characteristics, different environments) provide priceless observational constraints in this context.

A summary of the activities in sub-project 7.1 during the period covered by the report follows:

- Dr. Rodrigo Diaz, Dr. Damien Ségransan, and Dr. Danuta Sosnowska started to work on algorithms (to be implemented in DACE) for the derivation of multi-planet system solutions from radial-velocity, transit and/or astrometric observations, taking into account the various sources of noise (instrumental and stellar).

- Dr. Damien Ségransan with Dr. Jean-Baptiste Delisle (7.2) and Nicolas Buchschacher (DACE Platform) implemented in DACE a tool allowing for a quick determination of the parameters of a multi-planet system, based on the modelling of the system as a sum of Keplerian motions.

- Dr. Rodrigo Diaz also worked i) on the development, testing and characterisation of methods to estimate the Bayesian evidence, a key element for model comparison (so far, only applied to radial-velocity multi-planet system data), and ii) on simple modelling of activity-induced radial-velocity jitter using activity proxies such as the log(R’hk) index.

- Thibaut Roger, the PhD in co-supervision between projects 7.1 and 5.1 started work on January 1st 2015. He will spend the first 2 years in Geneva, and then move to Bern. He will regularly visit the other institution while in Geneva or Bern. During the first year, his work will focus on the reassessment of the expected PLATO planet yield, and the inferred telescope time required for the associated ground-based follow-up. The idea is to improve in various ways the first estimate made 4 years ago for the ESA selection process. Thibaut Roger is now familiarising himself with the transit and radial-velocity detection techniques, understanding their limits and inherent biases. He will then rethink the whole chain of criteria for the planet yield estimate.

2.2 Constraints from dynamical modelling of planetary systems

Important constraints on planet system architectures are obtained through dynamical analyses of multi-planet systems. Planet interactions during formation and long-term secular evolution, often also including dissipative processes, shape the system on time scales from a few orbital periods up to the star’s lifetime. A correct modelling of these effects is therefore mandatory for a deep understanding of planet formation and evolution, and for a sensible comparison of the end-state of the evolution process with observations. We aim to develop an analytical framework that will allow us to clearly underline the effect of specific parameters on the evolution of the system, or point out the potential inter-connection between a priori unrelated parameters (e.g. physical and orbital, etc.). The approach will be useful to study closely packed systems with strong planet-planet interactions, circumbinary planets, or the long-term secular evolution of multi-planet systems. Results can then be compared with state-of-the-art numerical integrations (Project 6).

During the period covered by the report, we can outline the following activities:

- Dr. Jean-Baptiste Delisle started on October 1st 2014. He is presently working on two important aspects: i) the effect of dissipation in the protoplanetary disc on shaping the architecture of planetary systems via convergent migration, resonance trapping and the pushing out of resonance, and ii) a parameterisation for the stability of multi-planet systems, to be used as a quick proxy in solution finding schemes. Following up on the work done in his thesis, he is also looking for analytical criteria that would allow a classification of the evolution of resonant planets that undergo migration/damping by the protoplanetary disc.

- Dr. Jean-Baptiste Delisle contributed to the implementation in DACE of a self-defining Keplerian fit for radial-velocity data, and is helping Manuela Raimbault (7.4) to do the same for astrometry.

- As stated above, negotiations are still on-going to have Dr. Rosemary Mardling part time in Geneva where she would co-lead sub-project 7.2. For the moment interactions are done via Skype. Significant progress has been made in the analytical estimate of Transit Timing Variations (TTV) of planets in systems. Several hundreds of packed systems detected by the Kepler satellite show significant TTV signatures, and are still waiting for a meaningful analysis. We hope to be very soon able to solve these cases.

2.3 Constraining the structure of small mass planets

The bulk composition and interior structure of a planet carry the fossil signature of its early formation history and internal evolution. On the low-mass end of the planet-mass distribution, a broad diversity is observed. Transiting Neptunes and super-Earths provide, then fundamental information to constrain the inner composition of these planets. Even if no unique solution is expected (degeneracy), basic guesses on the chemical species and constraints from planet formation models should allow for at least a partial solution of the problem. In this context, it is of the utmost importance to precisely measure the radii of small-mass planets. To achieve this goal, the next generation of transit surveys will concentrate on bright stars, allowing at the same time for, at the same time, precise radius measurement and high-precision radial-velocity confirmation and mass estimate. The focus of this sub-project is to help three major projects aiming to detect small-size transiting planets around bright stars: NGTS, CHEOPS and PLATO.

- NGTS: an ensemble of 12 robotic telescopes, in Paranal, Chile, designed to detect transiting Neptunes and possibly super-Earths around small stars (K and M dwarfs).

Fig. 3 View of the NGTS telescopes in Paranal

Dr. Daniel Bayliss started work officially on November 1st 2014. He participated to the NGTS consortium meeting in Berlin (November 3rd and 4th 2014). He is now familiarising himself with the project, and analysing the first images obtained from the first unit telescope fully installed in Paranal. For the moment these images are used to test NGTS performance, and the CCD that is still showing some suspect behaviour.

- Dr. François Bouchy participated in the installation and commissioning of the first 5 telescope units. He is also following the analysis of the first NGTS images. The facility is not yet completely robotized so observations are only obtained when someone is on site. The installation of the remaining telescope units and the beginning of operations are foreseen for March-April 2015. Both Dr. François Bouchy and Dr. Daniel Bayliss will actively participate to the final installation and tests.

- CHEOPS: ESA S1 mission, transit satellite for the precise follow-up of stars known to host planets. The goal is to observe or re-observe the transits of small-size planets in front of bright stars, and thus improve the estimation of planet radii and densities.

- The CHEOPS science team has established various working groups helping with the technical development of the satellite and is starting to prepare the scientific programme definition and the operations. Project 7 members help in various ways, contributing to the working groups: Dr. Rodrigo Diaz as a member of the WG on stellar parameters, and Dr. Daniel Bayliss in the WG assessing the performance of the instrument.

- Adrien Deline, PhD student, will start in April to work on the CHEOPS calibration and early science.

- PLATO: ESA M3 mission, transit mission that will unveil thousands of characterised terrestrial planets around bright stars, up to 100 of them in the habitable zone.

- Start of the organisation of the PLATO follow-up office in Geneva, mainly involving Prof. Stéphane Udry (PLATO follow-up scientist), Dr. Rodrigo Diaz, and Dr. Sophie Saesen from PlanetS.

2.4 Probing the outer regions of planetary systems

This sub-project focuses on the detection and orbital characterisation of planets on long-period orbits. The effort is tailored to the analysis of the results from two major instrumental developments that started activities in 2014, in phase with the start of the NCCR: the Gaia ESA mission and SPHERE on the VLT/ESO. Gaia will provide astrometric measurements allowing us to probe giant planets in the 1 to 7 AU range around near-by stars. SPHERE imaging is, on the other end, more sensitive to massive planets beyond 5 AU. As a CoI institute of the SPHERE consortium, UGE (including PlanetS members) in collaboration with ETHZ (Project 1) is sharing in the 260 nights of GTO observing time granted to the consortium. For the moment, activities of sub-project 7.4 are developing along the following lines:

Astrometry

Manuela Raimbault started as a PhD student in Geneva on October 1st 2014. Her PhD topic is planet detection using astrometric measurements. On-going collaborations with J. Sahlmann (ESA fellow working on the Gaia mission) on astrometric surveys (Gaia, VLT) provide the framework for her thesis. She is now familiarising herself with orbit fitting and orbital and physical parameter determination, including development of related tools for DACE. In preparation for the analysis of the Gaia data to be combined with high-precision radial velocities, she is also starting to work on combining Hipparcos public astrometric data with in-house Coralie radial-velocity observations, to derive the unbiased mass function of companions to solar-type stars from binaries down to the low end of the brown-dwarf regime.

SPHERE: Planet imager on the VLT, starting operations now

The postdoc position to work on direct imaging, and in particular on the SPHERE observations, has been filled. The candidate, Anthony Cheetham, will start in Geneva directly after the end of his PhD at Sydney University with Prof. Peter Tuthill mid-April 2015. He is working on high-contrast, high angular resolution imaging for planet detection, has expertise in observations with large telescopes (VLT, Gemini, Subaru), and in data reduction. He has already applied for telescope time (including SPHERE). He is also a specialist of sparse aperture masking, a device foreseen for SPHERE.

International Collaborations:

A short list of collaborations within various ongoing, developing, or running projects for planet detection (only indicated are the ones with clear NCCR relation or support) follows:

- Radial velocities: HARPS/3.6m, ESPRESSO/VLT, NIRPS/NTT. For the radial velocities, the link with Project 7 of PlanetS is not at the level of instrument development or operation, but rather with the analysis of the data in combination with observations obtained through other detection techniques (hereafter).

- Transit: NGTS, CHEOPS/ESA, PLATO/ESA, TESS/NASA. In addition to the analysis/use of the results, the involvement of PlanetS in these projects is at the level of the preparation and operations (follow-up observations).

- Imaging: SPHERE/VLT. PlanetS supports the analysis/use of the observations.

- Astrometry: GAIA/ESA, PRIMA/VLT. PlanetS supports the analysis/use of the observations.

### 3. Contribution to the overall goals of the NCCR

The proposed approach will benefit all projects of the NCCR. Basic physical parameters of planets (mass, radius, density) are primary inputs for internal structure modelling and, as such, will also influence the interpretation of observations of atmospheric features (Projects 1,3, and 5), a key element of habitability assessment. They are the first elements of a deeply inter-connected chain of analysis. The understanding of the dynamical evolution of systems also sets strong constraints on planet formation and evolution history and hence on chemical composition (Projects 1,2,3,4,5 and 6). The analytical and modelling approaches developed in this project are inherited from the detailed theoretical development and detailed analysis of the planets of our Solar System (Projects 2 and 4). We also directly benefit from the development of future ground-based instrumentation like ESPRESSO, or future observing facility (PCS, METIS, HiRes for the E-ELT), and in return will develop the needed tools for the efficient use of future giant telescopes and space missions. The approach developed in this project will be especially important and fruitful for the most difficult low-mass planets, and the habitable ones among them.

- Scientific collaboration within PlanetS

List of collaborations within PlanetS

- Collaboration within Projects 3, 5, and 7 for a study with Chinese colleagues on a possible space mission for exoplanet atmosphere characterisation through multi-band photometry.

- Collaboration with Project 5 on the ‘comparison of the properties of populations of synthetic planets with actual observations’: PhD in co-supervision, 2 years at UGE then 2 years at UBE.

- Collaboration with Project 1 on ‘planet imaging’ building on our common participation to the SPHERE consortium (improvement of the image treatment, statistical analysis of the results).

- Collaboration with Project 6 on the long-term stability of planetary systems: not started yet. We need first to develop the analytical approach to be compared to the numerical integration of planetary systems.

- Next steps

We describe here mainly short-term [also sometimes mid-term] plans for the various subprojects.

5.1 Optimal determination of planetary physical and orbital parameters

An important part of the activities will focus on the development of the first generation of tools to be implemented in DACE for the analysis of basic observations of stars hosting planets. Among them: combined light-curve + radial-velocities analysis, and the development of an astrometric package (in prevision for Gaia). This will be in a Bayesian statistical framework. Dr. Rodrigo Diaz, Dr. Damien Ségransan, and Dr. Danuta Sosnowska are the key persons for these activities.

As stated earlier in the report, Thibaut Roger (PhD) will reassess the expected PLATO planet yield, and the inferred telescope time required for the ground-based follow-up. He will in particular rethink the whole chain of criteria, starting from real PLATO fields (instead of galactic models), taking into account the statistics of small-size planet occurrence obtained from Kepler (better than the preliminary RV results used before), and implementing more realistic detection and characterisation criteria. This should take approximately one year.

5.2 Constraints from dynamical modelling of planetary systems

In the short term, Dr. Jean-Baptiste Delisle will continue with work on dissipation in protoplanetary discs and stability criteria for multi-planet systems. In practice he will be performing numerical simulations of resonant planets-disc interactions to test the derived analytical criteria, and be looking for similar criteria for stellar tide and disc dissipation affecting resonant planets.

We plan to set up in DACE the analytical framework developed by Dr. Rosemary Mardling for the analysis of TTVs and apply it to the unsolved candidates from the Kepler mission.

5.3 Constraining the structure of small mass planets

Dr. Daniel Bayliss will take part to the next NGTS commissioning in Chile in March 2015. He will continue to participate to improving the facility, examining the NGTS images. He will also start to organize (with Dr. Rodrigo Diaz and Prof. Stéphane Udry) the scheme for the follow-up of future NGTS candidates with the CORALIE and HARPS spectrographs. He will be at the same time continuing interesting projects started before coming to Geneva. Among them one is potentially very promising for NGTS and later PLATO: the use of several telescopes on the same targets in order to estimate and mitigate systematics in the observations (red noise).

A PhD position from the CHEOPS Platform has been devoted to a project between sub-project 7.3 and the CHEOPS mission. The idea is to develop a photometric reduction pipeline to detect transit candidates of the K2 mission (2-reaction wheel phase of Kepler/NASA), to be confirmed with Coralie on the Swiss telescope in Chile, in order i) to discover small-mass planets transiting bright stars in the K2 fields (sub-project 7.3), and then ii) provide exceptional targets for the CHEOPS mission. The PhD student will be under the co-responsibility of Dr. Christophe Lovis (CHEOPS science team) and Prof. Stéphane Udry. He will also work daily with Dr. Daniel Bayliss (7.3) who will thus have the opportunity to improve his experience with supervising students. The PhD student is foreseen to start in June 2015.

5.4 Probing the outer regions of planetary systems

In the coming months, Manuela Raimbault will focus on identifying binaries among the planets orbiting F, G, K, and M dwarfs, fit the data using Hipparcos data, get the physical parameters, and determine sources to be re-observed. She will also start a G, K, and M dwarfs catalogue of good candidates for Gaia data.

Anthony Cheetham will start work in April 2015. Discussion about planning for the SPHERE GTO observations and for the installation of the sparse aperture masking device on SPHERE are already taking place in the meantime

- List of publications resulting directly from PlanetS

Even if some publications clearly fall within the purview of Project 7 of the NCCR, the work or collaborations of PlanetS members started before the beginning of the project. They will thus all appear in the next section.

- List of publications with minor contributions from PlanetS

Refereed publications

- Kenworthy, M. A. et al., Mass and period limits on the ringed companion transiting the young star J1407, MNRAS 446, 411, 2015

- Bruno, G., Almenara, J.-M., Barros, S. C. C., Santerne, A., Diaz, R. F., et al., SOPHIE velocimetry of Kepler transit candidates. XIV. A joint photometric, spectroscopic, and dynamical analysis of the Kepler-117 system, A&A 573, AA124, 2015

- Zurlo, A. et al., Performance of the VLT Planet Finder SPHERE. I. Photometry and astrometry precision with IRDIS and IFS in laboratory, A&A 572, AA85, 2014

- Lanotte, A. A. et al., A global analysis of Spitzer and new HARPS data confirms the loneliness and metal-richness of GJ 436 b, A&A 572, AA73, 2014

- Neveu-VanMalle, M., Queloz, D., Anderson, D. R., Charbonnel, C., Collier Cameron, A., et al., WASP-94 A and B planets: hot-Jupiter cousins in a twin-star system, A&A 572, AA49, 2014

- Bonomo, A. S., Sozzetti, A., Lovis, C., Malavolta, L., Rice, K., et al., Characterisation of the planetary system Kepler-101 with HARPS-N. A hot super-Neptune with an Earth-sized low-mass companion, A&A 572, AA2, 2014

- Armstrong, D. J. et al., On the abundance of circumbinary planets, MNRAS 444, 1873, 2014

- Smith, A. M. S. et al., WASP-104b and WASP-106b: two transiting hot Jupiters in 1.75-day and 9.3-day orbits, A&A 570, AA64, 2014

- López-Morales, M. et al., Rossiter-McLaughlin Observations of 55 Cnc e, ApJ 792, LL31, 2014

- Neves, V. et al., Metallicity of M dwarfs. IV. A high-precision [Fe/H] and Teff technique from high-resolution optical spectra for M dwarfs, A&A 568, AA121, 2014

- Lendl, M. et al., WASP-117b: a 10-day-period Saturn in an eccentric and misaligned orbit, A&A 568, AA81, 2014

- Alonso, R. et al., Transiting exoplanets from the CoRoT space mission. XXVI. CoRoT-24: a transiting multiplanet system, A&A 567, AA112, 2014

- Vanderburg, A. et al., Characterizing K2 Planet Discoveries: A super-Earth transiting the bright K-dwarf HIP 116454, ApJ 800, 59, 2015

- Anderson, D. R., et al., The Well-aligned Orbit of Wasp-84b: Evidence for Disc Migration of a Hot Jupiter, ApJ 800, LL9, 2015

Non-refereed publications

- Köhler, R., Launhardt, R., Quirrenbach, A., Henning, T., & Queloz, D., Software for Astrometry with PRIMA at the VLTI, ASPC 487, 321, 2014

- Zurlo, A. et al., Methods for the detection and the characterisation of low mass companions using the IFS of SPHERE, SPIE 9147, 914770, 2014

- Zerbi, F. M., Bouchy, F., Fynbo, J., Maiolino, R., Piskunov, N., et al., HIRES: the high resolution spectrograph for the E-ELT, SPIE 9147, 914723, 2014

- Ricker, G. R. et al., Transiting Exoplanet Survey Satellite (TESS), SPIE 9143, 914320, 2014

- Langlois, M. et al., Infrared differential imager and spectrograph for SPHERE: performance assessment for on-sky operation, SPIE 9147, 91479P, 2014

- Cosentino, R., Lovis, C., Pepe, F., Cameron, A. C., Latham, D. W., et al., HARPS-N @ TNG, two year harvesting data: performances and results, SPIE 9147, 91478C, 2014

- Langlois, M. et al., High contrast polarimetry in the infrared with SPHERE on the VLT, SPIE 9147, 91471R, 2014

- Claudi, R. et al., The SPHERE IFS at work, SPIE 9147, 91471L, 2014

- Artigau, E. et al., SPIRou: the near-infrared spectropolarimeter / high-precision velocimeter for the Canada-France-Hawaii telescope, SPIE 9147, 914715, 2014

Submitted publications in peer-review journals

- Dressing, C. D., Charbonneau, D., Dumusque, X., Gettel, S., Pepe, F., et al., The Mass of Kepler-93b and The Composition of Terrestrial Planets, arXiv:1412.8687, 2014

- Brown, D. J. A., Anderson, D. R., Armstrong, D. J., Bouchy, F., Collier Cameron, A., et al., Discovery of WASP-85Ab: a hot Jupiter in a visual binary system, arXiv:1412.7761, 2014

- Moutou, C., Lo Curto, G., Mayor, M., Bouchy, F., Benz, W., et al., The HARPS search for southern extra-solar planets XXXVI: Five new long-period giant planets and a system update, arXiv:1412.6591, 2014

- Astudillo-Defru, N., Bonfils, X., Delfosse, X., Ségransan, D., Forveille, T., et al., The HARPS search for southern extra-solar planets XXXV. Planetary systems and stellar activity of the M dwarfs GJ 3293, GJ 3341, and GJ 3543, arXiv:1411.7048, 2014

- Hellier, C. et al., Three WASP-South transiting exoplanets: WASP-74b, WASP-83b & WASP-89b, arXiv:1410.6358, 2014

- Anderson, D. R. et al., Six newly-discovered hot Jupiters transiting F/G stars: WASP-87b, WASP-108b, WASP-109b, WASP-110b, WASP-111b & WASP-112b, arXiv:1410.3449, 2014

- Anderson, D. R. et al., The well-aligned orbit of WASP-84b: evidence for disc migration, arXiv:1409.6335, 2014

- Sahlmann, J., Lazorenko, P. F., Ségransan, D., Martin, E. L., Mayor, M., et al., Astrometric planet search around M8-L2 dwarfs from the ground and with Gaia, arXiv:1407.0590, 2014

- Woillez, J. et al., Improving the astrometric performance of VLTI-PRIMA, arXiv:1407.0470, 2014

Conferences:

- CHEOPS science meeting, Venice (Italy), 03.06.2014 – 04.06.2014 (S. Udry, participation)

- Alibert ISSI Team on planet formation (statistical constraints from observations, dynamics of planetary systems), Bern, 23.06.2014 – 27.06.2014 (S. Udry, speaker)

- “The external regions of planetary systems" as part of EWASS 2014 in Geneva, 03.07.2014 – 04.07.2014 (D. Ségransan, co-chair of the SOC).

- Kick-off meeting of the PLATO activities, Berlin (Germany), 16.07.2014 – 17.07.2014 (S. Udry, speaker)

- ISSI-BJ Forum in Beijing on "microarcsec astrometry from space", Beijing (China), 22.08.2014 – 23.08.2014 (S. Udry, speaker)

- ISSI/ISSI-BJ workshop on "The disk and the relation to the formation of planets and their protoatmospheres", Beijing (China), 25.08.2014 – 29.08.2014 (S. Udry, convener)

- Chinese Swiss Space Science Workshop, Lenk, 10.09.2014 – 11.09.2014 (S. Udry, participation)

- “Towards other Earths II”, Porto (Portugal), 15.09.2014 – 19.09.2014 (S. Udry, invited talk)

- Reimar Luest Lecture, Göttingen (Germany), Max Planck for biophysics and chemistry, 30.09.2014 (S. Udry, invited lecturer)

- NGTS meeting, Berlin (Germany), 03.11.2014 – 04.11.2014 (S. Udry, F. Bouchy, D. Bayliss)

- 4th Australian Exoplanet Workshop, Toowoomba (Australia), 25-26.11.2014 (D. Bayliss, speaker)

- ANU Mt Stromlo Colloquium, Canberra (Australia), 05.12.2014 (D. Bayliss, speaker)

- “ESO in the 2020s”, Garching (Germany), 19.01.2015 – 22.01.2015 (S. Udry, speaker)

Media:

- Press release and large media coverage, on 03.06.2014, of the characterisation of the "Mammoth" Earth Kepler-10c

- ESO Press release on the NGTS first light, 14.01.2015

- ESO Press Release in preparation (02.2015): SPHERE at the level of expectations, opening to the community

### 2.2.2 Research platforms

PlanetS contains five platforms. Fig. 2.6 shows the current platform structure of the NCCR. However, only two of these platforms are research units: DACE and CHEOPS.

Fig. 2.6: The platform structure of the NCCR. Of the five platforms only two are actual research units. These are the DACE and the CHEOPS Platforms (the two on the right).

In the following, we present these two platforms in some details. We report on their objectives and activities during the time since the establishment of PlanetS and present some of the first accomplishments.

The corresponding presentations of the other three platforms can be found in Sections 3 to 6.

### Platform DACE:  Data and Analysis Center for Exoplanets

## Project leader:  Stéphane Udry & Ben Moore – Universities of Geneva and Zürich

Project scientist:  Damien Ségransan – University of Geneva

### 1. Abstract

The Data Analysis Center for Exoplanets (DACE) is a facility based at the University of Geneva (CH) dedicated to extrasolar planet data visualisation, exchange and analysis. DACE is a platform of the Swiss National Centre of Competence in Research (NCCR) PlanetS, federating the Swiss expertise in Planetary Science research. DACE is at the core of PlanetS and is expected to trigger exchanges and collaborations between NCCR projects, and between the NCCR and the external community.

Fig. 1: Radial-velocity measurement of a star hosting a system composed of two giant planets (top figure). The Keplerian model adjusted to the data is represented as a black curve, while the periodogram of the residuals is displayed on the middle figure. The bottom figure represents the amplitude of the signal in m/s within the residuals.

Visualisation and data exchange tools are being developed within the platform to facilitate the comparison of theoretical and observational data while sophisticated data analysis tools are developed by the various projects. DACE is already accessible at the following address: http://dace.unige.ch. Additional functionalities are implemented regularly (typically every quarter).

Fig. 2: 3-Body integration of a planetary system over a time span of 2000 days. Small-amplitude oscillations of the orbital elements are clearly seen in the simulation. The N-body evolution is followed with the GENGA code developed at the University of Zurich.

### 2. Results and achievements since the last report

DACE started as a small-scale initiative at the University of Geneva, with a limited database of radial-velocity data and a simple web interface to query and visualise these data. Since the acceptance of PlanetS, in June 2014, we have been expanding the functionalities of DACE as well as setting-up the DACE team. Part of the “hard” work was in hiring computer scientists, with the last position filled in December 2014. We also defined, in each PlanetS project, a contact person for DACE as well as in external projects relevant to PlanetS such as CHEOPS, the ESA S1 space mission. As of today, the DACE Team is composed of 16 people (among them 2.5 computer scientists and 10 PlanetS astronomers).

Hired personnel:

- Nicolas Buchschacher, responsible for the design and development of the database, was hired from June 1st 2014 (100%, SNF-PlanetS).

- Dr. Danuta Sosnowska, paid through DACE from November 1st 2014 on, is working on the implementation of GENGA onto the DACE Platform (50%, SNF-PlanetS). This position is temporary in DACE. It was motivated by the need for a dedicated expertise to implement GENGA, and by the difficulty to rapidly find a computer scientist.

- Fabien Alesina, responsible for the web design, has started on December 15th 2014 (100%, SNF-PlanetS).

PlanetS’ project contact persons:

- Project 1, Discs and Planets. Dr. Sascha Quanz, ETHZ.

- Project 3, Planetary Atmospheres. Dr. Christophe Lovis, UGE.

- Project 4, Solar System remote sensing. Prof. Nicolas Thomas, UBE.

- Project 5, Planet formation and evolution. Prof. Christoph Mordasini, UBE.

- Project 6, Numerical laboratories. Dr. Joachim Stadel, UZH.

- Project 7, Planet properties and system architectures. Dr. Rodrigo Diaz, UGE.

- Communication and Outreach Platform: Dr. Pierre Bratschi, UGE.

External project contact persons:

- CHEOPS Science Team: Dr. David Ehrenreich, University of Geneva.

- Star formation & Evolution: Dr. Sylvia Ekström, University of Geneva.

- Extrasolar planets Encyclopaedia, Dr. Françoise Roques, Observatoire de Paris.

Results & Achievements:

As a PlanetS platform, DACE is dedicated to planet-related data access, exchange and visualisation.

On the purely technical point of view, the team has been working on several aspects:

- Restructuring of the database in order to add flexibility and modularity to the data storage and access, as well as to allow for the needs of the various PlanetS projects.

- Transition to a new javascript visualisation library (flot.js) since the previously used Google library (Google Chart) was not reliable. Performances are impressive but some fine-tuning is still required.

- Development of the first web-based 3D animations using webGl (Three.js)

- The code went through a major upgrade by using a Laravel as a new framework.

- The technical team is currently working on a new flexible web design that would allow the user to configure his or her personal user interface, with customised access to data and analysis tools. This is done using the bootsrap library.

On the project point of view, the team has mainly been working on the implementation of data and tools for Projects 6 and 7.

- Consolidation of the structure of the database set-up for radial-velocity, photometric and imaging data (link with Project 7).

- The new workstation dedicated to the data reduction and the archiving of radial-velocity data are online and the automatic daily update of the database with the velocities is almost finished (link with Project 7).

- Improvement of basic Keplerian modelling tools for radial-velocity observations, adapted to multi-planet systems (link with Project 7).

- Installation of GENGA (link with Project 6 & 7) on DACE, and the first set of functionalities with a web-based user interface, including 3D animations.

- Dr. Maxime Marmier (Project 7, self-group) worked on the census for the content of the historical CORAVEL database and cross-matching of the targets with the CDS catalogue in order to examine different strategies to import the CORAVEL database into DACE.

On the management point of view:

- A first draft of the DACE management plan has been written.

- The DACE Kick-off meeting was held in Geneva on January 16th 2015, with the participation from most of the team members and of the PlanetS Science Officer. The meeting triggered synergies between several projects - primarily between Projects 5, 6, 7, CHEOPS and the Communication and Outreach Platform. Each project contact person was assigned the task to write several “use cases” for their own project followed by user requirements.

- Project 5, 6 and 7 being significantly advanced, we are already starting the implementation of several of their functionalities.

- We also held a first meeting between DACE and representatives of the CHEOPS Science Team (January 19th 2015 with Dr. Michael Gillon and Dr. Sergio Sousa) in order to define synergies between DACE and the Cheops mission. It has been agreed that DACE will provide a set of tools to analyse Cheops light curves.

- The partnership between DACE and the Extrasolar Planets Encyclopaedia is underway. We had a first discussion in Paris in June 2014 and a draft of a Memorandum of Understanding has been produced.

### 3. Next steps

In the upcoming year:

- We plan to implement a new web interface to the DACE Platform using flexible web design.

- In addition, a first set of functionalities related to Projects 5, 6, 7, and to the Communication and Outreach Platform will be implemented.

- We expect to receive “use cases” for Projects 1, 3 and 4.

- In parallel, the DACE database will be filled with Hipparcos astrometry data and the first astrometry data analysis tools are expected to be delivered by Project 7.

### 4. List of publications resulting directly from PlanetS

- Buchschacher, N., Ségransan, D., Udry, S. & Díaz, R., Data and Analysis Center for Exoplanets, to appear in ASP Conference Series.

Conferences:

- Nicolas Buchschacher, ADASS XXIV, Calgary (Canada), 05.10.2014 - 09.10.2014

### Platform CHEOPS

## Platform leader: Willy Benz

### 1. Purpose of the Platform

The CHaracterising ExoPlanets Satellite (CHEOPS) is a joint mission between ESA and Switzerland to be launched in 2017. ESA’s Science Programme has selected CHEOPS in 2012 as the first small mission (S-mission) in its Programme. In order to meet the S-mission requirements CHEOPS is exploring innovative approaches with the help of ESA and the Swiss State Secretariat for Education, Research and Innovation (SERI). For details about the mission’s science goals and technical implementation see the CHEOPS website at http://cheops.unibe.ch.

The building of space experiments (including CHEOPS) is funded in Switzerland through an ESA programme called Prodex. While this programme allows for the building of experiments or instruments, it does not allow of the funding of the scientific exploitation of the data obtained by these experiments or instruments. In general, this has to be done through individual research grants from SNF.

Given the Swiss investment in the mission and the fact that CHEOPS is an international project, the scientific return to Switzerland must be secured. The purpose of the CHEOPS Platform within our NCCR is to secure this return by providing a coherent organisation and the funding for a high-visibility science exploitation of the mission.

### 2. Ways of working of the Platform

In order to reach its goals, the CHEOPS platform will

- Create a pool of young scientists working on CHEOPS science who are not attributed to a specific institute (Hubble Fellow model) but encouraged to work across institutional boundaries. This pool will consist of:

  - PhD students incorporated in the PlanetS doctoral network and encouraged to work in different projects. The budget allows for 2-3 PhD students.

  - Postdocs (3+1 year) with a small (10 kCHF) research budget. These positions will be advertised and competitively selected. The budget allows for 3-4 postdocs.

- Coordinate the Swiss scientific activities related to the CHEOPS data.

- Seek the best possible expertise available in the country.

The responsibility of this platform is essentially to act as the administrator of the funding allocated to this platform. The Executive Board is carrying out the selection of the Fellows following an open call.

### 3. Action taken since the last report

The Executive Board decided to start the implementation of the pool of fellows during Year 2 and to start with the PhD students. This was done to ensure that all scientists hired by the platform will still be working within PlanetS after the launch of CHEOPS.

- At its October 3rd 2014 meeting, the Executive Board of PlanetS decided to issue a call for thesis subjects for the first two CHEOPS graduate students to start working in June 1st 2015. The due date for the proposals was set in order to allow the discussion of the proposals at the next Board meeting on December 12th 2014.

- At its December 12th 2014 meeting, the Executive Board of PlanetS discussed the four PhD proposals received in response to the call. These proposals were sent by email in preparation of the meeting. After some discussion, a consensus emerged for the following two proposal:

  - “Best possible exploitation of the K2 and TESS results for the optimisation of the CHEOPS follow-up” proposed by Dr. Christophe Lovis and Prof. Stéphane Udry, UGE.

  - “Planet formation models as additional inputs for deriving internal structures of planets from the knowledge of mass and radius” proposed by Prof. Yann Alibert and Prof. Willy Benz, UBE

### 4. Actions planned

The plan for the next funding period is to issue a call for 2-3 CHEOPS Fellows (postdocs). This call will be issued in the fall of 2015 with the goal for the Fellows to start in the summer of 2016.

### 5. Collaborations within PlanetS

By construction, the CHEOPS Platform provides a pool of scientists that will work on a common scientific subject (CHEOPS Science) and be distributed throughout the projects. This will create synergy between the projects.

# Knowledge and Technology Transfer

### As we presented in Sect. 2.1, the Knowledge and Technology Transfer activities of our NCCR are carried out by three separate platforms, namely the Technology Platform, the Academic Coordination Platform, and the Communication and Outreach Platform. We present in this section the activities of the Technology Platform focusing exclusively on the transfer of knowledge and technology between the NCCR, universities of applied sciences and the private sectors. The report on the other components of knowledge transfer can be found in the respective report of the other two platforms below.

### This section presents the activities of the Platform, our strategy for the first phase being described in Annexe 1.

### 3.1 Results and achievements since the last report

Since the beginning of the NCCR, a series of actions have been undertaken by the Technology Platform:

- We have hired an Administrative Assistant (10%), Mrs Chantal Tacoy, to provide the administrative support of the Platform’s activities.

- On August 27th 2014, a meeting was held at the University of Bern with external experts to discuss the goals and organisation of the Technology Platform and to learn about the experience from industry and other NCCRs. Experts from industry, technical universities, space office and the NCCR MUST attended the meeting.

- A ‘Management Concept’ document was prepared after the meeting with these experts in August. The document has been circulated among the PlanetS Executive Board Members. It has been accepted by the Executive Board during its December meeting and was transformed into the Strategic Paper for the Technology Platform presented in Annexe 1 of this report.

- Possible extensions of the Technology Platform activities were discussed, e.g. collaboration with an equivalent structure in Grenoble (Labex-Focus), with Geneva Sciences Jobs Lab 2015+ or the Laboratoire de Technologies Avancées (initiated by MaNeP, Geneva).

- The official release of the Technology Transfer Strategic paper has been issued on January 31st 2015, and published on the website. It contains the planned activities and the path to an efficient implementation of the Technology Platform. This paper is reproduced in Appendix 1.

- A dedicated web page section was setup within the NCCR website. In addition to describing the Technology Platform and providing useful information, it is intended to become the access portal to a collaborative section offering services to PlanetS projects and external collaborators.

### 3.2 Actions planned

An external expert was mandated in February 2015, to organise the first activities of the Technology Platform. Indeed, discussions with other NCCR have shown that the activities of the Platform are better organised by a professional with good connections to the Swiss technological landscape. The Statement of Work is:

- Make a list of all the Swiss companies related to space and ground-based astronomy through the market of high-end components or R&D in mechanics, electronics, optics, software, or a combination of them.

- Contact companies in order to

- Identify a contact person within the company

- Identify 'off-the-shelf' products

- Identify areas of interest and R&D in which a collaboration is suitable

- Listen for suggestions and complaints with respect to knowledge and technology transfer with Technical Universities, Research Institutes and other NCCR or organisations.

- Produce a report on the status of the Strategy for Knowledge and Technology Transfer (KTT) in the areas related to astronomy and issue recommendations to PlanetS and the Technology Platform to enable and improve the KTT.

- Propose a web-based solution to collect information of interest that could enhance the KTT (more the concept and a list of information items than the implementation of the tool, which would be subcontracted) .

- Propose two topics for Swiss-wide workshops, e.g. in collaboration with MUST, including a preliminary list of participants (the workshop would be organised on a separate mandate).

- Once per year, an expert shall comb through all the projects for technologies and concepts developed within PlanetS with respect to potential transfer to industry or for commercialisation.

In addition, we will issue a call for proposal inside PlanetS in order to provide seed-funding for innovative technology projects. Initial contacts with different members of the NCCR have already identified three possible initiatives:

- Development of a Laser Frequency Comb (Project 3).

- Support of the start-up Ionight (UBE). This support would come in addition to a successful CTI proposal recently awarded to Ionight and the University of Berne.

- Support for patenting a new ultra-stable calibration lamp, presently used for calibration of the CHEOPS detector (UGE).

During the recent General Assembly, we have identified additional possible areas of knowledge transfer with industry, which we will explore in more detail:

- Transfer of extremely powerful GPU-based technology specifically developed for the computation of multi-body systems to commercial applications.

- Collaboration in the area of adaptive optics system between astronomy and other areas of research, e.g. medicine and ophthalmology.

# Education and training

As presented in Sect. 2.1, the education and training activities of the NCCR are carried out under the responsibility of two platforms: the Academic Coordination Platform and the Communication and Outreach Platform. In this section we report on the activities carried out by the Academic Coordination Platform which is coordinated by Prof. Michael Meyer (lead) and Prof. Maria Schönbächler (co-lead) and focused on education and training within the academic world. The report on activities in education and training of school children and the general public can be found in the report of the Communication and Outreach Platform below. We provide here a report on the activities of the Platform since the beginning of the NCCR. The strategy of the Platform is presented in Annexe 2 of this report.

4.1 Formation of the Academic Platform Team

- On October 1st 2015, the Academic Platform Coordinator, Dr. Audra Baleisis, was hired. Her duties for the Academic Platform include the support of: (1) the Lead (Prof. Michael Meyer), with the interdisciplinary courses and schools (see Education Strategy Paper), and (2) the Deputy (Prof. Maria Schönbächler) with Professional Development and Equal Opportunities activities and resources. The Coordinator is also supported by a local administrator (10 %).

- The Academic Platform team is further supported by, and receives input from, Dr. Sascha Quanz (ETHZ), Prof. Yann Alibert (UBE), Prof. Stephane Udry (UGE), and Prof. Lucio Mayer (UZH).

4.2 Past Events and Activities

- Survey of professional development needs: We have completed our first survey of young researchers in PlanetS, with respect to the kind of professional development assistance sought by PhD students and postdocs, which indicated a desire for:

  - training in science communication (asking/answering questions, professional correspondence, etc.),

  - training in scientific writing (publications and proposals),

  - improving their presentation skills,

  - the chance to network with peers across the NCCR PlanetS.

- Doctoral Network: We have begun the planning of our advanced doctoral programme in planetary sciences, with:

  - an inventory of existing planetary science programs (University of Chicago, University of Manchester, University College London, and the University of Arizona) and their curricula,

  - a survey of currently planned advanced courses across the five PlanetS institutions,

  - a discussion among NCCR professors of how to build a strong core curriculum of PlanetS courses across physics, astronomy, earth science and computer science topics, as well as integrating professional development activities requested by the PhD students and postdocs (e.g. proposal writing and verbal presentations) and flexible teaching structures that support remote learning (e.g. journal clubs, project-based learning, flipped classrooms). The results show that students often come to the study of planetary sciences with subject specific expertise, but are lacking in a broader base of knowledge, and that the professors are willing to try a range of instruction methods to achieve their learning goals.

4.3 Ongoing and Planned Activities

- We are supporting the 45th Saas-Fee Lecture on “Circumstellar Disks and Planet Formation” for PhD students, post-docs, and senior scientists of the NCCR.  The one week advanced course will be given by three international experts in March 15th-20th, 2015 in Les Diablerets, Switzerland.  Approximately 25 members of the NCCR will participate in the school.  The Academic Coordinator is working with the lecturers to enhance the lectures using best practice from education research.

- Pilot of remote participation in graduate courses - Spring 2015: The Exoplanets course, of Prof. Michael Meyer, at ETHZ will serve as a test of how to best enable successful and engaging remote participation from students across the NCCR home institutions. It is comprised of 13 Zurich-based students and 2 Bern-based students.

  - Input for the design of the course has been gathered from within the NCCR (Dr. Timm Riesen, UBE), ETHZ specialists in video streaming, and education specialists (who have experience in curriculum design for remote-participation in courses).

  - A number of different remote participation technologies (software such as online platforms and hardware such as high-quality microphones), will be tested during the course. Special attention will be paid to helping remote students feel part of the course as well as organising monthly face-to-face meetings.

  - Finally, instructional techniques will be adjusted when possible to enhance local and remote participants’ engagement with course materials, as educational research has shown that active participation by students enhances learning.

- Visiting scholars’ programme – the programme has been announced at the first General Assembly in January 2015, to solicit suggestions for whom to invite. Part of this announcement was a reminder to think especially of strong female candidates. A total of six names have been collected (three female) and we hope to have at least one visitor before fall 2015.

- The first Thinkshop will be held in summer 2015 on a topic yet to be chosen.

- Fall 2015 professional development workshop - (See Equal Opportunity Progress Report).

# Equal opportunities

The equal opportunities activities of the NCCR are under the responsibility of the ‘Academic Coordination’ Platform coordinated by Prof. Michael Meyer (lead) and Prof. Maria Schönbächler (co-lead). We provide here a report on the equal opportunities activities of the Platform since the beginning of the NCCR. The strategy of the Platform is presented in Annexe 2 of this report.

5.1 Formation of the Equal Opportunity Team

- On October 1st 2015, the Academic Platform Coordinator, Dr. Audra Baleisis, was hired. Her duties for the Academic Platform include the support of: (1) the Lead (Prof. Michael Meyer), with the interdisciplinary courses and schools (see Education Strategy Paper, Annexe 2 of this report), and (2) the Deputy (Prof. Maria Schönbächler) with Professional Development and Equal Opportunities activities and resources.

- The Equal Opportunity team is comprised of: (1) Prof. Maria Schönbächler as the Executive Board delegate, and (2) Dr. Audra Baleisis as the gender officer. They will be further supported and receive input from Prof. Michael Meyer, Dr. Sascha Quanz (ETH), Prof. Yann Alibert (UBE), Prof. Stephane Udry (UGE), and Prof. Lucio Mayer (UZH).

- Contacts have been made at the Equal Opportunity offices of ETH (Dr. Monika Keller), UZH (Tanya Neve-Seyfarth), UGE (Brigitte Mantilleri) and UBE (Lilian Carpenter).

5.2 Past Events and Activities

- Gender imbalance within the NCCR PlanetS: A count of the women and men at all levels of the collaboration highlighted a relatively low proportion of women PhD students, postdocs and senior researchers. This was reported to the Executive Board in December 2014 and it was decided that further investigation was necessary to understand the possible causes of this and to determine future action to improve the situation.

- Networking breakfast at the General Assembly, Anzère, January 2015: The first official event related to the Advancement of Women took place during this meeting, as an informal breakfast for all women researchers attending the meeting. Fourteen women attended, including a few female members of associated research groups that are not directly supported through the NCCR.  The goal of this event was (i) to provide women scientists with the opportunity to meet colleagues from across the various institutions (networking) and (ii) to raise problems related to equity that they would like to be addressed within NCCR and (iii) to seek information as to why woman are still a minority in science.  A first professional development tip (how to introduce oneself at a conference) was provided as a take-home sheet. The input from the women in attendance is summarised in the following and the main issues raised at this first event were: (i) the topic of being able to have a family while also having a job in academia; (ii) the availability of part time jobs, (iii) the need for mobility for a successful career and its impact on family planning, (iv) the need for more data about the reasons why women leave academia, (v) the challenge of how to best address equal opportunity because of its underlying complexity and (vi) a general discussion of whether women-only events were indeed necessary since diversity concerns both men and women, and hence, should include both. In addition, the strategy for the Advancement of Women was presented on the first day of the meeting.  Both after this presentation, and during the networking breakfast, attendees commented that men should also be part of discussions about gender equity.

- We are encouraged by the fact that a number of individuals voluntarily contacted Dr. Audra Baleisis after the General Assembly with requests for help and with self-initiated data collection related to women’s participation in the meeting. This is a first small indication that we have been successful at communicating our openness to hear input from the women (and men) of the NCCR PlanetS.

- Childcare was made available to attendees who wished to bring their children to the meeting, however none of the children came to Anzère in the end, due to illnesses. In addition, last minute remote streaming of the conference talks was enabled by the Communication team, which made partial participation a possibility for those who could not attend. Again, it was not used. However the added flexibility this would give to parents or others who could not be there in person was recognised and will be announced and organised ahead of time for the next General Assembly.

5.3 Ongoing and Planned Activities

- Currently underway is the collection of hiring statistics, specifically, of the gender distribution of the applicant pool and of the individuals to whom job offers were made. Interviews with Project Leaders will be conducted to add more detailed information on the circumstances influencing the hiring process (on the part of the employers and the employees).

- An e-mail distribution list of all interested individuals (both male and female) within the NCCR is being assembled, for distribution of gender- and work-life balance related events happening at the various NCCR PlanetS institutions. NCCR members will also be asked to submit events they think might be of interest to this list, to enable better coverage of all that is available (but often scattered across numerous websites).

- Links for the NCCR website are being gathered, to support services at each of the PlanetS institutions.

- An article summarising the Women’s Networking Breakfast at Anzère will be featured in the May 2015 edition of the newsletter.

- A presentation to the NCCR PlanetS Executive Board “Equality vs. Equity: What is the goal?” is planned for Spring 2015.

- An article is being prepared for the May 2015 newsletter about current research and scholarly writing on organisational diversity, equal opportunity, and women’s participation in academic science.

- Fall 2015 professional development workshop: A day-long event, mainly for junior researchers, will include: a chance to network with NCCR peers, topics related to science communication (as requested through a survey of PlanetS PhD students and postdocs), and a group activity and discussion of equality vs. equity.

# Communication

The communication and outreach of the NCCR is the responsibility of the Platform ‘Communication and Outreach’, led by Prof. Willy Benz. We provide here a report on the activities of the Platform since the beginning of the NCCR.

6.1 Formation of the communication team

Since the start of the NCCR PlanetS in June 2014 the following persons have been hired:

- Dr. Timm Riesen (UBE), Technical Officer, 50% since June 2014

- Dr. Pierre Bratschi (UGE), 100%, since September 2014

- Ulrich Stettler (UBE), 50% since October 2014

- Guido Schwarz (UBE), 50%, since December 2014

- Barbara Vonarburg (UBE), 50%, since February 2015

Dr. Sylviane Blum who is in charge of communication and outreach for the Centre for Space and Habitability (CSH) at the University of Bern is an associate of PlanetS. As of February 1st 2015, the team is complete. The members are professionals and are bringing together diverse skills and experience in the field of communication and outreach and therefore cover a broad range of expertise.

6.2 Communication and Outreach Concept

We prepared the concept for communication and outreach. In the strategy paper (see Annexe 4 of this report), we outline the strategy and the methodology to achieve our goals from which the most important are: Building a team spirit among all NCCR PlanetS members, informing the general public about the exciting progress in planetary research and generating a public entity “PlanetS” that will be recognised to facilitate the transition to a Swiss Institute of Planetary Sciences (SIPS) after the NCCR will terminate.

6.3 Past Events and Activities

- eNewsletter #1 published October 27th 2014

- Professional peer review of the website by KARGO Kommunikation GmbH

- 2 days COM-Kickoff-Meeting with Dr. Pierre Bratschi and the Geneva Team

- Article in the magazine of the Swiss Astronomy Society, Orion 1/15

- 1st General Assembly, January 28th – 30th 2015

- Website www.nccr-planets.ch, launched on January 28th.

- During the 1st General Assembly in Anzère on January 29th 2015, Nobel Prize laureate Prof. Brian Schmidt and Prof. Michel Mayor, both members of the NCCR Advisory Board, met 15 teenagers of the school of d’Ayent to answer questions.

http://www.rhonefm.ch/fr/temps-d-arret/des-eleves-du-co-d-ayent-rencontrent-un-prix-nobel-de-physique-a-anzere-241015

http://www.lenouvelliste.ch/fr/valais/sion/un-prix-nobel-a-anzere-497-1409158

https://www.facebook.com/photo.php?fbid=926185894071830

6.4 Media response

Press releases sent through the channel of the University of Geneva with impacts in the local press:

- WASP 94 (5.10.14)

http://espace-temps.blogs.nouvelobs.com/archive/2014/10/01/la-famille-des-exoplanetes-s-agrandit-avec-deux-cousines-gea-543423.html

- The vacuum tank for ESPRESSO (17.12.14)

http://www.24heures.ch/savoirs/sciences/La-chasse-aux-nouvelles-exoplanetes-est-relancee/story/25694429

http://www.letemps.ch/Page/Uuid/5356b72a-85e0-11e4-9cd5-59e213f8caa2/La_chasse_aux_exo-Terres_est_relanc%C3%A9e

http://www.ledauphine.com/sciences/2014/12/17/les-astronomes-genevois-se-lancent-a-la-recherche-de-planetes-habitables

http://www.arcinfo.ch/fr/suisse/geneve-a-la-pointe-de-la-chasse-aux-terres-extrasolaires-566-1389399

http://www.techno-science.net/?onglet=news&news=13490

https://www.youtube.com/watch?v=N1OPhK1aLfY

- The super earth discovered by Kepler K2 mission and confirmed by HARPS (20.12.14)

http://www.space.com/28046-nasa-kepler-exoplanet-k2-discovery.html

- First light of NGTS (14.1.15)

http://www.letemps.ch/Page/Uuid/2e317044-9c14-11e4-aa73-0eb920ec942b/Des_milliers_dexoplan%C3%A8tes_en_vue_gr%C3%A2ce_%C3%A0_de_nouveaux_t%C3%A9lescopes

6.5 Ongoing and Planned Activities

Internal communication

- eNewsletter #2 will be published end of February 2015, #3 end of May.

- Generation of website sections for internal use is in progress (3 separate sections for members, board members, associates).

- Work on a central communication plan specifying rules and responsibilities is in progress.

External communication and outreach

- Exhibition «Exoplanètes» at the “Muséum d’histoire naturelle de Genève”. This exhibition starts on March 21st 2015 and is substantially supported by the NCCR, with scientific advice, financial support, participation to a movie shown in the exhibition, conferences, and public animations for children.

- On April 20th 2015 the Geneva bus built to commemorate the entrance of Geneva into the Swiss confederation 200 years ago will arrive in Bern. The University of Geneva had been granted 20 m2 of exposition area in order to explain questions like: “What is an exoplanet?” and to present the PlanetS. There will be a public lecture by Prof. Michel Mayor.

- A metallic plaque with miniaturised versions of about 3000 drawings by children will be created and mounted on the CHEOPS satellite. This project is being realised in collaboration with the Centre for Space and Habitability (CSH) at the University of Bern. The drawings will be collected with the help of the many amateur astronomy clubs in Switzerland that belong to the Swiss Astronomy Society and other partners. The project will dramatically increase the awareness by the public with regard to Switzerland’s contributions to space sciences, research, and missions and its international collaborations and impact.

- Stellarium Gornergrat: The leading institution CSH, with the support of partners, is building a robotic observatory at the Gornergrat that offers schools the possibility to observe the sky as astronomers do. PlanetS is interested in becoming a customer and potential partner to this endeavour with the aim of contributing/devising an exoplanet activity that could be offered to the students at the Stellarium Gornergrat.

- Hands-on models: We will provide paper models and hands-on materials for children, juveniles, and adults.

- Micro Exhibitions: A first concept for a travelling exhibition that can be used in museums and shopping centres has been elaborated. We are now working on a detailed plan and look for potential exhibitors.

- Creation of a new show for the Planetarium of the Swiss Transportation Museum in Lucerne.

- Generation of website content for media and outreach is in progress.

- Work on the concept for an eNewsletter addressed to a wider audience interested in astronomy including science journalists, teachers, etc. has started.

- Media Relations: We maintain regular contact with journalists from different medias.

# Structural aspects

# 7.1 Structural measures at the University of Bern

The structural measures envisioned at the University of Bern leading house are defined in the annexe 3 of the contract. We follow the structure of this annexe in our discussion.

- New professorships

  - Tenure track assistant Professor “Physics and Planetary sciences”

Prof. Kevin Heng started his tenure track assistant professorship on January 1st 2013 and therefore just completed his second year. This position is funded by the Centre for Space and Habitability (CSH). As customary at the University of Bern, his progress towards tenure is followed closely and is reported yearly. It is already clear that Prof. Kevin Heng is scientifically very active and productive. He was able to obtain several significant external funding, including one from SNSF. He has also organised several very successful conferences and been very keen to participate in the teaching of advanced courses. His skills have not gone unnoticed and he is currently being courted by other institution. This might lead UBE to have to decide for an earlier promotion to tenure than after the usual four years.

  - Transformation of a Dozent I position into a professorship

No actions have been taken on this issue. The position of the University of Berne is to discuss the permanent positions during the second phase of the NCCR.

  - Succession within the NCCR: Replacement of Prof. Kathrin Altwegg

The position of Prof. Kathrin Altwegg will be advertised early fall 2015 with a probable start date set for mid-2016. The search will be for someone working in solar system physics with a focus on the analysis of data originating from space missions. The position will be advertised as a Dozent position with tenure and a possibility for promotion to associate professor after a few years. This would be the same position as held today by Prof. Altwegg.

  - Prof. Christoph Mordasini joined UBE on February 1st 2015 on a new 5-year SNF Starting Grant. His project entitled “Planets in time” also funds 2/3 of the salary of the PI, a postdoc and a graduate student. Since this group’s work is related to PlanetS activities, they will be closely associated to the NCCR.

- Education

  - Interdisciplinary training units for graduate students within the CSH

The Centre for Space and Habitability at UBE has started organising a yearly summer school for PhD students working at Swiss institutions. These schools take place during a full week and aim at teaching the students the basics in different topics of interest. The first school took place in the summer of 2013 and had Cosmochemistry as a central scientific theme. Three lecturers presented various aspects of the field, including basic chemistry, to 35 students. The school in summer 2015 will be on Cosmogeology.

  - National doctoral network

The setting-up of a national doctoral network offering a broad education and research opportunities is ongoing. This activity is in the remit of the Academic Platform (see report of the Platform for details).

- Infrastructure

  - Continued development of the Centre for Space and Habitability

The CSH has entered in its fourth year and last year of activity within the current funding contract. The CSH will be reviewed in 2015 and, if successful, the contract extended for another period of four years. The CSH is one of the Centres of Excellence established by the University of Bern. Besides excellence in research, these Centres have the mandate to foster interdisciplinary research within the University. The CSH finances four interdisciplinary PhD students and 9 interdisciplinary postdocs. Each scientist works within at least two different departments on projects defined jointly by professors of different departments. At present, the following departments/institutes are involved: Physics, Geology, Chemistry, Biology, Veterinary, Philosophy, Theology, and Education.

CSH is also very active in outreach activities. In particular, it runs the Stellarium-Gornergrat (http://stellarium-gornergrat.ch), which is a remote-controlled observatory for schools. This observatory is a joint project between UBE, UGE, the International Foundation High Altitude Research Stations Jungfraujoch and Gornergrat, and the Burgergemeinde Zermatt.

  - Dace Platform

The setting-up of the DACE exchange and collaboration platform is ongoing. This activity is in the remit of the DACE Platform (see report of the Platform for details).

  - CHEOPS Platform

The setting-up of the CHEOPS Platform to coordinate the scientific activities related to the CHEOPS mission and especially the exploitation of the data in the future is ongoing. This activity is in the remit of the CHEOPS Platform (see report of the Platform for details).

  - Software Engineering Group (SEG)

One of the key elements in regular successful participation in space missions is the ability to maintain and manage a highly skilled pool of engineers. While many of them are financed through projects, continuity and preservation of experience and know-how necessitates permanent positions. With the increased importance of software development for space instruments themselves or for the running of the diverse calibration facilities, the establishing of SEG at UBE was long overdue. This group (4 to 6 engineers depending upon projects) has now been established with the hiring by PlanetS of its head, Gaetano Borini who started his work on October 1st 2014.

  - Cosmochemistry group at UBE

Cosmochemistry at UBE is a topic of research at both the Institute of Geological Sciences  (Prof. Klaus Mezger, Project 2) and at the Institute of Physics (Prof. Ingo Leya, Project 2). PlanetS provides a natural scientific framework for these two laboratories. Over the years, PlanetS aims at establishing a single Cosmochemistry group at UBE even though the scientists will formally continue to be affiliated to different institutes. To start the integration, PlanetS has hired a technician (Hans-Erich Jenni) who will maintain and help running the mass spectrometers at both institutes. He will begin his work on April 1st 2015.

# 7.2 Structural measures at the University of Geneva

The structural measures envisioned at the University of Geneva, co-leading house, are defined in the annexe 3 of the contract. We follow the structure of this annexe in our discussion. We describe as well at the end the local management organisation set up to cope in an efficient way with the large volume of activities and the co-leading-house responsibilities.

- New professorships

  - Tenured Associate Professor “Modelling and observation of exoplanet atmospheres”

The position is foreseen for June 2016, at the beginning of the 3rd year of PlanetS. The support of the university is confirmed. No actions have been taken so far, more than very positive preliminary discussions with high-profile potential candidates. The call for the position will be issued during spring 2015.

- Additional structural positions

The three additional positions to be filled thanks to the support of the university to PlanetS are at the level of Maître d’Enseignement et de Recherche (MER, equivalent to lecturer) or senior engineer (same level of salary). They are spread in time over January 1st 2014 (in anticipation of the NCCR), the beginning of the NCCR (June 1st 2014) and the beginning of the 3rd year of the NCCR (June 1st 2016). They are tenure positions financed through a Convention of Objectives (COB) between the State and the University of Geneva in the form of a 4-year budget for priority activities of the university, the university then stabilising the positions at the end of the 4-year period. The first period of PlanetS (2014-2018) overlaps two COB exercises, the 2012-2015 one, and the 2016-2019 one. For PlanetS, it means that the first 2 positions have to be filled by the end of 2015 and the 3rd one by the end of 2019. However, as long as a promised position has not been filled, the corresponding budget is still available to PlanetS as “unused money” that in our current spending profile is actually used to provide additional funding for postdoc positions in complement to the 2-year positions financed through the SNF-PlanetS budget for Projects 3 and 7.

One of the structural positions was created in anticipation of the NCCR. We decided with the agreement of UGE to split this anticipated position (available from January 1st 2014), in two parts, 50% of a senior engineer and 50% of a MER to safely launch the related activities, the two part-time positions to be completed later through the remaining 2 positions available. The complementary 50% of position for the engineer has been furthermore ensured for 2 years as an additional support from the Science Faculty of UGE.

A graphical illustration of the filling profile for the additional structural positions is provided in the figure below. It reads as follows:

  - 50% Senior Engineer position in 2014, created in anticipation of the NCCR

Dr. François Wildi filled the 50% Senior Engineer position on January 1st 2014. This position is important to secure a strong long-term “in-house” high-level technical expertise, in order to ensure the active participation of our institute to the development of the next generation of astronomical instruments and space missions. F. Wildi is the perfect candidate for the position, in view of his experience and responsibilities in the SPHERE project (extreme adaptive optics system just commissioned on the VLT) and in the CHEOPS space mission (calibration of the focal plane detector and of the global payload).

  - 50% complement of Senior Engineer position for two years

In order to complete the position of Dr. François Wildi, the Faculty of Sciences of UGE is financing a 2-years 50% position from January 1st 2014 to December 31st 2015.

  - 50% Senior Engineer position in 2014

From June 1st 2014, we have a 50% senior engineer position available as guaranteed by the University of Geneva. The goal is that Dr. François Wildi will occupy this function when the Faculty of Sciences’ commitment ends, end of 2015. Very conveniently this date corresponds to the deadline for actually filling the position in the COB framework.

  - 50% MER (lecturer) position in 2014, created in anticipation of the NCCR

This position is not officially filled yet, but the hiring process is under way. Dr. Damien Ségransan, leader of sub-projects 7.1 and 7.4, as well as DACE project scientist, has been already promoted on self-group money to the MER level, in preparation for the available position. His candidacy was extremely well perceived by the UGE commission in charge of the nomination of MERs. The official call required by the university law for tenure positions will be issued next month, and the nomination on the stabilised position is foreseen for December 1st 2015. The unused money related to this position is used in the mean time for the employment of Dr. Maxime Marmier (sub-project 7.1) and Dr. Rosemary Mardling (sub-project 7.2) later on.

  - 50% MER (lecturer) position in 2014

This position completes the 50% MER position created in anticipation of the NCCR and is available from June 1st 2014. As mentioned above, the position will be filled by the end of 2015.

  - 1 MER (lecturer) position in 2016

No actions have been taken on this issue yet. We will issue the call for the position during spring 2015, in order to have the position filled by June 2016. The profile is now clearly defined in the area of the dynamical modelling of planetary systems. In case of difficulty of finding a suitable candidate, we still will have the possibility to postpone the actual hiring for the tenure position (till end of 2019) and use the corresponding budget to hire promising candidates on temporary positions.

Graphical representation of the structural tenure positions financed by the University of Geneva

- Education

  - National doctoral network

The setting-up of a national doctoral network offering a broad education and research opportunities is ongoing. This activity is in the remit of the Academic Platform (see report of the Platform for details).

- Infrastructure

  - New building on the site of Sauverny

With the full support of the State of Geneva, we are extending the infrastructure of the Department of Astronomy at UGE with a new building (wing) hosting a new integration hall and larger clean room, a renewed and enlarged mechanical workshop, as well as offices and meeting rooms to welcome new researchers, in particular from PlanetS and the CHEOPS project. Work started in October 2014 with the demolition of small buildings including the storage room, our old small clean room, and the test telescope dome. Subsequently, a large hole was excavated for the foundations of the new building. Beginning in 2015, the actual construction of the building started and the work is still advancing according to schedule. In 2016, the new integration hall should be available and by the end of that year the facility will be handed over to the users. Below are displayed some pictures showing the transformations of the site over the past few months.

  - Integration of PlanetS in the frame of the “Centre of Astronomical, Mathematical and Physical Sciences” at the University of Geneva

The new “Centre of Astronomical, Mathematical and Physical Sciences” is presently still being studied. The goal is that the new Centre will include larger facilities that will facilitate ambitious inter-disciplinary projects, and thus encourage research in the related topics and enhance visibility in these priority fields towards the scientific community and the public. The new building on the site of the Department of Astronomy is seen as a first step in this direction.

  - Dace Platform

The setting-up of the DACE exchange and collaboration platform is ongoing. This activity is in the remit of the DACE Platform (see report of the Platform for details).

  - CHEOPS Platform

The setting-up of the CHEOPS Platform to coordinate the scientific activities related to the CHEOPS mission and especially the exploitation of the data in the future is ongoing. This activity is in the remit of the CHEOPS Platform (see report of the Platform for details).

  - Establishment of the Technology Platform

The setting-up of the Technology Platform to integrate the R&D needs of the participating research groups and to offer a direct portal to industry partners is ongoing. We refer to the report of the platform for details.

- Geneva Management Office

A sizable fraction of the PlanetS activities are based in Geneva, the co-leading house, including in particular 2 out of 7 research projects (Projects 3 and 7) and 2 out of 5 platforms (DACE and Technology). Therefore, we have organised a local Geneva Management Office in order to be more efficient and assist the co-director, Prof. Stéphane Udry. The set-up of this Office is mostly funded through the Cash support of the University of Geneva. It covers the science and finance management needs, the administration, and the Geneva antenna of the Communication and Outreach platform (Dr. Pierre Bratschi, 100%). The Office is lead by Dr. Sophie Saesen playing locally the roles of Prof. Yann Alibert (Science Officer) and Dr. Carsten Knigge (Finance Administrator) at NCCR level (see Sect. 8). She helps the Geneva project and platform leaders with their 3-monthly and annual (science) reports. She manages the financial planning and controlling of the Geneva activities and monitors the advancement of the structural measures promised by the University of Geneva, in connection with the NCCR co-director.

For the administrative and financial tasks of the Geneva Office, Dr. Sophie Saesen gets the support of experienced key personnel, already employed by the Department of Astronomy before PlanetS, but who accepted to increase their work rate:

- Franca Costa-DeMeo, Administrative Assistant (secretariat, 40%, Cash UGE).

- Livia Schnyder, Administrative Assistant (human resources, 10%, Cash UGE).

- Myriam Burgener and Françoise Page, local Accountants (Self-group).

Besides the standard activities of the Geneva Office, we note the organisation of a Geneva PlanetS kick-off event that took place on October 30th and 31st 2014. The purpose was to provide a general introduction of the NCCR goals and organisation to the new comers and have them get to know each other better. Leaders of projects from other nodes of the NCCR participated as well, with the aim of emphasising possible bridges between these projects and the ones conducted in Geneva. In total, 39 participants (NCCR and associates) attended.

# Management

## 8.1 Overall PlanetS management

The management of the NCCR is organised in several units as illustrated in the figure below. The Executive Board, chaired by the Director, is the main decision and strategic planning body of the NCCR. It discusses all aspects of the projects, platforms, and the NCCR as a whole. Major decision items such as the level of funding of projects and platforms, the termination or start of activities, major budget re-allocations, etc. are presented to the Executive Board by a member of the Board and discussed. Decisions are taken by consensus. The Director and Co-Director are in charge of implementing these decisions.

The Programme Office is the central managerial coordination unit of the NCCR. It is headed by the Scientific Officer (Prof. Yann Alibert) whose primary task is to implement and monitor the scientific coordination between projects and platforms as decided by the Director and Co-Director. He reports to the Director and the Co-Director.

The Administrative Assistant (Mrs. Janine Jungo) is in charge of all daily secretarial tasks as well as with the organisation of special events such as the General Assembly or the Site Visit. A Technical Officer (Dr. Timm Riesen) is in charge of all technical needs (non-scientific) of the NCCR. He supervises the PlanetS Website, ensures proper video links between sites, advises on technical equipment, etc. With his prior experience of teacher, he also works with the communication and outreach team.

Organisation chart of the NCCR structure, focussing on the administrative aspects of PlanetS.

The financial administration of the NCCR is part of the NCCR Programme Office. The financial planning, reporting, controlling, and day-to-day administration is organised by the Finance Administrator (Dr. Carsten Knigge) with the help of an accountant (Mrs. Yesim Ege Vogel). In addition, UGE as co-leading house has established a similar local structure (see section 7.2). Finally, the NCCR being a project oriented structure; each project/platform leader has set-up a local administrative structure and designated a point of contact. The Financial Administrator is responsible for a proper organisation and appropriate execution of the monitoring of all financial activities in the NCCR.

The remaining administration of the NCCR is distributed at the different sites in order to carry out the local tasks. Points of contacts have been established in order to ensure a smooth flow of information.

Since the beginning of the NCCR, the management activities have been oriented towards three directions: hiring of new collaborators to make the NCCR administration working, organisation of the reporting and controlling structure of the NCCR, and organisation of the first General Assembly.

Hiring of new collaborators

Four new collaborators have been hired since the beginning of the NCCR:

- Dr. Carsten Knigge is our Finance Administrator since April 2014. He initially worked at 50% and is now working at 90% since October 2014.

- Janine Jungo is our Administrative Assistant since August 2014, working at 80% for the NCCR.

- Yesim Ege Vogel is our Accountant since September 2014, working at 50% for the NCCR.

- In addition, Dr. Timm Riesen is our Technical Officer since June 2014, working at 50%. Dr. Timm Riesen is also part of the communication team (see Sect. 6).

Finally, Dr. Sophie Saesen from the University of Geneva is the Geneva Science Officer since June 2014, and Prof. Yann Alibert from the University of Bern is the Science Officer since June 2014.

In addition to the new collaborators, we have established the network of corresponding administrative assistants in the different participating Institutes:

- Marianne Chiesi, Administrative Assistant at ETHZ, Department of Astronomy

- Michèle Tewlin, Administrative Assistant at ETHZ, Institute for Geochemistry and Petrology

- Suzanne Wilde, Administrative Assistant at the University of Zürich, Institute for Computational Science

- Franca Costa-DeMeo, and Livia Schnyder respectively Administrative Assistant and responsible of the Human Resources at the University of Geneva, Department of Astronomy

Reporting and controlling structure

The reporting and controlling structure has been organised following the ‘PlanetS: Internal Rules and Regulations – June 2014’:

- Projects and Platforms receive their yearly funding in two instalments.  One at the beginning of the funding year (June/July) and one after 6 months  (December/January). The instalments are contingent upon an appropriate scientific and financial planning and reporting.

- Project and Platform leaders report every 3 months on their activities to the Executive Board.

- Project and Platform leaders provide every three months a financial report on their expenses. This report serves as the basis for the determination of the following tranche of each project (in particular in case of large under- or overspending).

- At the end of each year, Project and Platform leaders provide a consolidated finance report that will serve to prepare the NCCR yearly financial report.

The first General Assembly

The first General Assembly took place in Anzère (VS) on January 28th-30th 2015. A total of 95 NCCR and associated members took part in this event including the two distinguished Advisory Board members (Prof. Brian Schmidt, Canberra and Prof. Michel Mayor, Geneva). During this first edition, the global structure of the NCCR was presented, and Projects and Platforms described their plans and first achievements. Ample time was reserved for discussion and networking between participants, and new ideas for inter-projects emerged at that time.

Besides its nominal work, the next special task of the management team concerns the organisation of the Review Panel Site Visit in Bern, scheduled for May 19th-20th 2015.

# Lists

## 9.1 Overview of personnel and functions

Will be generated by SNF from the NIRA data

## 9.2 Education and training

Will be generated by SNF from the NIRA data

## 9.3 Publications

Will be generated by SNF from the NIRA data

## 9.4 Lectures at congresses etc.

Will be generated by SNF from the NIRA data

## 9.5 Services, patents, licences, start-up companies etc.

Will be generated by SNF from the NIRA data

## 9.6 Cooperation with third parties

Will be generated by SNF from the NIRA data

# Statistical output data

Will be generated by SNF from the NIRA data

# Finance

## 11.1 Finance NCCR Overview

See document printed and signed by the NCCR Director

## 11.2 Funding sources

See document printed and signed by the NCCR Director

## 11.3 Allocation to projects

See document printed and signed by the NCCR Director

## 11.4 Expenditures

See document printed and signed by the NCCR Director

## 11.5 Comments on finances

The NCCR PlanetS cash flow is well balanced. The first year’s tranches of CHF 4’400’000 from the SNF, CHF 776’000 from the University of Bern, and CHF 513’500 from the University of Geneva funding have been allocated to the research projects, platforms, and management areas, as needed. Additionally, the Universites of Bern and Geneva approved a Betriebskredit of CHF 93’706 and CHF 35’000, respectively, to purchase basic office equipment and cover running costs (telephone, etc.).

Due to the planned spending profiles throughout PlanetS phase I as shown in NIRA budget and approved by the SNSF, a considerable amount has been kept in the reserve budget. The under spending in year 1 was actually considered as a serious possibility from the beginning as hiring is often more difficult than expected. The Executive Board decided early on to use some of this under spending as an opportunity to provide additional funding for promising activities and/or to start new initiatives.

After 8 months in year 1, the Executive Board felt sufficiently confident about the level of under spending level that it decided to free resources and initiate a call for new opportunities. Proposals received will be discussed at the next Executive Board meeting (March 2015).

Major equipment devices have been purchased or are planned during year 1 as follows:

1- Project 4	ThorLabs Spectral Domain OCT Imaging System		  CHF           55’856

2- Project 6	  GPU Cluster				approx.		  CHF 40’000
3- Workshop equipment (UBE) Fehlmann PICOMAX 95		             CHF 200’000
    (total price CHF 249’673; difference covered by non-NCCR funding)

4- DACE Platform	 	Hardware			  		 CHF 	         13’500

Details on the finance set-up of “Cash” contributions at the University of Geneva

In the first NCCR year, the University of Geneva allocated CHF 513’500 of cash money. For practical reasons, the money is divided over three accounts: DIP/Plage for money originating from the Public Instruction Department of Geneva, FIDEL/Plage (OB5232) for money from the Development and Innovation Fund (FID) and the investments account (UN9027/REC for 2014, a new account for the following years).

The distribution of the cash money from UGE for the first year is as follows:

- CHF 200’000 on DIP/Plage mainly used for the salaries of Dr. Pierre Bratschi (Communication and Outreach Platform), Franca Costa-DeMeo and Lydia Schnyder (both Geneva office).

- CHF 200’000 on FIDEL/Plage mainly used for the salaries of Dr. Sophie Saesen (Geneva Science Officer and sub-project 7.3) and Dr. Rodrigo Diaz (sub-project 7.1, discharge of the co-director).

- For investments, CHF 13’500 on UN9027/REC and CHF 100’000 (year 1 and 2 of the NCCR) in the new investment account.

The cash allocation was underspent in this first NCCR year, but this will be balanced with the spending profiles of the next years.

In order to set up an easy reporting process, expenses made with the cash money on the different accounts are labelled, allowing so a clear ventilation into the different projects, platforms and management areas: laboffice, labcomm, labarchi, labatmos, labdace and labtechno for expenses of the Office, Communication and Outreach Platform, Project 7, Project 3, DACE Platform and Technology Platform, respectively.

# Annexe 1: Strategy for Knowledge and Technology Transfer (KTT)

## 12.1 Scope of the document

Following the explanations provided in section 2.1, our strategy for KTT has been spread over three platforms. The Technology Platform strategy described here focuses only on the aspects related to technology and knowledge transfer to industry and universities of applied sciences. Knowledge transfer within academia is dealt with in the strategy paper of the Academic Platform while the knowledge transfer to the public in general is described in the strategy paper of the Communication and Outreach Platform.

The present document provides the goals of the Technology Platform as well as a strategy to achieve these goals and proposes a few selected high-level tasks. In general it follows the structure of the SNSF document ‘Strategy for Knowledge and Technology transfer (KTT)’ of November 14th 2014. It is planned to update this document after 4 months of its approval by including experts’ comments and early experience.

## 12.2 Current state and aimed goals

### 12.2.1 Assessment of the current state and general goals of the Technology Platform

As a matter of fact, present-day instrumental projects in astronomy and planetary sciences are subject to strong managerial constraints, in particular when they are carried out in the frame of large international and interdisciplinary projects under ESO's and ESA's control. Quality management requires configuration, costs, schedule and risks control at a high level, leaving only little room and resources for the development of new technology. One possibility to overcome this limitation is to separate R&D activity from specific project activity. This strategy has been followed by ESO, who 'outsourced' the R&D activity related to the E-ELT project to a dedicated European Union FP-7 project.

The main activities of PlanetS Institutes and Projects lie in the domain of exoplanets and the planetary sciences. Because of the lack of infrastructures, competences and manpower, technological R&D cannot be (solely) conducted by these Institutes. On the other hand, most PlanetS Projects want to make use of cutting-edge technology to progress in their respective fields. This technology is not available ‘off-the-shelf’ and must be developed in collaboration with Industry. The development costs of high-end prototypes cannot be afforded by the industrial partner alone, and because of the risks inherent to R&D, the commercial benefits cannot be ensured from the beginning. In addition, scientific requirements set by the 'end user' have to be converted into technical requirements of a prototype first, and a final product later. This task may be out of reach of both the PlanetS project and the industrial partner. A third actor, as e.g. Technical Universities or specialised centres, may be required to make the link between the scientific requirements on one side, and the industrial product on the other side.

The main goal of the Technology Platform (TP) is to integrate the various PlanetS activities with specific R&D, which will be useful and in some cases even critical for the success of these activities. It will offer the possibility to investigate the use of new technology and develop or adapt it for the specific project.

In the frame of PlanetS, we aim at developing a strategy on the Swiss scale, involving in a symmetric way partners from universities, technical universities, industry and other institutions related to astronomy and planetary sciences or having an interest in the techniques used in these domains of science. The tool foreseen for this purpose is the Technology Platform. Its goal is to bring these Partners together, promote exchange of information and knowledge, develop and exploit synergies, and promote and coordinate R&D activities.

Fig. 1: Technology Platform triggering the exchange of information and knowledge between the various actors and enabling R&D through seed funding.

### 12.2.2 Areas of intervention

The present strategy paper aims at describing two main areas of intervention requested by the KTT-strategy of SNF to the NCCRs. The two areas are:

- Technology transfer between private and public sector

- Collaborations

- Seed funding for R&D projects

- Seed funding for Start-Up and Spin-Off creation

- Industry grants and CTI projects

- Knowledge transfer between private and public sector

- Collaborations

- Events and workshops

- Expositions

- Portals and data bases

- Services

The TP shall be understood as a general service to any Institute of PlanetS and involve technical universities and industry. It shall be a structure that 'enables' and provides 'seeds' for important activities such R&D, creation of spin-offs, exchange of information. Its top-level objectives are:

- It must be a structure that 'enables' and provides 'seeds' for important activities such as R&D, creation of spin-offs and exchange of information.

- The TP shall first (during the first years) focus on networking activities, for instance:

- Organise the collection of information and identify topics of interest.

- Organise topical workshops.

- Create and support networking

- Define contact persons within the various Projects and Partners

- Organise data bases of people, machines, expertise and infrastructure

- The TP shall select specific projects for seed funding taking advantage of interactions with the various PlanetS projects. The TP should provide, in a second stage (starting during the second year), seed funding for

- Coaching (or help) in creating spin-offs and or preparing CTI proposals

- Coaching (or help) in space qualification tasks

- R&D of high-risk high-gain components/technology

- The TP shall emphasise personal relations, networking, more than technical and financial aspects. Exchange of people and ideas must be supported.

## 12.3 Organisation and resources allocation within the platform

### 12.3.1 Organisation

- A TP Director and a deputy are appointed by the PlanetS Executive Board for the duration of the (approved) NCCR period of 4 years. Their mandate can be extended to future NCCR periods. Together, they constitute the Directorate. The Executive Board can decide to change the composition of the Directorate at any moment. The TP director and the deputy can resign at any moment but remain operational until a successor has been appointed by the Executive Board. This transition period is limited to a maximum of 2 months.

- The TP Director is formally responsible for the achievement of the general goals in the long term (duration of PlanetS) and the execution of the specific tasks in the short term (year).

- The TP Director has decision authority over all decisions taken within the rules defined in the present document. Decisions must however be taken unanimously with the Deputy Director. In case of conflict between the Director and the Deputy Director, the latter may request that the decision is submitted to the Executive Board for approval.

- Changes of goals, organisation and rules can be proposed by the Director, the Deputy Director and Members of the Executive Board. They must be approved by the Executive Board and the present document must be updated accordingly to become applicable.

- In order to accomplish specific and demanding tasks, the Directorate can appoint external experts on the basis of mandates.

- The Directorate members may request administrative support from their host institutes. The University of Geneva commits to provide at least 10% of an administrative assistant each.

### 12.3.2 Use of funding

- The TP is allocated a budget on a 4-year basis. The yearly budget is reviewed and approved by the Executive Board at the beginning of each administrative PlanetS year. It is subject to proper planning and reporting.

- At least 50% of the allocated budget must be used for R&D projects and seed funding.

- The Directorate decides on funding allocation for administrative tasks and mandates, as long as 50% of the yearly budget is not exceeded.

- The Directorate organises calls for and allocates funding for R&D projects and other seed funding.

- The Directorate reports on activities in the TP at every Executive Board meeting and the use of funding to the Executive Board at the end of each administrative PlanetS year.

Fig. 2: Organisation chart of the Technology Platform

### 12.3.3 Seed funding for R&D projects

- Proposals for R&D activities and seed funding related to PlanetS can be submitted at any time to the TP. The proposal must have a connection with at least one activity carried out in PlanetS, in the sense that a possible benefit for this activity must be identified in advance.

- The proposal can be submitted by anybody, in particular also third parties from industry, technical universities and specialised centres, as long as they are supported by at least one Executive Board member.

- The Directorate prepares rules for the proposal submission and selection, which have to be approved by the Executive Board. The rules must be published on the TP web site within the PlanetS web site.

- The Directorate selects successful proposals, which request funding not exceeding 10’000 CHF.

- In the case of proposals requesting funding exceeding 10’000 CHF, the directorate will select a short list of proposal compliant with the goals of the TP and submit it to the Executive Board. The Executive board will decide whether to allocate funding and to which project considering the recommendations by the Directorate.

## 12.4 Action plan

After consultation with external experts, the following high-priority tasks have been identified in the two main areas of intervention:

1) Technology transfer between private and public sector

- Define paths and propose coaching (through external experts) for various activities, e.g. spin-off and start-up ideas, preparation of CTI proposals, space qualification activities, etc.

- Support submission of patents issued for PlanetS-related activities.

- Assign seed funding to R&D projects related to PlanetS activities and involving at least a PlanetS project and at least one partner from industry and technical universities.

2) Knowledge transfer between private and public sector

- Prepare a web portal describing goals and rules of the TP. Describe individual PlanetS projects, their interests and competences, technologies, contact persons. Also, the rules for applying for seed funding must be published.

- Mandate an 'expert' to establish a list of Swiss-wide contacts in the fields related to astronomy/planets (SW, electronics, mechanics, optics, and combinations) containing:

  - Company/Technical Universities/Research Institutes/Labs

  - Competences and technologies

  - Interests

  - Contact persons

- Organise 1 or 2 topical workshops per year on areas identified as 'interests' in a large number of companies/institutes. Possibly combine with other NCCRs, SwissPhotonics, or other organisations.

- Create contacts with other NCCRs and organisations, such as MUST, MaNeP, EUROSEARCH, SSOM, local consulting entities like UniTec at UGE and similar services in other Universities.

- Mandate an expert for making a Swiss-wide database containing available infrastructures and instruments (and conditions) in the previously mentioned entities. This could be done through a web form, and the database will be made available to all the contributors.

- Organise, enable or contribute to events that help improving the exchange of information and knowledge between all the parties, including students and futures collaborators.

- Once per year, an expert shall comb through all the projects for technologies and concepts developed within PlanetS with respect to potential transfer to industry or for commercialisation.

The list of high-priority tasks is updated once per year and must be in agreement with the general goals of the Technology Platform.

## 12.5 Examples for the Technology Platform activities

### 12.5.1 External mandate

An external expert will be mandated by February 1st 2015, to accomplish the task 2b). A preliminary Statement of Work foresees:

- Make a list of all of the Swiss companies related to Space and Ground-based astronomy and planetary sciences through the market of high-end components or R&D in mechanics, electronics, optics, SW, or a combination of them.

- Contact companies in order to

    - Identify a person of contact and establish coordinates

    - Identify 'off-the-shelf' products

    - Identify areas of interest and R&D in which a collaboration is suitable

- Listen for suggestions and complaints with respect to knowledge and technology transfer with Technical Universities, Research Institutes and other NCCR or organisations.

- Produce a report on the status of the KTT in the areas related to astronomy and planetary sciences, and issue recommendations to PlanetS and the Technology Platform to enable and improve KTT.

- Propose a web-based solution to collect information of interest that could enhance the KTT (more the concept and a list of information items than the implementation of the tool, itself that would be subcontracted)

- Propose two topics for Swiss-wide workshops, e.g. in collaboration with MUST, including a preliminary list of participants (the workshop would be organised on a separate mandate.

### 12.5.2 CTI project

Recently, a new CTI project ‘Development of a highly efficient and miniaturised femto-second fiber-laser system at kHz repetition rates’ proposed by the University of Bern and related to PlanetS has been approved. The Technology Platform will, within task 1a), support these activities to further strengthen KTT in this area between PlanetS and industry.

### 12.5.3 R&D project

CSEM proposes, in collaboration with Project 3, to start the laboratory development of a stable and accurate calibration source for precise calibration of high-resolution spectrographs. The proposal foresees also to include industry in the early phase in order to identify possible commercial slots. If approved, this project will be placed under task 1c) of the Technology Platform.

# Annexe 2: Strategy for Education and Training

The Education and Training activities of the NCCR are under the responsibility of the Academic Coordination Platform. Our Platform is focussed on: a) developing a doctoral network for PhD students and post-docs in planetary sciences, including academic training opportunities, b) providing professional development opportunities for junior scientists, c) developing a mechanism for generating novel research ideas, and d) promoting the scientific profile of the NCCR nationally and internationally.  We believe that by achieving our goals through best practice in education (and management) we will also help improve the diversity of our research community with regard to gender and other under-represented groups.  In addition, by making sure our activities are open to the widest possible population of colleagues, we will ensure excellence (and success) in our creative research.

## 13.1 Assessment of the current state

Planetary science is by its nature an interdisciplinary endeavour, involving the exploration and characterisation of our Solar System.  As the study of extra-solar planets matures, since the first discoveries in the mid-1990s, planetary science has come to include their discovery, and characterisation as well.  As an academic program, it has grown in stature and breadth richness through the “space race” of the 1960s and 1970s.  It makes use of discipline-specific techniques from physics, astronomy, chemistry, geology, computational sciences, and others.  Several prominent Universities (mostly within the United States) have units with the term “planetary science” in the title.  Within Switzerland there are no specific degree programs with the label “Planetary Science”.  This is also reflected in Europe.  However across the continent, as well as in Switzerland, there are many research groups active at the forefront of the field.  Indeed, most of the planetary science experts, from many disciplines, within Switzerland, are involved in the NCCR PlanetS.

To assess our current position, we have decided to make surveys of NCCR members central to the planning of our activities. They are intended to collect a broad range of ideas and help start group conversations about the goals of education at the doctoral level. Three surveys (of existing and planned advanced planetary science, ideas concerning what should be included in a core planetary science curriculum, and of PhD student and postdoc professional development needs) have been completed. The results are reported in the Progress Report.

## 13.2 Areas of intervention

### 13.2.1 Target Groups and Goals:

- Our main target audiences are PhD students and postdocs across the NCCR.  Our goal is to provide them with high-quality, interdisciplinary, scientific training over an appropriate breadth of topics, as well as professional development opportunities that will make them internationally competitive. These goals are synergistic with those of the Education and Outreach Platform, which targets younger students. We strive to do this within a supportive, equitable, and family-friendly setting, which is explained in more detail in the Equal Opportunity Strategy Paper.

- Second, we will provide creative, critical thinking environments (for research as well as management and also didactics) for the senior staff of the NCCR to stimulate novel research directions and new initiatives, and to support best practice in so-called “soft skills”, often underemphasised in training, to become senior staff.

- Our final target audience is the international scientific community in planetary sciences, to insure that we have the visibility needed to maintain our excellence.

### 13.2.2 Measures for intervention:

- Junior scientists

  - We will create the PlanetS Doctoral Network in Planetary Sciences further described in the Action Plan below.  Our goal is for members of the junior scientific staff to develop the scientific breadth and depth necessary to conduct interdisciplinary research in planetary science.  Guidelines for, practice with, and feedback on professional development topics 1, 2 & 3 above will be integrated as much as possible into courses (fall and spring semesters), Schools (e.g. the Saas-Fee School on “Circumstellar Disks and Planet Formation” scheduled for March 2015), scientific meetings (General Assembly and NCCR Thinkshops), and professional development workshops (one scheduled for fall 2015) in the coming calendar year.

  - Finally, we propose a Mentoring Program where junior scientists will be assigned a more senior mentor from another Project/Institution (see Action Plan).

  - We will invite two internationally prominent scientists in the field to visit Switzerland as Visiting Scholars, to spend between 2-8 weeks per year in residence and teach within our Doctoral Network.

  - Finally, feedback on the successful strengthening of young researchers’ scientific and professional skills will be collected at the next General Assembly, in January 2016.

- Senior scientists

  - The main interventions targeting the scientific leadership of the NCCR are the Annual General Assembly, Thinkshops, and other scientific meetings we plan to organise through the NCCR.  In particular the Thinkshops (at least one per year) are meant to spur creative thinking on complex research projects at the interfaces between multiple disciplines.  These three-day events will be co-organised by members of the junior scientific staff and will be framed around “grand challenge” problems contributed by all members of the NCCR and selected by the organisers.  Most of the agenda will comprise structured working time in teams with periodic reports back to the larger group.  Expected outcomes are collaborative research papers and/or new initiatives proposed to the NCCR Board.

  - Our senior staff will be encouraged to interact with our international Visiting Scholars.

  - With micro-training (e.g. an introduction to one type of peer instruction, a short discussion about equitable hiring practices, etc.) in the teaching, mentoring and other professional activities in which they are involved. These interventions will occur in sessions at the General Assembly, NCCR Board Meetings, and other informal activities.

- International planetary science research community

  - We will reach the international scientific community through our published research papers as well as prominence at international conferences and involvement in prominent international projects.

  - Our most effective mechanism to reach this audience will be to sponsor a major international conference every 1-2 years in planetary science.  Members of the NCCR are strongly involved in the upcoming “Pathways Towards Habitable Planets” to be held in Bern in summer 2015.  We will also propose another such conference in summer 2017 at the Congressi Stefani Franscini in Ascona, Switzerland on the topic of “The Composition of Forming Habitable Planets”.

  - Hosting our Visiting Scholars will also allow us to enhance our international connectivity.

### 13.2.3 Tools

In addition to the resources made available to the Academic Platform through the NCCR itself, there are other instruments we can utilise to support our efforts.  For example, sharing research through publications can be accomplished through the mechanisms of the Communication Platform.  Sharing of data and software will be strongly enhanced through the DACE Platform.  Technology needed to meet our “grand challenge” problems will be developed through the Technology Platform. There are synergies between the methods of the Gender Equality Strategy plan and the Academic Platform plan in mentoring and professional development.  We will also take advantage of resources available locally through our partner Institutions, particularly for professional development, as we do not intend to reinvent services adequately offered elsewhere.  Finally, some of our goals can be reached more efficiently with the help of our international partners (e.g. our strong interactions with peer institutions such as Harvard University, Cambridge University, and the Max-Planck-Institut für Astronomie in Heidelberg).

### 13.2.4 Metrics for success

In order to measure the outcome of our actions, we have adopted the following strategy:

1. It is our goal to offer our first certificates of completion for our “PlanetS Doctoral Network in Planetary Sciences” before the end of our first four years of the NCCR.  We will also attempt to track the success of our former students and post-docs to measure career success (Prize Fellowships, progress towards permanent positions, both inside or outside of academic research) relative to cohorts in our Institutions and Departments not evolved in the NCCR.

2. We will track the number of interdisciplinary (inter-project) publications each year as well as the number of new initiatives launched within the NCCR as a relative measure of our success year to year.

3.  It will be difficult to track success in terms of our international visibility as PlanetS is spread across several Institutions and Departments.  However, we will attempt to conduct a review of our success in comparison to peer initiatives (e.g. the Harvard University “Origins of Life” Center, Austrian “Pathways to Habitability” Network, Heidelberg “Origins of Life” Initiative).

## 13.3 Resource allocation and organisation

The Steering Committee, to whom belong members of the major partners of the NCCR:  Prof. Michael Meyer (ETHZ), Prof. Maria Schönbächler (ETHZ), Dr. Sascha Quanz (ETHZ), Dr. Yann Alibert (UBE), Prof. Stephane Udry (UGE), and Prof. Lucio Mayer (UZH), is the main governing body of the Academic Coordination Platform.  The Executive Group (Prof. Michael Meyer, Prof. Maria Schönbächler, and Dr. Audra Baleisis) meet regularly to prepare the business for the Steering Committee.  The Steering Committee meets via telecom before each Board Meeting to prepare any business for the NCCR Board.  The baseline annual Budget for the Academic Platform is as follows:

    - 38 kCHF for a the coordinator (25 %) and administrative support (10%)

    - 7 kCHF support for coordinator work (travel, printing, miscellaneous, etc.)

    - 40 kCHF for a Summer school and Professional Development Workshop

    - 20 kCHF for IT support (remote learning for doctoral network)

    - 20 kCHF for two visiting Fellows per year (they will also teach at school)

    - 40 kCHF to support the NCCR Thinkshops.

The total annual budget is 165 kCHF per year for the Academic Platform.

## 13.4 Action plan

|  | Goals | Measures |
| --- | --- | --- |
| PlanetS doctoral network | -Make available to PlanetS doctoral students and postdocs the combined strengths of the Swiss (and international) exoplanet research community through a certification program consisting of: two PlanetS courses, two Summer/Winter schools, and one external research project | -Coursework: each member institution will offer at least one specialised, advanced course per year in planetary science related to the content of the NCCR open (and accessible) to local students as well as all NCCR students. Reformed reaching techniques will be included in courses (e.g. peer instruction, formative assessment), to benefit all participants, but also because they have been shown to improve women’s experiences in science courses -Summer/winter school: One school per year, at a doctoral/early postdoctoral level, taught in English by instructors from within the NCCR and at least one external international guest lecturer. Novel lecture formats will be piloted and reported on, as well (e.g. student/professor team lectures, regular question breaks) -Interdisciplinary projects: Each PhD student will have one consequential research project outside her/his home institution, including bi-annual reports from both student and advisor to the Academic Platform coordinator. This will further support the goals of the SNSF “doctoral mobility” initiative whereby students are encouraged to work with researchers and other than the home Institution, exposing them to diverse research styles, and improving their international competitiveness. -Visiting scholars program: Yearly 2-8 week visits of international scholars (Gender mainstreaming note: women researchers will be especially recruited) will be organised, which will allow our students and postdocs more personal access to the international research community |
| Professional development | -Provide professional development opportunities that align with the needs and desires of NCCR doctoral students and postdocs | -Each year, survey current members (first survey completed December 2014) about experiences with mentoring and interests in terms of professional development -Once per year, a daylong professional development workshop in Fall run by the Academic Platform Coordinator and including at least one external expert presenter (Gender mainstreaming note: topics will include issues relevant to gender equity) -Provide a professional development session once per year at the annual PlanetS meeting, with an outside expert on a topic selected with input from young PlanetS researchers -Embed professional development activities when possible in Summer/Winter schools, meetings, and PlanetS courses, in order to keep activity load manageable for participants, and to ensure high standard of professional development training for all |
| Scientific meetings, Thinkshops | To foster innovative interdisciplinary research programs that cut across projects within the NCCR in order to increase our international standing in research excellence and provide unique professional development opportunities for junior scientists | - We plan to sponsor at least one Thinkshop per year organised in part by junior scientists with assistance from the senior staff. Grand challenge topics can be proposed by any member of the NCCR. The meetings will be workshop style rather than rich with formal presentations. They will last 2-3 days with the goal of generating ideas for new projects within the NCCR. - We will organise at least one major scientific conference every two years within the NCCR drawing top researchers from around the world to meet and discuss a particular theme within the broad range of topics in planetary science. |
| Work/life balance | -Raise awareness among young researchers for the variety of realisations of science careers (including part-time and non-academic career options) -Provide support for young researchers to take advantage of NCCR opportunities (including family-friendly scheduling). |  |
| Mentoring | -Provide manifold, high-quality mentoring opportunities for young researchers with more than one researcher senior to them | -Monitor yearly PhD student progress and satisfaction with program (survey) -Establish short, mandatory, twice yearly mentoring meetings (postdocs mentor PhD students, senior researchers mentor postdocs) -Interdisciplinary research projects for doctoral students including senior scientists who will interact with them |

# Annexe 3: Strategy for Equal Opportunities

## 14.1 Assessment of the current state

The NCCR PlanetS is a collaboration of scientists from the fields of Astronomy, Geology, Computer Science, and Physics for the study of planets inside and outside the Solar System.  The institutions represented include: the University of Bern (Leading House), the University of Geneva (Co-Leading House), the ETH Zurich, EPFL, and the University of Zurich.

### 14.1.1 Gender diversity situation in Switzerland and Europe

In 2010, the percentage of women employed as scientists and engineers is lower in Switzerland than in EU countries and other countries such as Turkey, Norway, Macedonia and Iceland.  For the EU-27 countries, on average 32% of scientists and engineers were women, whereas for Switzerland, that number was only 18%. This shows that women are still underrepresented across the continent (gender parity = 50% women), and that this inequality is even more exaggerated in Switzerland.

The causes of this situation are manifold, rooted in our cultures (both mainstream and academic), and are not easy to encapsulate.  Partially influenced by negative stereotypes about girls’ math abilities, less experience developing spatial skills, and cultural ideas about STEM (Science, Technology, Engineering and Mathematics) fields being “male”, a relatively low percentage of young women enter into undergraduate STEM programs. This is followed by the increasing challenge of retaining women in science the further they progress in an academic science career. This is related to the difficulty in balancing a family and a career at the same time and (at the professor level) the successful integration into departmental culture (due to long working and meeting hours, unconscious biases, a male-dominated working environment) .

### 14.1.2 Current state of gender diversity in the NCCR PlanetS

Despite best intentions, we have to admit that the first round of hiring for the NCCR was not very successful in terms of gender diversity. Once the list of current members was assembled, it was clear that women are underrepresented at all levels (except for administrators) compared to the numbers of the host institutions (see Appendix 1 of this document for numbers taken from the different host institutions)

Since we aim to promote gender diversity, the Executive Board for Equal Opportunity has decided to look into the reasons. The assessment has started with a review of the applicant pool gender make-up, as well as interviews with the Project Leaders about the various factors (on their side, and on the side of the applicants) that led to their final hires. Once these data are gathered, corrective measures will be implemented. These likely include discussions about equitable hiring practices, which will result in a list of suggested guidelines for future hiring. Future job searches will be monitored for improved gender balance, and the results will be reported (at the yearly Annual Meeting, once a year during a meeting of the Executive board, and in the online newsletter).

Table 1: Current gender make-up of the NCCR

| Category (total number of people) | Female | % of total |
| --- | --- | --- |
| PhD (16) | 3 | 19% |
| Postdoc (18) | 3 | 17% |
| Postdoc+Senior Scientist*(35) | 4 | 11% |
| Professor (Assist+Full) (16) | 1 | 6% |

* this category includes researchers who have a PhD degree, but are not professors.

### 14.1.3 General Assembly, Anzère, Switzerland, January 2015

The first annual meeting of the NCCR PlanetS was held at the end of January 2015.  This was the first time the larger group of students, postdocs, administrators and researchers met together.  The General Assembly is the major event in the NCCR year. We plan to incorporate the lessons learned from this first meeting to inform future General Assemblies.

- The first event for the Advancement of Women for NCCR PlanetS, a women’s networking breakfast, was held during the meeting (more details are in the Equal Opportunity section of the Progress Report). Future events will likely include male participants as well.

- There will be an Equal Opportunity-themed talk or session at future meetings.

- Due to inquiries from a number of participants, childcare was made available for this meeting. We will include this service (or consider a hotel that provides child care) in the future.

- Some NCCR members were not able to attend the meeting in person (in part due to family illnesses), because the location was so remote. We will strive to choose more accessible meeting locations in the future, but also provide live streaming of key talks.

## 14.2 Areas of intervention

The first year’s activities will focus on data collection and awareness raising within the NCCR. This is geared towards identifying imbalances and underlying causes that are directly relevant to the members of the NCCR (a bottom-up approach). The data collection includes: (i) gender statistics for applications and final hiring for current and future PhD student and postdoc positions, and (ii) gender statistics for meeting/course attendance and active participation (e.g. given presentations, numbers of questions asked), (iii) feedback on various events and activities to assure relevance to participants, and (iv) a tally of issues of interest or concerns raised by PhD students and postdocs. These data are reported to PlanetS decision makers and other participants to raise awareness of “the state of the NCCR” and to highlight actual gender-related problems or successes. The report is provided to the Executive board during one of its meetings, and presented to all NCCR participants during the General Assembly.

In terms of objectives and measures, there will be some overlap with educational and professional development activities (see strategy report for Education and Support of Young Researchers) and outreach (to spark the interest of girls at an early age for science). This is because we believe gender equity and diversity are not only women’s issues. Men’s participation is necessary for success, and success in these areas helps men’s experiences as well. In addition, it has been shown that thoughtful teaching, and mentoring, climate and work/life balance conditions within a department improve women’s performance and retention within academic science.

Subsequent years will build upon the experiences of the first year. We will continue with the type of data collection and reporting that yield the highest impact in the first year. We will critically evaluate the impact of our measures and focus on those that receive the most support and positive feedback from participants. We strive to be open to student- and postdoc-led initiatives, and are aware that new interests and needs will arise as new members join the group and may require an adjustment of the measures.

Our goal is to impact three main groups: (1) women who are part of the NCCR  (2) all PhD students and postdocs of the NCCR (male and female), because of their role as future leaders, teachers, professors, and mentors, and (3) the decision makers/gate keepers/leaders (people responsible for hiring, mentoring and teaching groups (1) and (2) within the NCCR.

## 14.3 Resource allocation and organisation

The gender officer for NCCR PlanetS will be Dr. Audra Baleisis, and the delegate of the Executive Board for Equal Opportunity will be Prof. Maria Schönbächler. Currently there are 3 members (2 women, 1 man) of the Academic Platform Steering Committee (which is responsible for both Education and Advancement of Women) from ETH. Select representatives (NCCR researchers) from the other PlanetS institutions will provide feedback to the Steering Committee. Financial resources are allocated to support the activities in the framework of equal opportunities and we have announced to our members the availability and support for applications to the SNF 120% program, where applicable.

We have also begun to establish relationships with the gender equity offices at the 5 participating institutions, for input to our strategies, but also with the goal to collect information about relevant resources and events, which will then be distributed to our members.

## 14.4 Action plan

We propose a wide range of measures to achieve our objectives (see Appendix 2 for more details). They can be summarised into a few main objectives:

- Gender equity is actively addressed in the communication within and outside the NCCR and during the hiring process

- A healthy and sustainable working climate is maintained for all NCCR members

- Familiarise NCCR members who teach NCCR graduate courses and/or summer/winter school courses with best educational practices and awareness of gender issues related in teaching

- Help train students, postdocs, and senior scientists in important, non-technical career skills, and in understanding the cultural aspects of academia that influence career satisfaction and persistence

- Provide PhD students and postdocs with more senior-level female role models

- Increase career support and mentoring resources available to PhD students and postdocs

- Report on our activities to the wider research community so others have ideas to build upon and/or increase their own awareness of gender-related issues

Summary of measures:

For group 1 (women PhD students and postdocs), we propose a network of peers, as well as women-only career development events as needed and/or requested.

For the larger group (all members of the NCCR), we aim to raise awareness of gender issues and the current state of the art in research on diversity. This will include topics such as: diversity of thought, gender statistics within the NCCR, unconscious gender bias and stereotype threat, the disadvantage of traditional gender roles (punishing women for assertiveness and men for showing emotion), equitable hiring practices, best educational practices (which have been shown to benefit women’s performance and retention in science courses), harassment, and institutionalised sexism (e.g. meeting times/locations that negatively impact primary caregivers of children, who tend to be women), and family-friendly workplaces. Through their future (and current) roles as leaders, teachers, advisors, and parents, these individuals are essential as allies to fostering gender equity.

Our approach includes a variety of measures (as detailed in Appendix 2), across the organisational, cultural, training, teaching, career development, and work/life balance aspects of the NCCR. The main components will be:

- Collecting relevant gender balance data and reporting it to the NCCR (through the website, newsletter and at meetings)

- Training NCCR members on equal opportunity issues (at dedicated meetings as well as the yearly General Assembly and regular Executive Board meetings)

- Providing mentoring and networking opportunities to PhD students and postdocs

- Providing useful information and links for career support, professional development and work/life balance issues (on the website and events)

- Emphasising family-friendly work structures and equitable hiring practices

- Reporting interesting outcomes from our NCCR to the wider research community.

Table 2: Gender situation in NCCR PlanetS home institutions for 2013

|  | Female % of total | Male % |
| --- | --- | --- |
| ETHZ (all departments) |  |  |
| Ph.D. | 31% | 69% |
| Postdoc | 28% | 72% |
| Oberassistent | 25% | 75% |
| Senior Scientist | 13% | 87% |
| Full Professor | 10% | 90% |
| UBE (fakult. Phil._Nat.) |  |  |
| Ph.D. (abschl) | 35% | 65% |
| Postdoc | N/A | N/A |
| Unterer Mittelbau | 34% | 66% |
| Oberen Mittelbau | 27% | 73% |
| Professor | 8% | 92% |
| UGE (Faculte des Science) |  |  |
| Ph.D. | 45% | 55% |
| Postdoctorant-e | 36% | 64% |
| Coll.enseignement et recherche | 35% | 65% |
| Professeur-e | 16% | 84% |
| UZH (MNF) |  |  |
| Ph.D. | 49% | 51% |
| Postdoc | N/A | N/A |
| Mittelbau | 40% | 60% |
| Professor | 16% | 84% |

Table 3: Action Plan

| Areas of intervention | Objectives | Measures |
| --- | --- | --- |
| Integration of Gender Equality in the NCCR (organisational, cultural, training, or policy level) | - Gender equity is addressed in the communication of the NCCR - Gender equity is actively addressed in hiring within the NCCR -Healthy and sustainable working climate is maintained for all NCCR members | -Monitoring and reporting NCCR gender balance statistics (at Executive Board meetings, in the newsletter, and at the yearly General Assembly) -Present main actions in Equal Opportunity on the NCCR website -Investigate and report on factors of initial round of hiring that led to under representation of women -Establish criteria for equitable hiring practices -Assign an NCCR contact person (A. Baleisis), and provide home institution contacts on website for counselling services, ombudspeople, and harassment problems of any kind -Provide links on website to SNF 120% program, equal opportunity offices/events at the 5 involved institutions, childcare topics |
| Gender-aspects in research and teaching | -Familiarise all NCCR members who teach NCCR graduate courses and/or summer/winter school courses with best educational practices | -Course structures should include peer instruction, clear feedback on student progress, feedback to instructors on student understanding, opportunities for supplementary help where necessary, all techniques that have been shown to increase the performance, participation and/or retention of women in STEM courses of study |
| Careers and career development | -Help train students, postdocs, and senior scientists in important, non-technical career skills, and in understanding the cultural aspects of academia that influence career satisfaction and persistence -Provide PhD students and postdocs with more senior-level female role models -Increase career support and mentoring resources available to PhD students and postdocs | -A yearly professional development workshop in fall semester for all students/postdocs, with gender-helpful aspects included (impostor syndrome, giving talks, job searches, etc.) -A yearly presentation in winter at the General Assembly, for all participants, on the State of the Art in diversity and equal opportunity (with invited expert speaker) -Twice yearly, a presentation for project leaders on gender diversity issues at a Board Meeting -The Visiting Scholars programme (see Education Strategy Paper) puts emphasis on inviting female researchers to visit at least 2 of the participating institutions for multiple weeks -Survey PhDs yearly for progress, adequate mentoring, problems encountered, and satisfaction with program -Assign postdoc mentors to PhD students, and senior researcher mentors to postdocs, to meet at least 2x per year -Follow the professional development of all our female students and postdocs, not only regarding their work after their NCCR contract, but for the whole duration of the NCCR (networking) |
| Work/Life Balance | -Provide a work life experience that takes into account members’ non-work responsibilities | -Keep appropriate meeting/class start and stop times, and locations -provide partial financial child-care support at PlanetS meetings -Provide remote access to meetings that some members are not able to attend -Support applications to the SNF 120% program -Include work/life balance themed discussions by NCCR members (students, postdocs and senior scientists) in the newsletter and on the website |
| Gender aspects in the wider academic science community | -In Years 2-4: report on our activities to the wider research community so others have ideas to build upon and/or increase their own awareness of gender-related issues | -Collect data that can be published outside the NCCR (according to institutional ethical guidelines) -Exchange information with other actors in Equal Opportunity (e.g. other NCCRs). If possible, publish in a professional journal our diversity related data, activities, and/or results |

# Annexe 4: Communication Strategy

## 15.1 Starting point and analysis

### 15.1.1 The NCCR PlanetS

The NCCR PlanetS is a national effort in the coordination of research in origins, evolution, and characterisations of planets (solar system & exoplanets). This effort is structured in individual research projects and common platforms. This structure will lay the foundations of a Swiss Institute of Planetary Sciences (SIPS) that will carry on these activities beyond the lifetime of the NCCR.

### 15.1.2 Vision

The NCCR PlanetS is to become a leading organisation worldwide dedicated to the study of the origin, evolution and characterisation of planets within our own solar system and beyond. The NCCR PlanetS carries out integrated research in planetary sciences that combines the interests, research capabilities and capacities of the institutes involved and is oriented towards a long-term vision.

### 15.1.3 Mission

Within the NCCR PlanetS we aim to coordinate academic education by creating an interdisciplinary doctoral network in planetary sciences to train the next generation of highly skilled scientists. We will operate platforms for technology development and transfer as well as for data exchange and analysis. We will have an internationally visible and coordinated scientific exploitation of data from the CHEOPS satellite. We will develop new research groups and new laboratory facilities and we carry out a large multi-regional education and outreach programme.

## 15.2 Communication

Communication is an essential component of scientific activities. Within a comprehensive programme such as the NCCR PlanetS, continuous communication between the participants ensures that the resources and results are optimally exploited. Being informed about the progress of the different research projects enables the participants of NCCR PlanetS to concentrate efforts and make use of synergies. Broad communication within the international scientific community is crucial for generating new knowledge since measurements have to be verified and theories must be tested.

New insights into the formation of planetary systems and particularly into the origin of the Earth are topics of great interest to the general public. For millennia, people have wondered where we come from and whether we are alone in the Universe or if there could be extra-terrestrial life out there. These questions are popular topics for fantasy novels, science fiction movies and scientific speculations. For the first time in history, we are now on the verge of being able to provide a scientific answer to these questions. The general public should and wants to be informed about the exciting progress in planetary research. An open and comprehensible communication helps the taxpayer to understand the science results and appreciate the cultural value of scientific knowledge.

Developing an efficient communication for an endeavour of this magnitude with research teams distributed over several geographical locations, affiliated to different institutions, speaking different languages, and having different cultural background is a real challenge but nonetheless of central importance. We are convinced that the success of PlanetS as an NCCR hinges for a large part on efficient internal communication.

Our overall goals are:

- To build an efficient and productive global team while acknowledging local strengths

- To generate the identity “PlanetS” that will be recognised in the public and that facilitates the transition from NCCR to a self-sufficient institution after the NCCR will terminate.

In the next section, we perform an analysis of the current situation, with the said goals in mind and will use it to derive our basic guidelines, concept, and specific communication goals.

We evaluated the (S)trengths, (W)eaknesses, (O)pportunities and (T)hreats to the NCCR PlanetS with respect to the content of our communication (research, science) and the possible impact on it.

## 15.3 Communication objectives

The main purpose of communication is to inform all members of the NCCR (internal), the scientific community in general, as well as the public (external) about the activities taking place within the NCCR, the opportunities available, and the results achieved. Its role is to establish and strengthen the reputation (external) and identity formation (internal) and to increase the awareness of the brand NCCR PlanetS in order to pave the way to the foundations of a Swiss Institute of Planetary Sciences (SIPS) that will carry on our activities beyond the lifetime of the NCCR.

Because the topic of our research finds a particular resonance within the general public, we use this advantage to promote interest in natural sciences among students of all ages, gender, and level. We set the following communication objectives:

##### Communication objective 1 (external, scientific community)

The communication team provides the researchers of PlanetS the help needed to communicate their research results efficiently and attractively to fellow scientists. In a competitive scientific environment, efficient communication is an essential element to attract future large projects.

#### Indicators:

- Of all NCCR PlanetS media releases, 80% will be advertised in international webpages and in news services that carry an audience interested in these topics.

##### Communication objective 2 (external, general public)

The communication team helps the researchers of PlanetS to explain their results to the general public in an understandable and attractive way. Popular articles, texts, and targeted outreach activities will increase the awareness of the general public. It will also underline and confirm the long-term usefulness of our research, and of natural sciences in general, and its benefits to the society.

#### Indicators:

- The number of media reports will increase by about 15% per year.

- The number of feedback forms used after school workshops that state the experience as «positive» is greater than 75%.

##### Communication objective 3 (internal)

The communication team provides the maximum support for ensuring an efficient internal flow of information and a sense of togetherness. Building a coherent research effort with maximum synergy out of a diverse and geographically distributed group of research teams is one of the major challenges.

#### Indicators:

- 95% of the NCCR PlanetS members will open the issues of the newsletter

- 70% of the NCCR PlanetS members will click at least one of the links provided in the issues of the newsletter

- 90% of the NCCR PlanetS members will participate in the yearly General Assembly

- Each contact person for communication of the 7 NCCR PlanetS projects will fill out a qualitative survey about the communication in mid 2015 and mid 2016

##### Communication objective 4 (external & internal)

We emphasise the fascination with the subject. And we show the people behind the research. We create an emotional bond between the topic and the target groups.

#### Indicators:

- We measure a 15% increase in queries (email, phone, etc.) and requests for visits, special events, and talks over the years.

## 15.4 Communication strategy 2014 – 2018

Since human and financial resources are limited, we are focusing our work on communication activities with the greatest impact. We use the financial resources to support a few selected larger activities. Smaller events we support with PR material and know-how.

#### Communication guidelines

- We communicate openly, understandably and in a timely manner.

- We encourage publication of information. The communication department is always informed about the newest results and interesting facts.

- We use information in a reasonable and scientifically accurate manner.

- We always have all target groups in mind.

- Requests from media and other stakeholders will be generally answered immediately but at the latest within 24 hours. If researching specific information takes longer, we send a message acknowledging the query and provide information as to when the information will become available.

- We put the people that are actually behind the research into the centre of our communication.

- The communication to the public is generally offered in German and French. In some cases, Italian and English are used.

- Press releases are always available in English, German and French.

- The internal working language is English.

## 15.5 Target groups & messages

#### External target groups

- Scientists outside PlanetS

- General Public

- Media

- School classes of all levels
- pupils, high-school students
- teachers

- University students (potential members of the NCCR PlanetS)
- special focus: women

- Museums and Exhibition makers
- Science & Natural history and Technical Museums
- Shopping centres
- Events, e.g. BEA expo

- Decision-makers (Politics and Economy)
- SNF
- State Secretariat for Research, Education, and Innovation (e.g. SSO) 
- Universities, e.g. Rectorate, Directors of Institutes

- Selected parliament members (at federal, cantonal, and local levels)

- Partner organisations

- Musée d’histoire des sciences, Genève

- Swiss Museum of Transport, Lucerne

- Burgergemeinde Zermatt

- ESA

- ESO

- Industry

- Organisations: SWISSMEM, SSIG, etc.

- Individual companies, especially the SME

- Astronomy and Space Clubs

#### Internal target groups

- NCCR PlanetS Members

- NCCR PlanetS Project leaders

- Scientists working on related topics at UBE, UGE, ETHZ, UZH, EPFL

## 15.6 Communication style

#### General addressing of stakeholders

With respect to language, we aim to use an objective and passionate tone. For our texts, presentations etc. we adjust the jargon and the degree of complexity to each target group. While we use scientific jargon to address scientists, we leave off as much jargon as possible for the general public and replace it with common terms or describe them pictorially.

#### Multimedia

In our communication we use, wherever possible, images, videos and audio files. If there are no related materials available on a specific topic, we try to get appropriate material or create it ourselves.

If we produce it ourselves, we aspire to professional standards whenever possible. This means that at least one person of the communication team is trained in the appropriate medium or has experience in dealing with this kind of media.

#### Pictures

- For each text there is at least one image available.

- To explain a topic we create info graphics.

#### Audio and video

- We provide footage of major events and record interviews and animations.

- We follow long-term projects using time lapse.

## 15.7 Marketing activities

##### Activities for external target groups

#### Media relations

In order to have a presence in the public domain, we need to communicate to the media that the NCCR PlanetS exists and inform them about its objectives.

2014/2015

- Media Conference. Inform the media about the NCCR PlanetS, show the current status and introduce the main persons behind it. For this, we will need
- basic documentation about the NCCR PlanetS
- current status of all projects and platforms

- Media releases. To maintain a public presence, the NCCR PlanetS will prepare a media release at a regular interval (typically every 3 months). To do so, we will need to collect
- content that is worth to be told (new research results, events etc.)

2016-2018

- One media conference per year

- Send out at least one media release every 3 months

#### Website (with respect to external target groups)

2014/2015

- Build the web content for the general public, media, and scientist worldwide. We inaugurated and launched the website on January 28th 2015 during PlanetS General Assembly (see http://nccr-planets.ch).

2016-2018

- We extend the content on the website continuously.

#### Social Media

One of the most important channels in the social media is Facebook. We are considering creating a Facebook channel to reach the general public. We keep other social media in mind as well.

2014/2015

- Create a concept for the planned Facebook activities.

- If the effort is justified: create the Facebook page and run the page.

2016-2018

- Continue to run the page.

#### Public events

2014/2015

- Obtain and maintain an overview of all public events in which we could participate.

- Organise the CHEOPS children drawing event during the partial eclipse day

- March 22nd: “Treffpunkt” ETH City (provisional)

- April 20th: Geneva bus arrives in Bern. Public lecture of Michel Mayor, University of Geneva

- September 5th: public event initiated in the framework of the 200th Jubilee of the National Academy of Natural Sciences.

- September 5th: Stellarium Gornergrat Show for Foundation Members of the High Alpine Research Station Jungfraujoch and Gornergrat.

2016-2018

- Create at least 2 public events per year.

#### Museums & Exhibitions

To reach the general public we will collaborate with museums and other exhibitors, such as shopping centres.

2014/2015

- Exhibition at the Musée des sciences naturelles in Geneva. In March 2015 the exhibition about Exoplanets will be opened and last for an entire year.

- Participate in already existing activities being carried out at different institutions
- Stellarium Gornergrat
- Physiscope at UGE
- FocusTerra at ETHZ

- Travelling exhibition. Create a concept for a travelling exhibition, which can be used in museums and shopping, centres and look for potential exhibitors.

- Create the concept and for a new show for the Planetarium of the Swiss Transportation Museum in Lucerne.

2016-2018

- Participate in the exhibition «Fremde Welten» of the Swiss Space Museum (2016).

- Participate the renewed space exhibition of the Swiss Transportation Museum in Lucerne.

#### School classes (external)

2014/2015

- Activities related to the “Ferienpass” in different cantons

- Teaching activities: Create teaching activities in modular form for different school levels (combined with Gornergrat)

- Initiate a cooperation with IngCH (www.ingch.ch; Technikwochen) and/or Swissmem (www.tecmania.ch) TecDay (http://www.satw.ch/veranstaltungen/tecday/index)

2016-2018

- Create downloadable exhibition panels for schools

- Organise visits for school classes in institutes and observatories

- Support teacher’s training

#### Astronomy clubs

2014/2015

- March 20th/March 21st: Activities together with the Schweizerische Astronomische Gesellschaft SAG during the Solar Eclipse/«Nacht der Astronomie»

- August 14th to 16th: Exoplanet-Marathon at the Star Party, Gurnigel

2016-2018

- Support planned activities of astronomy clubs.

##### Activities for internal target groups

#### eNewsletter

2014-2018

- Publish the eNewsletter every 3 months

#### Website (with respect to internal audience)

2014/2015

- Further develop the web site and internal pages.

- Build the communication online planning

2016-2018

- We extend and maintain the content on the website continuously.

#### General Assembly

2014/2015

- Build team spirit

2016-2018

- Enforce team spirit

#### SNF

2014-2018

- Annual Report

- Site Visit

## 15.8 Budget

The budget for communication activities until May 2018 will be CHF 600’000.

All expenditure on communication activities must be coordinated with the University of Bern.

Expenses so far:

- Exhibition at the Musée des sciences: CHF 100’000

- Development of the design of the website: CHF 10’000

- CHEOPS Pins: CHF 4’000

Planned Expenses for 2015:

- Travelling exhibition: CHF 25’000

- Geneva Bus (Michel Mayor): CHF 5’000

## 15.9 Organisation

Each of the involved projects defines a person who is in charge of the communicative interests.

The two leading houses in Bern and Geneva coordinate the major announcements of the NCCR. However, on a working basis each institution involved in PlanetS can communicate independently of the others. In this case, the other institutions shall be informed in advance.

To achieve maximum transparency of communication activities, a central communication plan is prepared, which can be viewed and edited on the website by all who are in charge of communication. The plan contains media and outreach activities, events etc. and shows when it will happen and who is involved. It also provides the rules of engagement and guidelines to ensure a clear chain of internal and external communication processes that defines who within PlanetS is authorised to provide information to the different media and other external partners.

## 15.10 Evaluation

To ensure quality control, we work with defined evaluation periods. We are careful to evaluate our activities regularly and use the feedback to improve. A summary will be shown in the annual report.

## 15.11 Communication channels

#### Internal channels

- Website www.nccr-planets.ch

- DACE Platform

- eNewsletter

- General Assembly

- Colloquia etc.

#### External channels

- Website www.nccr-planets.ch

- Media Relations

- School programme

- Public events

- Museums & Exhibitions

- eNewsletter

- Social Media – Facebook, Youtube channel, Flickr etc.

- Livestream

- Contests & Public Participation

- Direct Mailing

- Online Magazine (e.g. www.issuu.com)

- eLearning (e.g. www.coursera.org)

ibrarian.phys.washington.edu/astro/index.php/Research:ChaNGa

(2013) She figures 2012 - Gender in research and innovation. [EU Commission - Working Document]

„Why So Few? Women in Science, Technology, Engineering, and Mathematics“, (2010) by Catherine Hill, Christianne Corbett & Andresse St. Rose. American Association of University Women

Research indicates that establishing responsibility for diversity (not just implementing training, mentoring and networking) is vital for increasing actual numbers of women in organisations.  Kalev, A., Dobbin, F., & Kelly, E. (2006). Best practices or best guesses? Assessing the efficacy of corporate affirmative action and diversity policies. American sociological review, 71(4), 589-617.

Lorenzo, M., Crouch, C. H., & Mazur, E. (2006). Reducing the gender gap in the physics classroom. American Journal of Physics, 74(2), 118-122.

National Research Council. (2009). Gender differences at critical transitions in the careers of science, engineering and mathematics faculty.  Washington, DC: National Academies Press.

ETH – data from all departments combined, retrieved Feb 3rd 2015 from http://www.equal.ethz.ch/gender_monitoring/gender_monitoring_2013/gender_monitoring_2013_EN

UBE – data from Fakultat Phil._Nat., retrieved Feb 3rd 2015 from http://www.gleichstellung.unibe.ch/unibe/qualitaet/gleichstellung/content/e3510/e4193/e4330/e4466/NAT_2013_Homepage_ger.pdf

UGE – data from Faculty of Sciences, retrieved Feb 5th 2015 from http://www.unige.ch/dadm/stat/files/3014/1700/9676/1.3_Sciences.pdf

UZH – data from Mathematisch-naturwissenschaftliche Fakultet, Mittelbau includes Assistierende, OberAssist., and Wissenschaftl. Mitarb.), retrieved Feb 4th 2015 from http://www.gleichstellung.uzh.ch/politik/gleichstellungsmonitoring/GLM_Datentabellen_2013.pdf